## Read Me
STROKE NETWORK OF SOUTHEASTERN ONTARIO
Regional Stroke Workplan 2023-2025
PRIORITY #1 - STROKE PREVENTION: Optimize Integrated Strategies for Secondary Stroke Prevention and Vascular Risk Factor Management PRIORITY #2 - HYPERACUTE: Sustain and enhance organized regional pathways for timely access to hyperacute treatment PRIORITY #3 - INTEGRATED INPATIENT CARE: Enhance integrated inpatient care for timely access, quality of care, and improved patient experience PRIORITY #4 - COMMUNITY: Enhance access to stroke rehabilitation and supports in the community to optimize recovery, the patient experience and community re-integration
The workplan supports the Canadian Best Practice Recommendations for Stroke Care.
The workplan aligns with Strategic Directions of CorHealth Ontario and the Ontario Health Business Plan.
Within each worksheet there are regional and local aspects to the plan with geographic distributions as follows:
*Regional Plan for Southeastern Ontario
*Quinte District Stroke Plan for the Counties of Hastings & Prince Edward (HPE)
*Kingston, Frontenac, Lennox & Addington Counties (KFL&A-KHSC)
*Kingston, Frontenac, Lennox & Addington Counties (KFL&A-KHSC/PCH)
*Leeds & Grenville Counties (L&G)
*Lanark County
Please scroll through the different worksheet tabs to read each priority
Please scroll within each worksheet to read regional and local plans within each priority of the care continuum
The final 2 worksheets cover the Regional Education Workplan and Leadership & Coordination Requirements
ALIGNMENT with Ontario Health
1. Reduce health inequities
2. Transform care with the person at the centre
3. Enhance clinical care and service excellence
4. Maximize system value by applying evidence
5. Strengthen Ontario Health's ability to lead

## Symbols
CHOOSE from LIST
improved; likely to achieve target
achieving target
worsening; target may still be achieved
improved; may achieve target
unchanged; may or may not achieve target
worsening; may not achieve target
improved; not likely to achieve target
unchanged; not achieving target
worsening; not likely to achieve target

## Progress Report
Stroke Network of SEO - 2023-25 Regional Stroke Workplan PROGRESS Report
Priority / Area |  | Objectives | Status | Progress Notes
RSSC PRIORITY #1: Optimize Integrated Strategies for Secondary Stroke Prevention and Vascular Risk Factor Management | R P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments. | CHOOSE from LIST
| R P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | CHOOSE from LIST
| R P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | CHOOSE from LIST
|  | Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | CHOOSE from LIST
| R P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | CHOOSE from LIST
| R P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | CHOOSE from LIST
| HPE P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | CHOOSE from LIST
| HPE P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | CHOOSE from LIST
| HPE P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | CHOOSE from LIST
|  | Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | CHOOSE from LIST
| HPE P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | CHOOSE from LIST
| HPE P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | CHOOSE from LIST
| KFL&A-KHSC P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | CHOOSE from LIST
| KFL&A-KHSC P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | CHOOSE from LIST
| KFL&A-KHSC P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | CHOOSE from LIST
|  | Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | CHOOSE from LIST
| KFL&A-KHSC P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | CHOOSE from LIST
| KFL&A-KHSC P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | CHOOSE from LIST
| L&G P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | CHOOSE from LIST
| L&G P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | CHOOSE from LIST
| L&G P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | CHOOSE from LIST
|  | Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | CHOOSE from LIST
| L&G P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | CHOOSE from LIST
| L&G P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | CHOOSE from LIST
| Lanark P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | CHOOSE from LIST
| Lanark P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | CHOOSE from LIST
|  | Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | CHOOSE from LIST
| Lanark P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | CHOOSE from LIST
|  | Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | CHOOSE from LIST
| Lanark P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | CHOOSE from LIST
| Lanark P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | CHOOSE from LIST
RSSC PRIORITY #2: Sustain and enhance organized regional pathways for timely access to hyperacute treatment | R H1 | Monitor & Sustain Regional/District Acute Stroke Protocol | CHOOSE from LIST
| R H2 | Update & Monitor Changes to Thrombolysis Delivery | CHOOSE from LIST
| R H3 | Monitor and Sustain Regional EVT Service | CHOOSE from LIST
| R H4 | Assist with Telestroke Reassessment at Brockville General Hospital (BrGH) | CHOOSE from LIST
| R H5 | Support continued implementation of the regional cerebral aneurysm coiling service at KHSC | CHOOSE from LIST
| R H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | CHOOSE from LIST
| HPE H1 | Monitor & Sustain District Acute Stroke Protocol | CHOOSE from LIST
| HPE H2 | Update & Monitor Changes to Thrombolysis Delivery | CHOOSE from LIST
| HPE H3 | Monitor and Sustain Quinte Access to Regional EVT Service | CHOOSE from LIST
| HPE H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | CHOOSE from LIST
| KFLA-KHSC H1 | Monitor & Sustain Regional Acute Stroke Protocol | CHOOSE from LIST
| KFLA-KHSC H2 | Update & Monitor Changes to Thrombolysis Delivery | CHOOSE from LIST
| KFLA-KHSC H3 | Monitor and Sustain Regional EVT Service | CHOOSE from LIST
| KFLA-KHSC H4 | Assist with Telestroke Reassessment at Brockville General Hospital | CHOOSE from LIST
| KFLA-KHSC H5 | Support continued implementation of the regional cerebral aneurysm coiling service at KHSC | CHOOSE from LIST
| KFLA-KHSC H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | CHOOSE from LIST
| L&G H1 | Monitor and Sustain Local Access to Regional Acute Stroke Protocol | CHOOSE from LIST
| L&G H3 | Monitor and Sustain Local Access to Regional EVT Service | CHOOSE from LIST
| L&G H4 | Reassess Telestroke Readiness at Brockville General Hospital | CHOOSE from LIST
| L&G H5 | Support continued local access to the regional cerebral aneurysm coiling service at KHSC | CHOOSE from LIST
| L&G H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | CHOOSE from LIST
| Lanark H1 | Monitor & Sustain Local Access to Regional Acute Stroke Protocol | CHOOSE from LIST
| Lanark H3 | Monitor and Sustain Local Access to Regional EVT Service at Regional Stroke Centre | CHOOSE from LIST
| Lanark H5 | Support continued local access to the regional cerebral aneurysm coiling service at KHSC | CHOOSE from LIST
| Lanark H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | CHOOSE from LIST
RSSC PRIORITY #3: Enhance integrated inpatient care for timely access, quality of care, and improved patient experience | R I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | CHOOSE from LIST
| R I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | CHOOSE from LIST
|  | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Participate in stroke distinction program Support teams to develop action plans to facilitate QI | CHOOSE from LIST
| R I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | CHOOSE from LIST
| R I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | CHOOSE from LIST
| HPE I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | CHOOSE from LIST
| HPE I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | CHOOSE from LIST
|  | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Participate in stroke distinction program Support teams to develop action plans to facilitate QI | CHOOSE from LIST
| HPE I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | CHOOSE from LIST
| HPE I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | CHOOSE from LIST
| KFLA-KHSC-PCH I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | CHOOSE from LIST
| KFLA-KHSC-PCH I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | CHOOSE from LIST
|  | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Participate in stroke distinction program Support teams to develop action plans to facilitate QI | CHOOSE from LIST
| KFLA-KHSC-PCH I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | CHOOSE from LIST
| KFLA-KHSC-PCH I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | CHOOSE from LIST
| L&G I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | CHOOSE from LIST
| L&G I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | CHOOSE from LIST
|  | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Support teams to develop action plans to facilitate QI | CHOOSE from LIST
| L&G I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | CHOOSE from LIST
| L&G I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | CHOOSE from LIST
| L I1 | Continue to facilitate an integrated stroke patient pathway to enhance timely local access to acute stroke care in Brockville and timely repatriation to rehabilitation in Perth (access and flow) | CHOOSE from LIST
| L I2 | Deliver quality expert stroke rehabilitation (core best practices) a) Support expertise in delivery of essential core stroke best practices in stroke rehabilitation | CHOOSE from LIST
|  | Deliver quality expert stroke rehabilitation (core best practices) b) Support stroke rehab team in quality improvement | CHOOSE from LIST
| L I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | CHOOSE from LIST
| L I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | CHOOSE from LIST
RSSC PRIORITY #4: Enhance access to stroke rehabilitation and supports in the community to optimize recovery, the patient experience and community re-integration | R C1 | Support local providers to innovate in the delivery of new, enhanced and integrated Community Stroke Rehab (CSR) Programs to align with the provincial CSR Model of Care | CHOOSE from LIST
|  | Participate in and inform the CorHealth Ontario CSR Project Data Strategy | CHOOSE from LIST
|  | Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | CHOOSE from LIST
| HPE C1 | Support local providers to innovate in the delivery of new, enhanced and integrated CSR Programs to align with the provincial CSR Model of Care | CHOOSE from LIST
|  | Participate in and inform the CorHealth Ontario CSR Project Data Strategy | CHOOSE from LIST
|  | Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | CHOOSE from LIST
| KFL&A-PCH C1 | Support local providers to innovate in the delivery of new, enhanced and integrated CSR Programs to align with the provincial CSR Model of Care | CHOOSE from LIST
|  | Participate in and inform the CorHealth Ontario CSR Project Data Strategy | CHOOSE from LIST
|  | Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | CHOOSE from LIST
| L&G C1 | Support local providers to innovate in the delivery of new, enhanced and integrated CSR Programs to align with the provincial CSR Model of Care | CHOOSE from LIST
|  | Participate in and inform the CorHealth Ontario CSR Project Data Strategy | CHOOSE from LIST
|  | Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | CHOOSE from LIST
| L C1 | Support local providers to innovate in the delivery of new, enhanced and integrated CSR Programs to align with the provincial CSR Model of Care | CHOOSE from LIST
|  | Participate in and inform the CorHealth Ontario CSR Project Data Strategy | CHOOSE from LIST
|  | Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | CHOOSE from LIST
| R C2 | Complete Community Re-integration Consultation | CHOOSE from LIST
| R C3 | Person-Centred Skilled Stroke Care & Rehabilitation: a)Sustain and build upon regional approach to Aphasia Supportive Conversation Groups. | CHOOSE from LIST
|  | Person-Centred Skilled Stroke Care & Rehabilitation: b) Support stroke expertise and best practice in the Long Term Care and community settings | CHOOSE from LIST
| R C4 | Support Individual Well-Being & Meaningful Engagement: a) Sustain and enhance Community Stroke Support Services to meet diverse needs | CHOOSE from LIST
|  | Support Individual Well-Being & Meaningful Engagement: b) Self-management | CHOOSE from LIST
|  | Support Individual Well-Being & Meaningful Engagement: c) Sustain and enhance Community Stroke Specific Exercise Programs | CHOOSE from LIST
| R C5 | Community Co-Navigation and Access to Services: | CHOOSE from LIST
Leadership & Coordination | R L&C1 | Develop Leaders A. Plan successions to build and mentor new leaders within the regional stroke program | CHOOSE from LIST
|  | B. Develop Stroke Team leadership skills and sustain engagement | CHOOSE from LIST
| R L&C2 | Build and Sustain a resilient Stroke Network that is flexible and responsive to a changing provincial context. | CHOOSE from LIST
| R L&C3 | Monitor quality and evaluate stoke care performance in the SE against provincial and national standards / best practice recommendations | CHOOSE from LIST
| R L&C4 | Develop, monitor and implement Regional Stroke Workplan based on RSSC priorities and program mandate | CHOOSE from LIST
| R L&C5 | Engage stakeholders in workplan priorities through an effective communication strategy | CHOOSE from LIST
| R L&C6 | Sustain governance infrastructure for effective program oversight and stakeholder engagement | CHOOSE from LIST
| R L&C7 | Build Regional Communication and Accountability Links with Ontario Health - CorHealth Ontario, Ontario Health East Region and OHTs | CHOOSE from LIST
| R L&C8 | Sustain and grow partnership and collaboration with other Regional, Provincial and National Organizations and Networks to advance stroke care | CHOOSE from LIST
| R L&C9 | Manage fiscal and human resources within given parameters | CHOOSE from LIST
| R L&C10 | Contribute to innovation and knowledge translation in stroke care | CHOOSE from LIST

## StrokePrevention
Stroke Network of Southeastern Ontario - Regional Stroke Workplan 2023-2025
RSSC PRIORITY #1: Optimize integrated strategies for secondary stroke prevention and vascular risk factor management
Regional | Objectives | REGIONAL Implementation Activities - Stroke Prevention & Risk Factor Management | Timeline | Lead/Contact
R P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | ● Re-establish local links with primary care (PC) with respect to vascular health and stroke prevention - link to local PC Infographic for Secondary Stroke Prevention - visit/meet with 1-2 PC teams with local SPC team member(s) - promote updated PC resources within the Ontario Stroke Prevention Core Elements' Toolkit on CorHealth Ontario website - promote vascular health in alignment with local OHT plans (e.g., FLA OHT-Wellness/Equity group, LLG PC Council, HPE Social Determinants of Health group) ● Explore and inform Integrated Stroke pathways within OHTs in relation to prevention ● Host joint PC/SPC engagement/education event re prevention in each local area: Brockville, Perth, Kingston, Belleville ● Ensure completion of core best practice care processes for TIA/minor stroke within EDs - ensure linking to local SPC on discharge from EDs ● Continue to link with Stroke Prevention leads in CE and Champlain to share prevention innovations within Eastern region | Ongoing 2023/25 2 events in Year 1 2 event in Year 2 Ongoing 2023/25 | C.Murphy/SPC leads C.Murphy/C.Martin H.Jenkins/C.Murphy C. Murphy/SPC Leads C. Murphy
R P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | ● Adopt the 2022 Provincial SPC triage algorithm across the SE. ● Redesign how SPCs monitor wait times using new triage algorithm scales and targets ● Advise on work of provincial Prevention Task Group e.g. updated SPC resources, standardized use of data, evaluation of SPC resources ● Work with region-wide ED & Imaging providers to ensure best practice timely imaging for TIA/Minor stroke (CTA, MRI) | April 2023 2023/24 Ongoing 2023/25 | C.Murphy/SPC Leads C.Martin/C.Murphy/ SPC Leads C.Murphy Dr.Jalini/SPC Leads
| Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | ● Continue to incorporate hybrid platforms into clinic workflow (video, telephone & in-person visits); ● Make use of provincial SPC Virtual Care Resources | Ongoing 2023/25 | C.Murphy/ SPC leads
| Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | ● Support SPCs in education strategies to build pool of stroke prevention experts ● Strengthen regional connection between the SPC teams ● Support strategies to grow adequate pool of stroke prevention experts and to plan for successions | Ongoing 2023/25 | C. Murphy/H.Jenkins /SPC Leads C. Murphy/Dr Jin/SPC Leads
R P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | ● Support the IIPCT to sustain Indigenous blood pressure screening services through re-visiting use of community volunteers for outreach ● Continue to link with other vascular group(s) in supporting IIPCT (e.g., Indigenous Diabetes Circle, CKD screening) | March 2025 Ongoing 2023/25 | C. Murphy/H.Jenkins C.Murphy
| Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | ● Adapt local Secondary Stroke Prevention Patient Discharge Summary for use in SPCs and on transition to primary care ● For discharged inpatients, facilitate uptake of Stroke Information Package in SPCs adding current prevention resources ● For patients with TIA/minor stroke, facilitate inclusion of current prevention resources in educational packages ● Build from Anticoagulation Adherence Summary to complete a patient education resource to address barriers | March 2025 | C.Murphy/SPC Leads Dr. Jalini/C.Murphy
R P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | ● Increase awareness of SPC providers of community prevention resources & services including Indigenous services/resources ● Re-visit connection with HCCSS about Vascular Health Directory on southeasthealthline.ca. ● Re-visit physical activity and smoking cessation maps with Public Health ● Ensure community paramedicine teams are aware of the stroke prevention supports and resources ● Link with FLA, HPE and LLG OHTs to enhance awareness of resources and programs ● Support SPC providers to attend Indigenous cultural safety courses | Ongoing 2023/25 | C.Murphy C.Murphy/H.Jenkins C.Martin/C.Murphy H.Jenknis
R P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | Inform LUMEO and begin to monitor impact re: ● Communication links between providers including linkage with primary care sites piloting LUMEO ● Order sets ● Documentation templates ● SPC pathways and workflows to help reduce manual tracking and improve automation ● Assessment and screening tools ● Key quality indicators and care outcomes | 2023/25 and as per LUMEO timelines | C.Murphy/C.Martin/ SPC Leads
HPE | Objectives | HPE - QUINTE DISTRICT - Local Implementation Activities - Stroke Prevention & Risk Factor Management | Timeline | Lead/Contact
HPE P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | ●ensure strong local links with primary care (PC) with respect to vascular health and stroke prevention - promote updated PC resources within the Ontario Stroke Prevention Core Elements' Toolkit on CorHealth Ontario website - promote vascular health in alignment with local OHT plans (i.e. HPE Social Determinants of Health group) ● Explore and inform Integrated Stroke pathways within OHTs in relation to prevention. ●Ensure linkage to Quinte Health SPC on discharge from ED. | Ongoing 2023/25 | SPC Team District Stroke Coordinator
HPE P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | ● Adopt the 2022 Provincial SPC triage algorithm. ●Ensure best practice for timely imaging for TIA/Minor stroke (CTA, MRI) between ED and DI. | 2023 Ongoing 2023/25 | SPC Team Code Stroke Team
| Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | ● Continue to incorporate hybrid platforms into clinic workflow (video, telephone & in-person visits). ● Make use of provincial SPC Virtual Care Resources. | Ongoing 2023/25 | SPC Team
| Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | ● identify and apply education strategies to build pool of stroke prevention experts and support succession planning. ● Focus on physician recruitment to support SPC activity. ● Connect regularly with other SPC's in the region and province to share expertise and ideas. | Ongoing 2023/25 | SPC Team Patient Services Manager, ISU and Rehab Medical Director Program Director
HPE P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | ● Continue to link with other vascular group(s) in supporting IIPCT (e.g., Indigenous Diabetes Circle, CKD screening). ● For patients with minor stroke/TIA,add current prevention resources to education packages if benefit to patients is determined. ● Advise regional initiative to build from Anticoagulation Adherence Summary to complete a patient education resource to address barriers to adherence. | Ongoing 2023-2025 | SPC Team Patient Services Manager, ISU and Rehab PPL District Stroke Coordinator
| Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | ● Shadowing experience for ISU Physician Assistants and Nurse Practitioners in SPC to build competencies. ● Determine and initiate a QI initiative for improving anticoagulant rates for patients with stroke/TIA discharged with Afib. | Ongoing starting in 2023 | SPC Team Medical Director PPL DSC
HPE P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | ● Increase awareness of SPC providers of community prevention resources & services including Indigenous services/resources. ● Connect with CCSH Stroke Support Groups and Quinte Day Rehab to ensure a timely and seamless distribution of stroke survivor education materials. ● Re-visit expansion of Ocean tablets to support virtual care, visits with patients and preserve flow in Stroke Clinic. ● Encourage and support participation of SPC staff in Indigenous culture safety courses. ●Continue to share new stroke prevention supports and resources with HPE community paramedicine teams. | Ongoing 2023-2025 | SPC Team Virtual Care Team IS Manager DSC
HPE P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | ● Provide input to LUMEO and begin to monitor impact locally re: ● Communication links between providers ● Order sets ● Documentation templates ● SPC pathways and workflows to help reduce manual tracking and improve automation ● Assessment and screening tools ● Key quality indicators and care outcomes. | 2023-2024 | SPC Team Patient Services Manager, ISU and Rehab DSC
KFL&A | Objectives | KFL&A-KHSC- Local Implementation Activities - Stroke Prevention & Risk Factor Management | Timeline | Lead/Contact
KFL&A-KHSC P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | ● Ensure Stroke Prevention Clinic physician letters are communicated to primary care physicians in a timely manner post clinic visit ● Monitor uptake of Revised Orders sets for ED High Risk TIA patients in EDIS ● Update TIA assessed in the ED Care Guideline ● Continue to advocate for vascular primary prevention focus through FLA OHT (e.g., Wellness and Equity Group) | Ongoing 2023/25 December 2023 2023/25 | Dr. Jalini/P.Christie C.Murphy/C.Martin
KFL&A-KHSC P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | ● Replace existing triage process with the 2022 Provincial Stroke Prevention Clinic Algorithm ● Provide education & information to the Interprofessional Team to promote consistency in the triage process - Include education in the orientation of new nursing and clerical staff ● Incorporate Triage Algorithm into updated SPC care guideline | September 2023 December 2023 | P.Christie/C.Murphy P.Christie/Dr.Jalini
| Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | ● Continue to determine best method / clinical setting for SPC patient assessment - In person, E visit, telephone appointments, as per patient circumstances and medical college requirements. Consider hybrid model of care as per individual circumstances. ● Continue to collect and monitor monthly volume of referrals to SPC and wait time from referral date to first clinic visit | Ongoing 2023/25 | P.Christie/Dr. Jalini SPC team/C.Martin
| Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | ● Consider re-establishing the Regional SPC Nurses Group - Contact the Regional SPC nurses to determine interest and timing, considering clinic workloads ● Continue to participate in annual Regional SPC Team half day meeting and other Regional Stroke education opportunities ● Continue to build on existing orientation plan and educational resources for new nursing staff (Part time RN), allowing adequate time for mentorship to occur | September 2023 Annually 2023-25 2023/25 | P.Christie SPC team P.Christie
KFL&A-KHSC P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | ● Support connections with Indigenous Interprofessional Primary Care Team (IIPCT) ● Ensure KHSC SPC staff are aware of funded opportunities for Indigenous cultural safety training (included in Regional Education Plan) | Ongoing 2023/25 2024 | SPC team H.Jenkins
| Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | ● Continue to update SPC education folder with new written material as new information and resources become available ● Consider mailing folders to patients who have been assessed in SPC by E visit or telephone appointments ● Ensure that newly diagnosed patients with Atrial Fibrillation who have been prescribed Warfarin receive KHSC publication - "About Warfarin Information for Patients" ● Continue to depend on Community Pharmacists to provide comprehensive medication instruction for all newly prescribed medications to all patients ● Direct patients to the Heart and Stroke Foundation Consumer Website to access public education and information on prevention, risk factors, family health, treatments, support, and interactive assessment tools ● Advise development & assist with completion of patient resource to address barriers to anticoagulation | Ongoing 2023/25 March 2024 Ongoing 2023/25 March 2025 | SPC team Dr. Jalini
KFL&A-KHSC P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | ● Review and update community resources- current contact information and description of services ● Increase knowledge of local resources for vulnerable patients - Identify local resources - who to call if needed to assist. Issues to consider: elderly with limited mobility, family support, financial resources, no primary care provider - Determine with organizations such as 'In from the Cold' and 'Integrated Care Hub' how to locate patients who are homeless - transient with no permanent address or contact information & patients with mental health challenges to arrange clinic appointments and diagnostic testing | Ongoing 2023/25 | SPC team
KFL&A-KHSC P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | ● Participate in Regional Health Information System LUMEO series of meetings focused on Stroke Prevention ● Advocate for inclusion of all members of the Interprofessional Team and to be suitable for each unique environment ● Inform LUMEO and begin to monitor impact re: ● Communication links between providers; including primary care sites piloting LUMEO ● Order sets ● Documentation templates (SPC power plan) ● SPC pathways and workflows to help reduce manual tracking and improve automation ● Assessment and screening tools ● Key quality indicators and care outcomes | 2023-24 (start Feb 2023) | P. Christie/ C.Murphy P.Christie/Dr. Jalini/ C.Martin/C.Murphy
L&G | Objectives | LEEDS & GRENVILLE - Local Implementation Activities - Stroke Prevention | Timeline | Lead/Contact
L&G P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | ● Re-establish local links with primary care (PC) with respect to vascular health and stroke prevention through implementing local SPC pamphlet - link to local PC Infographic on BGH site for Secondary Stroke Prevention/Re-share local infographic with local PC - visit/meet with 1-2 PC teams with stroke network team members. Implement e-Referral to support ease of referrals from PC. Link to Ontario Stroke Prevention Core Elements' Toolkit on CorHealth Ontario website - participate in PC/SPC engagement/education event ● Improve information available on BGH website to link patients and providers to resources | 2023 (e-referral) 2023/25 PC visits and promotion of SPC and Infographic 2024 2023/25 | D.Andress/M. Smith-Mutton
L&G P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | ● Monitor use of 2022 Provincial SPC triage algorithm within BGH SPC ● Review current process for monitoring wait times using new triage algorithms and targets. ● Work with Stroke Network and BGH ED, SPC, and DI to ensure best practice and timely imaging for stroke/TIA/Minor stroke. Review best practices in utilizing CT, Ultrasounds, and MRI in stroke care to begin to plan for MRI on site, and implement new process for accessing MRI (2024) | 2023/24 review new algorithm and tracking 2024 MRI Algorithm | D. Andress/M. Smith-Mutton Denis Arseneau/ Chief of ED and DI
| Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | ● Implement online referral for ease of access by PC providers and improved communication between BGH and patient regarding appointments and follow ups ● Review processes in place with virtual care platforms to identify opportunities for improvements. Explore use of Provincial Virtual Care Resources. | Ongoing 2023/25 | M.Smith-Mutton/ D. Andress/ D.Henson
| Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | ● Develop Stroke Champions within ED/SPC/ISU/DI ● Recruit and retain physician leader to SPC | Ongoing 2023/25 | M. Smith-Mutton/D. Henson/ B. Kontes/D. Arseneau
L&G P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | ● Educate and provide education materials on knowing your vascular risk factors , how to screen , monitor and report changes to your primary health care provider ● Learn and connect to the Indigenous Interprofessional Primary Care Team who provide outreach across South East ● Take an Indigenous Cultural Safety Course | 2023/25 ongoing | D. Andress H. Jenkins/ SPC team
| Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | ● Adapt Secondary Stroke Prevention Patient Discharge Summary for use with implementation of Cerner ● Review opportunities to update and improve Stroke Prevention Resources provided to patients upon discharge from SPC and ISU ● Advise on draft anticoagulation adherence patient resource | 2023/25 | D. Andress/J.Lynch
L&G P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | ● Ensure local resources to support patients and families following Stroke and TIA are shared with patients and patients are referred as appropriate. Look at opportunities to increase warm handoffs where able | Ongoing 2023/25 | D. Andress/J.Lynch
L&G P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | ● Assist in the development of LUMEO standardized assessment of patients in the SPC setting, order sets specific to SPC and documentation templates | Ongoing 2023/25 | D. Andress/ M.Smith-Mutton/ D. Henson
Lanark | Objectives | LANARK - Local Implementation Activities - Stroke Prevention & Risk Factor Management | Timeline | Lead/Contact
L P1 | Enhance linkages to stroke prevention best practices in primary care and Emergency Departments | ● Continue to strengthen communication linkages & warm handover between primary care/VPC: - Refer Primary Care to local PC Infographic for Secondary Stroke Prevention; update infographic with changing best practices - Visit/meet with at least 1 PC team to review VPC processes and highlight current stroke best practices - Promote updated PC resources within the Ontario Stroke Prevention Core Elements' Toolkit on CorHealth Ontario website - Participate in planning/delivery of PC/SPC engagement/education event re prevention in Perth ● Ensure TIA referral to VPC from ED - Continue to follow up with ED if referral not received after checking ED census - Complete audit on ED charts and meet with decision support/patient records lead to compare data to ensure data quality and have further follow up with ED, as needed - Continue to check on ED to ensure they have supply of VPC packages including staff info (referral form, diagnostic requisitions) ● Update TIA d'ced from ED collaborative care plan-re-engage ED, DI and pharmacy in the update | Ongoing 2023/25 March 2025 2023/24 Ongoing 2023/25 Sept 2023 Ongoing 2023/25 2023/25 | T. Thorne/S/ Luco H.Jenkins/VPC team T.Thorne/ S.Luco/ED Lead physician
L P2 | Enhance SPC triage, efficiencies & expertise a) Maximize triage processes | ● Implement new Provincial SPC triage algorithm. Incorporate new algorithm into triage process including collection and reporting of wait time data - Include education with nurse and physician covering VPC - Participate in evaluation of provincial triage algorithm ● Continue to submit and monitor wait times to VPC incorporating new triage wait time levels. QI if increase in wait times ● Ensure vascular intra/extra cranial CTA concurrently done with CT in ED. Monitor patients not receiving best practice imaging in ED prior to discharge (see hyperacute LH1); follow up with ED team, radiologists, and decision support/patient records to compare data quality and have further follow up with ED; meet with radiology group re TIA best practices & collaboratively develop process guide re imaging timelines ● Monitor wait times for echocardiograms given new diagnostic clinic in Carleton Place; consider development of decision making guide for echos | September 2023 Ongoing 2023/25 2023/24 | T.Thorne/C.Murphy T.Thorne S. Luco/T.Thorne w ED/Radiology teams VPC team
| Enhance SPC triage, efficiencies & expertise b) Enhance SPC workflow with virtual care | ● Continue to do telephone follow-ups and monitor for effectiveness ● Review and consider making use of provincial virtual care resources and consider opportunities to overcome barriers for video visits | Ongoing 2023/25 | S.Luco/T.Thorne
| Enhance SPC triage, efficiencies & expertise c) Build pool of SPC experts | ● Continue to ensure nursing/physician coverage of VPC ● Continue to provide orientation with new nurses covering the VPC ● Continue to support learning of covering physician ● Participate in regional SPC nurse meeting when restarted ● Continue to participate in annual regional SPC Team half day meeting sharing of case studies | Ongoing 2023/25 | PSFDH Leaders T.Thorne S.Luco T. Thorne VPC team
L P3 | Support efforts to improve Vascular Risk Factor screening and management a) Support Indigenous Blood Pressure screening | ● Learn about and connect Indigenous patients with vascular health supports including regional Indigenous Interprofessional Primary Care Team ● Attend an indigenous cultural safety course | Ongoing 2023/25 | VPC team H. Jenkins
| Support efforts to improve Vascular Risk Factor screening and management b) Enhance use of patient education tools | ● Continue to provide patients with package of standard written material to patients and add new info and resources as they become available. Direct patients to available appropriate on-line resources (e.g., Heart and Stroke Foundation & Hypertension Canada) ● Consider adapting provincial Secondary Stroke Prevention Patient Discharge Summary & add to package of materials ● For discharged inpatients, continue to ensure patient has standard Stroke Information Package adding current prevention resources ● Continue to check with ED to ensure that they have a supply of VPC stroke packages; update packages accordingly with new resources ● Advise on development of Anticoagulation Adherence Summary to address barriers | Ongoing 2023/25 March 2024 Ongoing 2023/25 2023/25 | T.Thorne T.Thorne/S.Luco
L P4 | Enhance SPC awareness to navigate local self management and prevention resources, and local community programs | ● Continue to connect patients to community prevention resources & services including Indigenous services/resources ● Review patient Stroke Prevention Info Package and ensure community resources and contact info are up to date ● Refer patients including fragile populations to Rideau Community Health Services for support services and help with navigating the system, as needed | Ongoing 2023/25 | T.Thorne
L P5 | Advise LUMEO team on embedding stroke prevention best practices into LUMEO system | ● Participate in LUMEO series of meetings focused on Stroke Prevention (e.g., advise on power plan) ● Inform LUMEO and begin to monitor impact re: ● Communication links between providers ● Order sets ● Documentation templates ● SPC pathways and workflows to help reduce manual tracking and improve automation - learn about outcome of primary care sites piloting LUMEO- linkage between primary care & SPCs ● Assessment and screening tools ● Key quality indicators and care outcomes | 2023/24 (start Feb 2023) | T.Thorne/C.Murphy VPC team

## Hyperacute
Stroke Network of Southeastern Ontario - Regional Stroke Workplan 2023-2025
RSSC PRIORITY #2: Sustain and enhance organized regional pathways for timely access to hyperacute treatment
Regional | Objectives | REGIONAL Implementation Activities - Hyperacute Care | Timeline | Lead/Contact
R H1 | Monitor & Sustain Regional/District Acute Stroke Protocol | ● Sustain Regional Acute Stroke Protocol (RASP) and related reporting ● Update local ASP processes with new emerging evidence (e.g., time windows, TNK, imaging) ● Facilitate and support education & refreshers re updated hyperacute best practices - ACT-FAST including access to provincial resources - LAMS in extended time window ● Support QI initiatives as needed in response to data & emerging best practices ● Monitor timely access to vascular imaging using regional dashboard ● Renew/Sustain contracts with RAPID AI at Quinte Health and KHSC | Ongoing 2023/25 & as evidence emerges | C.Murphy/C.Martin C. Murphy/T. Wing C.Martin w Imaging Leads
R H2 | Update & Monitor Changes to Thrombolysis Delivery | ● Update processes and order sets for TNK delivery as per emerging evidence ● Share learnings with other providers ● Sustain 30 min DTN at KHSC-KGH and QH-Belleville | December 2023 2023/24 Ongoing 2023/25 | C.Murphy/M.Roblin Dr. Jin (KHSC)/ M.Roblin/I.Manzer (QH)
R H3 | Monitor and Sustain Regional EVT Service | ● Update processes and order sets for EVT delivery as per emerging evidence ● Sustain EVT and ASP reporting processes and facilitate QI as needed through EVT Workgroup - review EVT outcomes q6 months; include 6-24 h timeframes; update graphs for review of trends - report EVT process times & outcomes annually w BrGH & QH;consider PSFDH & LACGH as volumes ↑ - support QI initiatives as needed in response to data & emerging evidence ● Support QH-Belleville progression to 45 min DIDO time ● Sustain QH-Belleville flow algorithm & transfer algorithm; update as needed | 2023/25 At 6 mos EVT workgroup meetings March 2025 Ongoing 2023/25 & as evidence emerges | C.Murphy/Dr. Jin C. Martin/Dr. Jin/C. Murphy M.Roblin/I.Manzer/A.Samis M.Roblin/C.Murphy
R H4 | Assist with Telestroke Reassessment at Brockville General Hospital (BrGH) | ● Engage executive leaders (VP and COS) at BrGH and KHSC; review readiness and barriers ● Support ED, Critical Care & IM physician engagement in readiness assessment ● Host Engagement meeting with clinical leaders including physicians & administrators from DI, ED, CC, ISU ● Assist BrGH leaders to update the CorHealth Ontario Telestroke readiness document ● Validate the barriers to telestroke implementation. ● Map out key areas of focus to begin to address barriers ● Explore contract with RAPID AI at BrGH | September 2023 December 2023 March 2024 December 2023 2024 2024 | C.Martin/D.Henson Dr.Jin/BrGH COS C.Murphy/H.Jenkins with BrGH leads C.Murphy with BrGH leads C.Martin/BrGH DI leads
R H5 | Support continued implementation of the regional cerebral aneurysm coiling service at KHSC | ● Continue to support KHSC in updating funding allocation for ruptured and unruptured coiling ● Monitor data quality with KHSC teams ● Continue to contribute to and promote KHSC results in CCSO Intracranial Aneurysm Care Scorecard ● Support coordination and updating clinical processes as needed ● Support development of KHSC SAH order set for those undergoing coiling | Ongoing 2023/25 September 2023 | C. Martin C. Martin/C.Murphy C. Murphy/N. Lawler and Dr. Cook/Tampieri
R H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | Inform LUMEO and begin to monitor impact re: ● Workflows and protocols ● Order sets ● Documentation templates ● Assessment and screening tools ● Key quality indicators and care outcomes ● Communication links between providers | Ongoing 2023/25 & as evidence emerges | C.Murphy/C.Martin/Dr Jin with ED Leads and LUMEO team
HPE | Objectives | HPE - QUINTE DISTRICT - Local Implementation Activities - Hyperacute Care | Timeline | Lead/Contact
HPE H1 | Monitor & Sustain District Acute Stroke Protocol | ● Sustain Regional Acute Stroke Protocol (RASP)/Code Stroke and related reporting. ● Update local ASP/Code Stroke processes with new emerging evidence (e.g., time windows, TNK, imaging). ● Facilitate and support education & refreshers re updated hyperacute best practices - ACT-FAST including access to provincial resources - LAMS in extended time window ● Identify and support QI initiatives as needed in response to data & emerging best practices. ● Monitor timely access to vascular imaging using regional dashboard. ● Renew/Sustain contracts with RAPID AI at Quinte Health. | ongoing 2023-2025 TNK- 2023 | Code Stroke Team DSC Stroke Resource Nurse Professional Practice Patient Services Managers- ED, DI
HPE H2 | Update & Monitor Changes to Thrombolysis Delivery | ● Plan and implement for use of TNK as thrombolytic treatment. ● Update processes and order sets for TNK delivery. ● Monitor effectiveness and efficiency of use of TNK. | 2023-2024 | Stroke Medical Leadership Program Director Professional Practice DSC Stroke Resource Nurse
HPE H3 | Monitor and Sustain Quinte Access to Regional EVT Service | ● Identify and carry out measures to achieve and sustain 45' DIDO time or better at BGH. ● Work with SNSEO to sustain Quinte Health-Belleville flow algorithm & transfer algorithm; update as needed. | Ongoing 2023-2025 | Code Stroke Team Program Director Stroke Resource Nurse DSC Stroke Resource Nurse Professional Practice Patient Services Managers- ED, DI
HPE H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | Inform LUMEO and begin to monitor impact re: ● Workflows and protocols ● Order sets ● Documentation templates ● Assessment and screening tools ● Key quality indicators and care outcomes ● Communication links between providers | 2023-2024 | ED Leads DSC
KFL&A | Objectives | KFL&A-KHSC- Local Implementation Activities - Hyperacute | Timeline | Lead/Contact
KFL&A-KHSC H1 | Monitor & Sustain Regional Acute Stroke Protocol | ● Update processes re KHSC-KGH Acute Stroke Protocol (ASP), KHSC-HDH Regional Acute Stroke Protocol (RASP) and KGH Internal ASP with new emerging evidence (e.g., time windows, TNK, imaging) ● Deliver education, refreshers & support communication re ASP and hyperacute best practices - cardiac monitoring - ACT-FAST in KGH ED including access to provincial resources - Awareness of paramedic LVO screen-LAMS in extended time window - Internal ASP with RACE team & new hires - Explore potential to utilize LMS for Internal Stroke Protocol education ● Participate in QI initiatives as needed in response to data & emerging best practices ● Continue to participate in TNK & hyperacute-related research studies and facilitate knowledge translation ● Monitor timely access to vascular imaging in ED using regional stroke dashboard ● Renew/Sustain contracts with RAPID AI at KHSC-KGH site ● Continue to promote/update ED Repatriation Transfer Guide and Physician Guide for Regional Transfer | Ongoing 2023/25 & as evidence emerges | Dr. Jin/A.Dube/C.Hall/ C. Murphy E.Murphy/C.Murphy J. Carss/Paramedic Chiefs A.Dube/C.Hall Stroke neurologists/ Clinical Leads C.Martin w Imaging Leads Stroke neurologists/ C.Murphy
KFL&A-KHSC H2 | Update & Monitor Changes to Thrombolysis Delivery | ● Sustain 30 min KHSC-KGH DTN ● Monitor change in processes re TNK administration including TNK after non-contrast CT ● Monitor change re anticipated expanded thrombolysis time window to 9 hours for select cases ● Update processes for IV thrombolysis as per emerging evidence | Ongoing 2023/25 & as evidence emerges | Stroke neurologists/ Clinical Leads
KFL&A-KHSC H3 | Monitor and Sustain Regional EVT Service | ● Sustain EVT process times: Door to Puncture < 60 mins and Door to Reperfusion < 90 mins ● Update processes and order sets for EVT delivery as needed to align with emerging evidence ● Participate in EVT workgroup meetings and continue to share ideas to improve processes, if required ● Sustain EVT and ASP reporting processes and facilitate QI as needed - Review EVT outcomes q6 months; include >6 hour timeframes; update graphs for review of trends - Implement QI initiatives as needed in response to data & emerging evidence ● Continue to monitor and improve door to CT times (target < 15 mins) | Ongoing 2023/25 At 6 mos EVT workgroup meetings Ongoing 2023/25 & as evidence emerges | Stroke Neurologists/ Clinical Leads/C.Murphy EVT Workgroup C.Martin/A.Jin/C.Murphy EVT Workgroup
KFL&A-KHSC H4 | Assist with Telestroke Reassessment at Brockville General Hospital | ● KHSC executive leaders (VP and COS) to engage with BrGH leaders re barriers to Telestroke ● Share/collaborate on need to build hyperacute capacity & potential facilitators for telestroke readiness ● Participate in engagement meeting with BrGH clinical leaders including physicians & administrators from DI, ED, CC, ISU | April - September 2023 March 2024 | Dr. Jin/KHSC Executive Leads/C.Martin Dr. Jin/C.Murphy/H.Jenkins
KFL&A-KHSC H5 | Support continued implementation of the regional cerebral aneurysm coiling service at KHSC | ● Continue to deliver coiling program, improving access across neurosurgical catchment area ● Continue to support allocation of budget for ruptured and unruptured coiling ● Monitor data quality and outcomes ● Connect with larger KHSC group to assess progress & clinical process for elective coiling ● Continue to submit KHSC data to Critical Care Services Ontario Intracranial Aneurysm Care Scorecard ● Coordinate and update clinical processes as per emerging evidence/new technology ● Develop KHSC SAH order set for those undergoing coiling | Ongoing 2023/25 Annual 2023/25 Ongoing 2023/25 December 2023 | Drs. Cook/Tampieri/ N.Tompkins N/ Tompkins/C.Martin C.Martin/C.Murphy/Dr. Tampieri/Health Info Leads N. Lawlor/Dr Tampieri Dr. Tampieri Clinical Leads/ C. Murphy/N. Lawler/ Drs. Cook/Tampieri
KFL&A-KHSC H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | Inform LUMEO and begin to monitor impact re: ● Workflows and protocols ● Order sets ● Documentation templates ● Assessment and screening tools ● Key quality indicators and care outcomes ● Communication links between providers | Ongoing 2023/25 | Dr Jin/A.Dube/C.Hall/ Clinical Leads/ C.Murphy/C.Martin and LUMEO team
L&G | Objectives | LEEDS & GRENVILLE - Local Implementation Activities - Hyperacute | Timeline | Lead/Contact
L&G H1 | Monitor and Sustain Local Access to Regional Acute Stroke Protocol | ● Continue to embed education regarding ASP & ACT-FAST to sustain access to Stroke Protocols within LG ● Continue to work towards reducing barriers to Telestroke at BGH ● Continue to monitor data regarding imaging and SPC referrals and identify and address barriers quarterly ● Share data re use of ASP and local EVT data with stroke stakeholders | Ongoing 2023/25 | D. Henson/ D. Arseneau/ D. Roy/ Department Chiefs
L&G H3 | Monitor and Sustain Local Access to Regional EVT Service | ● Ensure education regarding EVT and ACT-FAST is embedded in program orientations. Update with emerging evidence | 2023/25 | D. Henson
L&G H4 | Reassess Telestroke Readiness at Brockville General Hospital | ● Continue to actively address barriers to implementation of Telestroke ● Update the CorHealth Ontario Telestroke readiness document | 2023/24 2024/25 | D. Henson/ Chief of Staff/ Dr. Steyn/Dr. Shenfield
L&G H5 | Support continued local access to the regional cerebral aneurysm coiling service at KHSC | ● Share provincial coiling data with teams as applicable ● Support continued local access to regional cerebral aneurysm coiling service at KHSC | Ongoing 2023/24 | Data Analysts
L&G H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | ● Continue to support LUMEO build by engaging with questions and meetings regarding build and implementation. | 2023/24 | SMEs and Clinical Leaders
Lanark | Objectives | LANARK - Local Implementation Activities - Hyperacute Care | Timeline | Lead/Contact
L H1 | Monitor & Sustain Local Access to Regional Acute Stroke Protocol | ● Ensure that ED staff and physicians have the tools required to utilize the Regional Protocol. ● Ensure that all suspect stroke patients have access to effective and timely treatment to help prevent or decrease permanent disability from stroke. | Ongoing 2023/25 | Chantal Menard
L H3 | Monitor and Sustain Local Access to Regional EVT Service at Regional Stroke Centre | ● Initiate appropriate and timely investigations and management of suspect stroke patients. | Ongoing 2023/25 | Chantal Menard
L H5 | Support continued local access to the regional cerebral aneurysm coiling service at KHSC | ● Continue to work in partnership with KHSC to support access to coiling services offered. | Ongoing 2023/25 | Chantal Menard
L H6 | Advise LUMEO team on embedding hyperacute stroke best practices into LUMEO system | ● Work with the LUMEO team to embed the Regional Stroke Protocol workflow/template in LUMEO, including Regional Stroke Order Sets | Ongoing 2023/25 | Chantal Menard

## IntegratedInpatientCare
Stroke Network of Southeastern Ontario - Regional Stroke Workplan 2023-2025
RSSC PRIORITY #3: Enhance integrated inpatient care for timely access, quality of care, and improved patient experience
Regional | Objectives | REGIONAL Implementation Activities - Integrated Inpatient Care | Timeline | Lead/Contact
R I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | ● Support and adapt Ontario Stroke Unit Task Group requirements with 3 Stroke Units (Acute part): 1. Dissemination/uptake of Stroke Unit Definition 2. Dissemination/use of Stroke Unit Capacity Assessment Tool 3. Completion of Stroke Unit Self-assessment/Attestation; work with teams on Action Plans for priority gaps ● Promote, monitor, and sustain local integrated flow pathways (ARC-acute to rehab to community) & inform/link to 3 OHTs a) Access to Acute Care ● Support and promote stroke unit utilization rates > 75% & facilitate QI, as needed ● Sustain & monitor flow algorithms to the 3 Stroke Units (SU); update as needed per emerging evidence ● Support ongoing evaluation of patient flow and outcomes on Integrated Stroke Units (ISUs) in HPE and LLG b) Access to inpatient rehabilitation across the region ● Support integrated patient flow in KFLA, HPE and LLG & support QI, as needed ● Ensure continued delivery of KFLA Integrated Stroke Care Clinical Task Group workplan in support of "one team" ● Sustain KHSC/PCH Fast-Track Initiative; explore spread to other regular stroke rehab referrals & other rehab groups ● Use/analyse local stroke patient flow data by Alpha FIM to further identify rehabilitation access opportunities ● Advocate for 7 day week therapies and sustain continuity of therapy ● Apply understanding of low intensity (LI) rehabilitation in the Southeast to consider impact on access to best practice (CCC in Trenton, LI at PCH, CCC in Brockville, and Perth) | March 2024 -SU (1-3 Requirements) Ongoing 2023/25 Ongoing 2023/25 Ongoing 2023/25 2023-24 | C.Murphy with SU leads C. Murphy/T. Wing with SU and Rehab leads T. Wing with Integrated Care Leaders T. Wing with Stroke Team/Allied Leads T. Wing
R I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | ● Communicate changes re best practices and promote uptake of educational resources (e.g., webinars, SMART TIPS for Stroke Care, Provincial Stroke Care Core Competency Framework, & NIH Stroke Scale training toolkit) ● Support local experts to lead education to address gaps in best practice knowledge & skills (e.g., blood pressure management, mobility and feeding strategies with KHSC mobility and nursing assistants) ● Continue to build/sustain a pool of stroke experts (e.g., stroke mentors/champions in critical care, acute & rehab) ● Update protocols, pathways, and order sets to align with current best practices (Also see RI-4 below re LUMEO) ● Support stroke expertise for nurses working in Rehabilitation ● Provide support for Rehabilitation Intensity education for inpatient rehab teams including exploring use of rehabilitation intensity module and quiz ● Coordinate Alpha FIM training/certification and explore incorporating new Alpha FIM training module resource with KHSC, BrGH and QH | Ongoing 2023/25 Ongoing 2023/25 Ongoing By March 2022 By Sept 2022 | H.Jenkins/C. Murphy/T. Wing C. Murphy/T. Wing T.Wing/H.Jenkins
| Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Participate in stroke distinction program Support teams to develop action plans to facilitate QI | ● Sustain KHSC and QH Accreditation Canada Stroke Distinction programs ● Support PCH to consider application to Accreditation Canada Stroke Distinction Program ● Support teams in QI based on Stroke Distinction data, Report & Self-Assessment and identified gaps within Critical /Acute Care/Rehab (e.g., UTI, mobilization, oral care, interprofessional teamwork) ● Support teams in QI specific to Integrated stroke units with consideration of learnings from other Ontario ISUs ● Monitor & ensure timely Alpha FIM completion rates for KHSC, QH, BrGH ● Monitor Rehabilitation Intensity and consider any opportunities to improve RI or related outcomes such as FIM Change | Ongoing 2022/23 December 2024 Ongoing 2023/25 Ongoing 2023/25 | C.Murphy/I.Manzer T. Wing C. Murphy/I.Manzer /T.Wing with Stroke Champions T. Wing
R I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | ● Support ongoing implementation and spread of learning from use of local patient experience tools: e.g., patient tracers; telephone discharge follow-up calls; patient surveys; patient interview tools; ISU patient experience tools. ● Respond to these learnings by supporting patient experience initiatives across the region ● Share findings at Regional Symposium & other stroke events ● Promote stroke information package with focus on health literacy & and other key integrated strategies for patient/family education and information sharing. | Ongoing 2023/25 | T.Wing
R I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | A) Inform LUMEO on embedding stroke best practice and monitoring: ● workflows and protocols ● order sets ● documentation templates including patient/family standardized education tool ● assessment and screening tools ● Key quality indicators, care outcomes, dashboards and communication tools B) Explore use of IDS ● Explore how IDS can be used to support monitoring at participating sites C) MONITOR, SHARE, COMMUNICATE the QUALITY AND FLOW INDICATORS ● Communicate & implement new KQIs with dashboards and tools ● Assess and sustain newly revised Regional Dashboard ● Sustain reporting on Stroke Distinction program KQIs where applicable; ensure data available & leverage to support QI ● Monitor key indicators related to flow and transition in/out of Stroke Units; ensure data available & leverage to support QI | 2023/25 as per LUMEO timelines Ongoing September 2023 Ongoing 2023/25 | C. Martin/T. Wing/ C. Murphy with Stroke Champions T. Wing/C.Murphy/ C. Martin T.Wing/C.Murphy
HPE | Objectives | HPE - QUINTE DISTRICT - Local Implementation Activities - Integrated Inpatient Care | Timeline | Lead/Contact
HPE I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | ● Work with SNSEO to meet Ontario Stroke Unit Task Group requirements (Acute part): 1. Dissemination/uptake of Stroke Unit Definition 2. Dissemination/use of Stroke Unit Capacity Assessment Tool 3. Completion of Stroke Unit Self-assessment/Attestation; if identified gaps, develop action plans ● Implement and monitor effectiveness of integrated flow pathways (ARC-acute to rehab to community) a) Access to Acute Care and Rehabilitation ● Aim to achieve and sustain stroke unit utilization rates > 75% & facilitate QI, as needed. ● Monitor and report on patient flow and outcomes on Integrated Stroke Unit (ISUs). ● Enhance timely "transfer" of acute stroke patients to rehab once readiness established. | 2023-2024 | Patient Services Manager, ISU and Rehab Stroke Resource Nurse Therapy Team Leads DSC
HPE I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | ● Continue to build/sustain stroke skills and expertise through stroke-specific orientation and skills days for interprofessional team members. ● Identify opportunities for stroke-specific education through self-identification by staff of on-going learning needs. ● Communicate changes re best practices and promote uptake of educational resources (e.g., webinars, SMART TIPS for Stroke Care, Provincial Stroke Care Core Competency Framework, & NIH Stroke Scale training toolkit) with team members who provide stroke care on units. ● Continue to plan annual physician education (Stroke School) in collaboration with SNSEO support. ● Facilitate Rehabilitation Intensity education for inpatient rehab teams including exploring use of rehabilitation intensity module and quiz. ● Explore incorporating new Alpha FIM training module resource. | Ongoing 2023-2025 | Patient Services Manager,ISU and Rehab Stroke Resource Nurse Therapy Team Leads DSC
| Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Participate in stroke distinction program Support teams to develop action plans to facilitate QI | ● Prepare to meet all requirements for Stroke Distinction Accreditation at Quinte Health. ● Complete Stroke Distinction Accreditation survey in May/23 and sustain program following survey. ● Support teams in QI based on Stroke Distinction data, Report & Self-Assessment and any identified gaps. ● Monitor & work with staff to achieve timely Alpha FIM completion rates. ● Monitor Rehabilitation Intensity and consider any opportunities to improve RI or related outcomes such as FIM Change. ● Facilitate Rehabilitation Intensity education for inpatient rehab teams including exploring use of rehabilitation intensity module and quiz. | 2023-2024 Stroke Accreditation Survey May 30-31/23 | DSC Stroke Resource Nurse Program Director Patient Services Manager, ISU and Rehab Therapy Leads
HPE I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | ● Ensure that stroke information package is available to stroke patients and families and is reviewed regularly to ensure that key local information is included. ● Collect feedback on the stroke patient experience and engage stroke team in review of information and identification of QI opportunities based on feedback. | Ongoing 2023-2025 | ISU Team Stroke Resource Nurse Patient Services Manager, ISU and Rehab DSC
HPE I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | A) Inform LUMEO on embedding stroke best practice and monitoring: ● workflows and protocols ● order sets ● documentation templates including patient/family standardized education tool ● assessment and screening tools ● Key quality indicators, care outcomes, dashboards and communication tools B) Explore use of IDS ● Explore how IDS can be used to support monitoring | 2023-2024 | Stroke Resource Nurse Patient Services Manager, ISU and Rehab DSC Therapy Leads PPL
KFL&A | Objectives | KFL&A-KHSC and PCH - Local Implementation Activities - Integrated Inpatient Care | Timeline | Lead/Contact
KFL&A-KHSC/PCH I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | ● Review and adopt Ontario Stroke Unit Task Group requirements 1. Review updated Stroke Unit Definition 2. Utilize Stroke Unit Capacity Assessment Tool & share results with Executive & Clinical Leaders 3. Complete Stroke Unit Self-assessment/Attestation; work with teams on Action Plans for priority gaps ● Work with Senior Leaders to increase KHSC neuro bed capacity and improve access to Acute Stroke Unit (ASU) ● Sustain timely repatriation processes to BrGH and Quinte Health ISUs ● Promote, monitor, and sustain integrated flow pathway (ARC-acute to rehab to community) & inform/link to FLA OHT a) Timely Access to Acute Care ● Sustain stroke unit utilization rates > 75% (using MRDX codes); perform chart audits & implement QI, as needed ● Sustain & monitor timely flow to ASU b) Timely Access to inpatient rehabilitation across the region ● Sustain KFLA Integrated Stroke Care Clinical Task Group chaired by Regional Stroke Director/PCH Rehab Director ● Deliver KFLA Integrated Stroke Care Task Group workplan activities in support of "one team" ● Spread KHSC/PCH Fast-Track Initiative to regular stroke rehab referrals ● Extend referral process map to include discharge from IP Rehab ● Use/analyse stroke patient flow data by Alpha FIM to further identify rehabilitation access opportunities ● Explore/Evaluate opportunities for 7 day week therapies in acute and rehab settings for continuity of therapy ● Evaluate patient flow through Complex Care and Lo-Intensity Rehab pathways | March 2024 -SU (1-3 Requirements) Ongoing 2023/25 Ongoing 2023/25 Ongoing 2023/25 March 2024 2023/25 March 2024 | T.Hands/S/Dacosta A. Dubé/C.Hall ASU and Rehab Leads Integrated Care Leaders P. Harvey/ C. Martin Fast Track Workgroup J Dolphin, J Bonney, K Morris/T Wing Allied Health Leads J Bonney/ T Wing
KFL&A-KHSC/PCH I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | ● Enhance knowledge about new stroke best practices (e.g., webinars) and utilize new provincial educational resources (e.g., SMART TIPS for Stroke Care, Stroke Care Core Competency Framework, & NIH Stroke Scale training toolkit) ● Continue to disseminate stroke best practices: - Hold Informal huddles & deliver in-the-moment best practice teaching - Provide best practice updates/"briefings" (e.g., UTI, mobilization, oral care) & utilize news letters - Deliver KHSC Neuroscience and PCH Rehab education/workshops - Orient new team members; develop stroke expertise in new acute and rehab staff ● Plan and/or deliver educational activities to address gaps in best practice knowledge & skills (e.g., blood pressure management; mobility and feeding strategies for assistants) ● Plan, participate in and contribute to Regional Acute Care Collaborative session & other regional acute/rehab educational events (e.g., Stroke Symposium, rehab therapy workshops, professional education fund) ● Mentor colleagues and build/sustain a pool of stroke experts in critical care, acute & rehab ● Inform/update protocols, pathways, and order sets to align with current best practices (see RI-4 below re LUMEO) ● Sustain completion of AlphaFIM by Day 3 at KHSC ● Complete Alpha FIM training/certification by all new KHSC OT/PTs - make use of Alpha FIM LMS module: "Assessing Client Function with the Alpha FIM" ● Sustain Rehabilitation Intensity (RI) education at PCH: - Continue annual Rehab Intensity (RI) refresh education and orientation for key PCH staff - Support therapy staff to complete RI Education module and quiz | Ongoing 2023/25 Ongoing Ongoing December 2023 Ongoing Ongoing | KHSC/PCH Stroke Teams/practice leaders and clinical learning specialists/educators T. Wing and Allied team J Dolphin, K Morris/T Wing
| Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Participate in stroke distinction program Support teams to develop action plans to facilitate QI | ● KHSC to sustain Accreditation Canada Stroke Distinction status - Continue to participate in Stroke Distinction Committee meetings - team to provide updates, review data, & contribute to QI initiatives, as needed - Identify next innovative project and initiate planning - Allied team to monitor & ensure timely completion of Alpha FIM ● PCH to consider participation in Stroke Distinction Program; create action plan to include: - review standards and program requirements - review learnings from KSHC/QH and other IP Rehab sites in province - learn about data collection requirements ● Participate/lead QI when necessary based on stroke data & self-assessment and any identified gaps within Critical /Acute Care/Rehab (e.g., UTI, mobilization, oral care, alpha FIM completion, interprofessional teamwork, rehab intensity) ● PCH to Increase Rehabilitation Intensity (RI) and related outcomes at PCH - Continue to monitor RI with quarterly reports - Review in relation to related outcomes such as FIM Change - Support QI to improve RI through opportunities such as: - ensuring patient readiness for therapy - optimizing use of therapy assistants ● Identify processes to support transition to Community Stroke Rehab - warm hand-off to OP and In-Home programs | Ongoing 2023/25 2023/25 Ongoing in response to data December 2024 Ongoing | KHSC Distinction Committee/C.Murphy Allied team /T. Wing PCH Leads, P. Harvey with T. Wing Stroke Champions KHSC Allied Team PCH RI Leads P Harvey / T Wing
KFL&A-KHSC/PCH I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | ● KHSC to sustain telephone discharge follow-up calls and share data with acute stroke team ● KHSC, PCH, and Home and Community Care Support Services to continue participation in Patient Tracer project with at least 2 more patient tracers - Collate main patient themes from tracer findings - Share themes with care teams and patient advisors to identify areas for action - support teams to Implement key improvements to enhance a positive patient experience - share learnings with other stroke providers - Present findings at Regional Stroke Symposium and other stroke events (e.g., World Stroke Congress) ● Seek opportunity to review/analyse stroke-specific content within corporate patient surveys. Review survey findings for opportunities for improvements and review these with the care teams; consider actions to respond ● Stroke Information Packages: - Continue to coordinate collation of stroke information packages in clinical areas - Continue provision of standard patient/family/caregiver stroke information packages; continue to add individualized materials (e.g., aphasia friendly) and new emerging patient-centred / health literacy-friendly materials ● PCH to re-visit/Implement QI project to provide unit orientation for patients on admission to Rehab program ● PCH to Identify quality improvement initiative to improve interdisciplinary care conference documentation to support information sharing to patients and caregivers during inpatient stay ( e.g. consider use of bedside terminal) | ongoing ongoing April 2023 June to Sept 2023 June - Oct 2023 Sept 2023 ongoing 20223-25 | D.MacPhail (Patient Tracer), Professional Practice Lead (Follow up Telephone Calls) with Integrated Care Leaders KHSC Stroke Leaders A.Dube/C.Hall K Morris / T Wing J Dolphin/Clinical Stroke Team / T Wing
KFL&A-KHSC/PCH I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | ● Participate in LUMEO project (e.g., Change Agents) A) Participate in LUMEO meetings and Inform LUMEO on embedding stroke best practice and monitoring: ● workflows and protocols ● order sets ● inform LUMEO of documentation requirements/templates including patient/family standardized education tools ● assessment and screening tools ● Key quality indicators, care outcomes, dashboards and communication tools ● Evaluate impact of LUMEO documentation changes on Rehab Referral process - Fast-Track/Regular referrals B) Explore use of IDS (Integrated Decision Support) ● Explore how IDS can be used to support monitoring at participating sites ● PCH to consider participating with IDS platform as regional stroke performance tool C) MONITOR, SHARE, COMMUNICATE the QUALITY AND FLOW INDICATORS ● Sustain newly revised regional dashboard with updated KQIs; ● Make use of refreshed dashboards and tools to communicate with care teams ● Assess newly revised Regional Dashboard after one year ● Sustain reporting on Stroke Distinction program KQIs where applicable; ensure data available & leverage to support QI ● Monitor key indicators related to flow/transition in/out of Stroke Units; ensure data available & leverage to support QI ● Identify ways to share site specific data from regional reports (Stroke Report, Dashboard) | 2023/25 as per LUMEO timelines September 2023 March 2024 Ongoing 2023/25 March 2024 | Stroke Champions with Stroke Network team T. Wing, J. Roth Decision Support Leads/Patient Records J. Roth/T Wing Quality Leads with T. Wing/C.Murphy/ C. Martin Clinical teams with Regional team
L&G | Objectives | LEEDS & GRENVILLE - Local Implementation Activities - Integrated Inpatient Care | Timeline | Lead/Contact
L&G I1 | Facilitate an integrated stroke patient pathway to enhance timely access to acute and rehabilitation stroke unit care (access and flow) | ● Continue to work with PSFDH to improve access to Rehab following acute stay at BGH. ● Monitor stroke unit capacity to ensure timely access to care. Ensure SU utilization> 75% ● Participate in/adapt Ontario Health CorHealth Ontario's Stroke Unit Requirements | 2023/25 | B.Kontes/J.Lynch/J.Peters
L&G I2 | Deliver quality expert acute and rehabilitation stroke unit care (core best practices) a) Support expertise in delivery of essential core stroke best practices in critical care, acute care, and rehabilitation | ● Review current education/orientation and revise education to updated best practices. Provide education/sharing messages of best practice updates ● Develop new RN and RPN Stroke Champions in ISU ● Obtain and review feedback from stroke education fair (March/April 2023) to determine gaps and learnings for next education events | 2023/24 | S. Ferguson/D. Henson/B. Kontes
| Deliver quality expert acute and rehabilitation stroke unit care (core best practices) b) Support stroke teams in quality improvement Support teams to develop action plans to facilitate QI | ● Improve data collection regarding rehab intensity and FIM scoring. Monitor completion of documentation and continue with ongoing education regarding NRS data. ● Implement QI as per stroke data and team's feedback, as needed including: - improving transitions in care within hospital and transition to community through standardized Transfer of Care and Discharge Checklist. | Ongoing 2023/25 | B. Kontes/C. Render/Data Analysts/J. Peters/D.Henson
L&G I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience | ● Create updated patient questionnaire for implementation within the ISU upon and/or following discharge ● Share survey findings with internal and external stroke partners and identify QI based on patient and family feedback | Ongoing 2023/25 | J. Gerritsen/B. Kontes/D. Henson
L&G I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | ● Monitor and share Key Performance Indicators(KPI) within ISU stroke care with program ● Support LUMEO build and implementation by actively engaging with LUMEO team. Identify KPIs to be pulled and monitored with Cerner implementation to identify ongoing QI | 2023/25 | B.Kontes/D. Henson/Data Analysts.
LANARK - Local Implementation Activities - Integrated Inpatient care
L I1 | Continue to facilitate an integrated stroke patient pathway to enhance timely local access to acute stroke care in Brockville and timely repatriation to rehabilitation in Perth (access and flow) | ●Continue to support the repatriation of patients in our catchment area, explore opportunities to improve flow of patients from hyperacute | 2023 | Chantal Menard
L I2 | Deliver quality expert stroke rehabilitation (core best practices) a) Support expertise in delivery of essential core stroke best practices in stroke rehabilitation | ● Could explore opportunities. In order to better support, we would need NRS designated rehab beds, would need to increase capacity and staffing such as appropriate nursing to support the increased capacity. If we were to seek NRS designated beds within our present capacity, it would likely affect flow | 2023-24 | Chantal Menard
| Deliver quality expert stroke rehabilitation (core best practices) b) Support stroke rehab team in quality improvement | ● Encourage nursing to participate in rehabilitation webinars supported by the Stroke Network. Continue to promote and provide support for education of our SLP, OT, PT and PTA rehab team for additional education to maintain best practice | Ongoing 2023-25 | Chantal Menard
L I3 | Support implementation and spread of local initiatives to learn about and respond to the patient experience
L I4 | Inform and make use of standard regional information systems to support and advance flow and to embed quality best practice | ● Explore if resources standard in LUMEO | Ongoing 2023-25 | Chantal Menard

## Community Rehab & Supports
Stroke Network of Southeastern Ontario - Regional Stroke Workplan 2023-2025
RSSC PRIORITY #4: Enhance access to stroke rehabilitation and supports in the community to optimize recovery, the patient experience and community re-integration
Regional | Objectives | REGIONAL Implementation Activities - Community Rehab & Supports | Timeline | Lead/Contact
R C1 | Support local providers to innovate in the delivery of new, enhanced and integrated Community Stroke Rehab (CSR) Programs to align with the provincial CSR Model of Care | Informed by the provincial gap analysis: ● Support local providers in responding to gap analysis and potential funding opportunities ● Support the development of innovative models of care for community based rehab delivery (hybrid models, innovative integrated teams, dedicated community stroke rehab teams) ● Consider feasibility and potential benefits of a home-based rehab contract that is stroke specific ● Support programs to use Provincial CSR and Regional Integrated ARC Access Pathways in program planning and evaluation ● Participate in ongoing CSR Provincial project opportunities (work groups, surveys, engagement sessions, community of practice) ● Identify Community Rehab Planning (CoRP) meeting process improvements to ensure seamless transition from hospital to CSR ● Identify opportunities to improve intensity of therapy provided in both in home and outpatient programs including use of rehabilitation assistants and/or other models (e.g. hybrid OP/Community models, satellite clinics, virtual care) ● Identify and address education needs of community based rehabilitation providers to support expertise as directed by gap analysis/provider feedback | Sep 2024 March 2024 Sept 2024 January 2024 Ongoing November 2024 Ongoing Ongoing | T Wing T Wing T Wing T Wing T Wing T Wing T Wing/H Jenkins
| Participate in and inform the CorHealth Ontario CSR Project Data Strategy | ● Support providers in implementation of CSR data strategy activities/recommendations ● Participate in ongoing CRS Provincial project opportunities (work groups, surveys, engagement sessions, PROMS/PREMS) ● Revise CSRP Annual report to align with CorHealth data strategy | March 2024 Ongoing September 2024 | T Wing T Wing T Wing
| Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | ● Inform LUMEO about ongoing CSR clinical documentation, utilization data and process/outcome data collection requirements ● Ensure required stroke data is understood by LUMEO team | March 2024 | T Wing T Wing
REG | Objectives | REGIONAL and Local Implementation Activities - Community Rehab & Supports | Timeline | Lead/Contact
HPE |  | QUINTE DISTRICT - Community Rehab & Supports
KFLA |  | KFLA COUNTY - Community Rehab & Supports
L&G |  | LEEDS & GRENVILLE COUNTIES - Community Rehab & Supports
Lanark |  | LANARK COUNTY - Community Rehab & Supports
R C2 | Complete Community Re-integration Consultation | ● Complete region-wide Community Consultation ● Analyze and develop themes ● Communicate findings; compile report and deliver presentations ● Consider how themes inform workplan; revisit for year 2 | 2024 September 2023 January 2024 January 2023 | K. Purdon
R C3 | Person-Centred Skilled Stroke Care & Rehabilitation: a)Sustain and build upon regional approach to Aphasia Supportive Conversation Groups. | ● Follow up on proposal request to OH East for aphasia funding to meet demands and increasing volumes ● Continue to facilitate quarterly regional meetings with Community Support Agencies and Speech-Language Pathologists who facilitate Aphasia Supportive Conversation Groups ● Support healthcare providers in accessing training through the Aphasia Institute ● Facilitate access to caregiver aphasia training through Aphasia Institute (i.e. The Path to Resilience) ● Support referral and linkages to Aphasia Supportive Conversation Groups in the community ● Explore potential to initiate standard clinical regional intake process (e.g. decision regarding use of BOMPA tool) ● Initiate regional program evaluation of Aphasia Supportive Conversation Groups - Evaluation to include virtual connections | 2024 Ongoing Ongoing Ongoing Ongoing September 2023 April 2023 | K. Purdon K. Purdon/H. Jenkins K. Purdon/Stroke Support Group Facilitators (SSGF)
| Person-Centred Skilled Stroke Care & Rehabilitation: b) Support stroke expertise and best practice in the Long Term Care and community settings | ● Assess education approaches (e.g. virtual education, key messaging) and needs of LTC homes and provide support ● Promote the use of LTC Stroke Care Plans, Brain, Body & You, Education Posters, SMART TIPS for stroke care and other best practice resources ● Support education for stroke-specific expertise in LTC (e.g. promote use of Shared Work Day and Field Experience) ● Collaborate with partners to support LTC (e.g. RNAO, Psychogeriatric Resource Consultant, Palliative Pain and Symptom Management Consultant, etc.) ● Continue to leverage evaluation data to promote best practice stroke care in LTC (e.g. CCC/LTC Report, RAI, data provided by CorHealth) | Ongoing Ongoing Ongoing Ongoing Ongoing | K. Purdon/H. Jenkins K. Purdon
R C4 | Support Individual Well-Being & Meaningful Engagement: a) Sustain and enhance Community Stroke Support Services to meet diverse needs | ● Follow up on proposal request to OH East for stroke support service funding to meet demands and increasing volume of services ● Continue to facilitate regional quarterly Facilitator meetings and regional quarterly Community Reintegration Leadership Team meetings ● Sustain and adapt innovative models to meet the varying needs of persons with stroke and their caregivers (e.g. regional virtual meetings, hybrid models, interest groups, stroke-specific adult day program, co-facilitated peer-led models, etc.) ● Ensure inclusiveness and respond to community consultation needs (e.g. consider groups for young caregivers, young stroke survivors, Indigenous populations, rural populations, adults living with aphasia etc.) ● Continue to support and build upon peer visiting across the region in collaboration with hospital and community partners ● Promote awareness and uptake of Return to Work Toolkit and Return to Driving After Stroke Resource ● Evaluate services and complete Community Stroke Support Services: Southeastern Ontario Annual Report - Highlight services, innovations and recommendations for the future - Evaluation to include virtual connections | 2024 Ongoing Ongoing Ongoing Ongoing Ongoing June 2023/June 2024 | K. Purdon K. Purdon/SSGF K. Purdon
| Support Individual Well-Being & Meaningful Engagement: b) Self-management | ● Support the delivery of the Regional Community Stroke Education Program ● Transition to the updated Living with Stroke Program™ when available | 2023 June 2023 | K. Purdon/SSGF
| Support Individual Well-Being & Meaningful Engagement: c) Sustain and enhance Community Stroke Specific Exercise Programs | ● Refresh knowledge and awareness of community stroke-specific exercise programs ● Support referral and linkages to stroke-specific exercise programs in the community (i.e. ensure stroke teams, therapists and community providers are aware of programs and how to refer/link) ● Encourage collaboration with community organizations and recreational facilities to enhance referral linkages and services ● Support education for stroke-specific expertise in community exercise programming ● Promote awareness and application of Canadian Stroke Community-Based Exercise Recommendations ● Continue to facilitate semi-annual regional meetings of stroke-specific exercise program coordinators ● Evaluate usage of community stroke-specific exercise programs across the region | Ongoing Ongoing Ongoing Ongoing Ongoing Ongoing Ongoing | K. Purdon/T. Wing K.Purdon/H. Jenkins K. Purdon
R C5 | Community Co-Navigation and Access to Services: | ● Review and update the Community Stroke Rehabilitation Program Transitions Checklist and support improved integration into practice ● Assist with connections to support groups and community services after discharge (e.g. use of stroke information package including the patient journey map and regional referral form) ● Sustain hospital and community collaboratives (e.g. "Ask a Survivor", warm hand offs) and quarterly regional meetings between hospital representatives and community stroke support group facilitators ● Maintain and share "Navigation and Transitions" section of Stroke Network of Southeastern Ontario website with emphasis on community resources ● Continue to support patient-centred navigation and linkages based on results from community consultation related to - psychosocial supports - financial assistance - transportation and return to driving - self-management programs | Ongoing Ongoing Ongoing Ongoing Ongoing | K. Purdon/T. Wing K. Purdon
HPE | Objectives | HPE - QUINTE DISTRICT - Local Implementation Activities - Community Rehab | Timeline | Lead/Contact
HPE C1 | Support local providers to innovate in the delivery of new, enhanced and integrated CSR Programs to align with the provincial CSR Model of Care | ● Consider Provincial CSR and Regional Integrated ARC Access Pathways in local program planning and evaluation. ● Engage when invited with ongoing CSR Provincial project opportunities (work groups, surveys, engagement sessions, community of practice). ● Review CoRP meeting processes and identify any improvement opportunities to ensure seamless transition from hospital to CSR. | 2023-2024 | Program Director Patient Services Manager, ISU and Rehab DSC
| Participate in and inform the CorHealth Ontario CSR Project Data Strategy | ● Implement CSR data strategy activities/recommendations as they are developed through CorHealth Ontario CSR Project. | 2023-2024 | Decision Support DSC Patient Services Manager, ISU and Rehab
| Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | ● Inform LUMEO about ongoing CSR clinical documentation, utilization data and process/outcome data collection requirements | 2023-2024 | Decision Support DSC Patient Services Manager, ISU and Rehab Stroke Resource Nurse Professional Practice
KFL&A | Objectives | KFL&A-PCH - Local Implementation Activities - Community Rehab & Supports- COMMUNITY REHAB | Timeline | Lead/Contact
KFL&A-PCH C1 | Support local providers to innovate in the delivery of new, enhanced and integrated CSR Programs to align with the provincial CSR Model of Care | ● Continue to participate in CorHealth Community Stroke Rehab (CSR) project opportunities ● Identify and prioritize needs for future CSR funding requests ● implement Outpatient Stroke Program at PCH ● Consider feasibility of integrating Outpatient Stroke Program services to include home visits ● Explore staffing models that support IP and OP coverage at PCH ● Refine outpatient patient visit scheduling to maximize number of visits/intensity available ● Initiate outpatient program evaluation utilization in relation to Regional Integrated ARC Access Pathways ● Develop stroke expertise with outpatient therapy team members | ongoing spring 2023 2023 - 2025 | J Dolphin/Travis
| Participate in and inform the CorHealth Ontario CSR Project Data Strategy | ● Support development and implementation of Minimum Data Set for OP stroke program ● Trial use of outcome measure (Reintegration to Normal Living Index (RNLI)) ● Consider use of PROM for OP stroke program (SS-QOL) | ongoing January 2024 | J Dolphin/Travis
| Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | ● Inform LUMEO of project of documentation requirements ● Evaluate LUMEO impact to workflow in OP stroke program | ongoing January 2025 | J Dolphin/Travis
L&G | Objectives | LEEDS & GRENVILLE - Local Implementation Activities - Community Rehab | Timeline | Lead/Contact
L&G C1 | Support local providers to innovate in the delivery of new, enhanced and integrated CSR Programs to align with the provincial CSR Model of Care | ● Implement QI as per stroke data and team's feedback, as needed Explore potential funding opportunities to implement dedicated CSR with support from Stroke Network | Ongoing 2023/25 | D.Henson/J.Peters
| Participate in and inform the CorHealth Ontario CSR Project Data Strategy | ● Participate in ongoing CSR Provincial project opportunities | Ongoing 2023/25 | D. Henson/J.Peters
| Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | ● Continue to support LUMEO build and implementation through ongoing engagement with LUMEO team | Ongoing 2023/25 | D.Henson/J.Peters
Lanark | Objectives | LANARK - Local Implementation Activities - Community Rehab | Timeline | Lead/Contact
L C1 | Support local providers to innovate in the delivery of new, enhanced and integrated Community Stroke Rehab (CSR) Programs to align with the provincial CSR Model of Care | ● Continue to participate in CorHealth CSR project initiatives ● Explore opportunities to align to CSR Model of Care staffing model ● Evaluate existing local access pathways to day hospital program and identify process to incorporate 'warm hand-off' from inpatient partners | Ongoing | Chantal Menard
| Participate in and inform the CorHealth Ontario CSR Project Data Strategy | ● Trial outcome measure for stroke patients in day hospital program | Ongoing | Chantal Menard
| Advise LUMEO team on embedding Community Stroke Rehab best practices into LUMEO system | ● Share documentation practices with LUMEO project team ● Evaluate use of standardize documentation on day hospital workflows | Ongoing | Chantal Menard

## Leadership & Coordination
Stroke Network of Southeastern Ontaro Regional Stroke Workplan 2023-2025
Leadership & Coordination
REG | Objectives | REGIONAL and Local Implementation Activities- Leadership & Coordination | Timeline | Lead/Contact
R L&C1 | Develop Leaders A. Plan successions to build and mentor new leaders within the regional stroke program B. Develop Stroke Team leadership skills and sustain engagement | A. Plan successions to build and mentor new leaders within the regional stroke program • Build skills in change management, quality improvement, evaluation, communication. • Watch for opportunities to recruit new leaders for succession planning • Build stroke champions in each local community and in each sector of the care continuum. B. Develop Stroke Team leadership skills and sustain engagement • Sustain funded stroke centre/SPC human resource infrastructure; recruit, retain, develop staff • Support achievement of Professional Development/Goal Setting and Engagement Plans by RSC/DSC/SPC staff • Ensure each team member has opportunities to develop leadership/QI/KT/change management skills • Continue development of knowledge in virtual learning and in virtual practice/care • Continuously develop stroke team best practice knowledge through participation in national stroke congress; and other relevant conferences including virtual learning and care - deliver at least 3 provinical or national posters/presentations • Continue to learn about the patient experience and tools for facilitating this learning; make use of narrative practice and patient tracers to communicate patient-centred care and to develop interprofessional team expertise • Share professional development, best practice and leadership information amongst stroke teams | Ongoing Ongoing as detailed in professional development plans | C. Martin
R L&C2 | Build and Sustain a resilient Stroke Network that is flexible and responsive to a changing provincial context. | Build and Sustain a resilient Stroke Network that is flexible and responsive to a changing provincial context • Build strong communication links with Ontario Health East and OH - CorHealth Ontario as well as local OHTs • Advise on recommendations to the MOHLTC by CorHealth Ontario in relation to the stroke infrastructure • Advise on plans to sustain and build on stroke networks and apply learnings within the new context of Ontario Health and Ontario Health Teams, integrated stroke care pathways- see also L&C 7 below. • Revisit the workplan on an ongoing basis to accommodate any changes in mandate given changing health care context. | Ongoing Connections with Ontario Health and OHTs are still developing | C. Martin
R L&C3 | Monitor quality and evaluate stoke care performance in the SE against provincial and national standards / best practice recommendations | Quality Monitoring and Evaluation (As embedded in each section of the stroke workplan) • Disseminate CorHealth Stroke Evaluation Report; Regional/legacy LHIN and Sub-region analyses • Ensure stakeholders are aware of local Stroke Report performance - population and facility-based data • Communicate annually with local leaders of designated stroke centres about Stroke Evaluation Report via letters to CEOs • Continue to use and improve on Regional Stroke Dashboard refreshed in 2022- report quarterly, use to plan and sustain local QI initiatives; specifically promote use at local level with local stroke teams in 2023-25 • Assist with data interpretation and use of data in integrated care models such as the KFLA Integrated Stroke Care Report and rerpots for National Stroke Distinction Program (KHSC and Quinte Health ) • Use data to inform workplan activities and best practice implementation priorities at regional and local levels • Support data quality in CIHI project #340, #640, #740, #440 and CIHI NRS including Rehab Intensity measures • Continue to collect SPC activity & wait times on a regional basis through manual data collection and submisison from each SPC • Support CorHealth in considering a trial of NACRS lite for Outpatient Rehab data collection (pending OH approval) • Sustain collaborative data sharing agreement with RPPEO and paramedic services for annual pre-hospital Stroke Report • Sustain Regional monitoring and delivery of 6 month interim and annual evaluation reports of Community Stroke Rehab Program uisng new formats developed in 2022-23, • Sustain Regional monitoring and delivery of annual evaluation reports on Community Stroke Supports: Stroke Support Group and Community Aphasia Conversation Groups using new format developed in 2022-23 • Support Providers in ensuring stroke care is documented accurately within LUMEO as noted throughout workplan • Promote instances where LUMEO, South East Integrated Information Portal (SHIIP) and ConnectOntario might assist the Stroke Network and its stakeholders in informing regional stroke care performance and transitions in care • Leverage findings of CCC/LTC Evaluation Report in participation with the provinical group of Community & LTC Coordinators • Participate in Stroke Evaluation and Quality Committee of CorHealth Ontario. | Ongoing as indicated in Workplan | C. Martin with team
R L&C4 | Develop, monitor and implement Regional Stroke Workplan based on RSSC priorities and program mandate | Develop, monitor and deliver Regional Stroke Workplan • Engage partners, identify gaps, plan and implement change, monitor and sustain change to support best practices and QI • Build Integrated Care across the care continuum to improve the patient experience • Build and sustain capacity for interprofessional stroke expertise across the care continuum • Report on workplan progress at RSSC meetings using progress reports, regional performance dashboard and briefing notes • Engage and support stakeholders in reporting on local aspects of workplan with emphasis on integrated stroke care • Sustain infrastructure required to oversee workplan • Deliver on Education/Knowledge Translation plan embedded in workplan building capacity for best practice expertise • Continuously review evaluation data and adjust workplan accordingly with stakeholders • Set new priorities for and develop next two year plan with stakeholders | Ongoing as detailed in workplan | C. Martin with RSSC
R L&C5 | Engage stakeholders in workplan priorities through an effective communication strategy | Engage stakeholders in setting and addressing workplan priorities through a communication strategy: • Ensure website is current and communication strategy is linked with workplan priorities • Share Briefing Notes, Performance Dashboards and Workplan Progress Reports to key stakeholders through RSSC • Direct stakeholders to website resources through regular updates to news page and quarterly e-news • Make use of Adobe Illustrator, CanVa and other programs to create infographics for communication of performance and projects • Increase photography archive for use on SE website • Highlight the patient experience promoting updake of video clips co-created with patients • Build use of virtual on-line learning modules and resources; continue to make use of Articulate Storyline • Maintain current contact lists - check annually • Ensure strong internal team communication - monthly team meetings and regular workplan review | Sustain: Website RSSC Reports E-news quarterly Team comm'n Contact lists | C. Martin with team
R L&C6 | Sustain governance infrastructure for effective program oversight and stakeholder engagement | Sustain governance infrastructure for effective program oversight and stakeholder engagement • Coordinate strategic focus of Regional Stroke Steering Committee (RSSC) • Sustain close communication with RSSC Chair to plan and guide strategic approach to meetings • Maintain membership of RSSC and subcommittees/workgroups per terms of reference (TOR) • Review and revise TOR for each committee/workgroup as specified in TOR • Sustain stroke survivor/caregiver advisory membership and active engagement in RSSC and related committees • Provide orientation for every new member of RSSC • Evaluate RSSC meetings using Qualtrics Survey after each meeting with call for Agenda items; follow up on suggestions provided • Perform a full evaluation of steering committee every 3 years and respond accordingly • Sustain Subcommittees and develop Workgroups as required to deliver workplan • Provide support as needed to Quinte District Stroke Advisory Council (QDSAC) | Ongoing RSSC meetings 4x/year next full RSSC evaluation due in 2024-25 | C. Martin
R L&C7 | Build Regional Communication and Accountability Links with Ontario Health - CorHealth Ontario, Ontario Health East Region and OHTs | Build Stroke Program Communication and Accountability Links with Ontario Health: CorHealth, OH- East, local OHTs • Build relationship and communication links with Ontario Health East Region, and local OHTs, connecting as needed with planning & performance teams for effective information flow and collaboration in health system change • Sustain Ontario Health East membership on RSSC (Director and Planner, Capacity Access and Flow Portfolio) • Build alignment of Stroke Network Workplan with Ontario Health Annual Business Plan, OH-CorHealth Ontario; OH-East e.g. CorHealth Stroke Plan for Hyperacute, Acute Stroke Units and Community-Based rehab; Integrated Care; Virtual/Digital care • Participate in CorHealth Provincial Priority Workgroups (Acute Stroke Units, CSR, Hyperacute Care) • Participate in/support leaderhip in other CorHealth provincial committees and workgroups such as Stroke Leadership Council, CorHealth EVT and Telestroke Steering Committee and workgroups, Ontario Regional Education Group-OREG, Regional Director/DSC Advisory Council, Regional Rehabilitation Coordinators,CLTC Coordinators Workgroups, Best Practice Coordinators Workgroup, Prevention Workgroup • Build connection with Ontario Health East representatives to discuss Stroke Evaluation and Performance, interpretation, progress and implications for workplan • Sustain communication with Regional Stroke Networks across Ontario Health-East to ensure collaboration and communication in meeting stroke accountabilities across sub-regions - continue to hold quarterly meetings. • Build relationships with each OHT in the region: FLA, HPE and LLG OHTs to enable collaborative work on mutual priorities such as stroke prevention, access to Primary Care & wellness; participate in local committees as appropriate. • Learn more about the OH intent behind "OHTs- the Path Forward" released Nov 2022. Seek direction with respect to the identification of stroke as one of four integrated care pathways within OHT mandates. Build on opportunities that arise including innovative approaches to prevention. | Ongoing | C. Martin
R L&C8 | Sustain and Grow partnership and collaboration with other Regional, Provincial and National Organizations and Networks to advance stroke care | Provincial and National partnerships, collaboration and linkages • Maintain close communication with all stroke regions with focus on shared learning • Participate in Rehab Care Alliance and Community Stroke Rehab Community of Practice • Build/Sustain links with Queen's university, St Lawrence College and other academic institutions • Participate in provincial opportunities for best practice collaboration in LTC and Community Care • Contribute to new/updated provincial and national Stroke Educational Resources & Best Practice Recommentations/Guidelines • Sustain/Build relationship with Heart and Stroke Canada; March of Dimes Canada • Facilitate awareness, dissemination and uptake of provincial and national stroke care resources | Ongoing | C. Martin and team
R L&C9 | Manage fiscal and human resources within given parameters | Fiscal Planning & Human Resource Management • Monitor fiscal resources and variances associated with designated stroke funding at each centre • Ensure staff roles are filled, recruit to vacancies, select, orient, develop and retain staff; ensure adequate succession planning • Deliver on accountabilities for mandated stroke services • Ensure designated stroke staff deliver on Professional Development Plans and Workplan accountabilities • Contribute as requested in the recruitment and retention of medical leaders in stroke care across the region. | Ongoing | C. Martin
R L&C10 | Contribute to innovation and knowledge translation in stroke care | Contribute to innovation and knowledge translation in stroke care • Ensure new stroke services are developed with optimal quality (e.g. Community Based Rehabilitation Services, Integrated Stroke Units, Aphasia conversation groups, Indigenous Blood Pressure Screening, virtual care, hyperacute stroke treatments such as TNK, Cerebral aneurysm coiling) • Engage and support stakeholders and academic partners in responding to relevant funding opportunities/calls for proposals • Support partners in stroke project implementation, evaluation and dissemination of project findings • Sustain and spread project learning to promote knowledge translation and practice change • Sustain links with academic organizations including Queen's and SLC in research trials • Maintain awareness of current funded research and Clinical Trials related to stroke best practice and apply findings to workplan activities as they become relevant (e.g.acute stroke trials; stroke prevention trials; rehab/community practices) • Collaborate with Queen's School of Rehab in rehabilitation research as appropriate | Ongoing | C. Martin and team

## Education Plan 2023-24
SOUTHEASTERN ONTARIO KNOWLEDGE TRANSLATION PLAN 2023/2024
Project # | Title | Regional Priority | Details | Timeline | [11 empty] | Budget Item | Projected Costing Breakdown | Total Projected Cost
|  |  |  | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 24 | 24 | 24
|  |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | Regional Stroke Prevention Clinic Best Practice and Clinical Update Meeting | #1 Prevention | Format: Teams Meeting Objective:1) Meet best practice learning needs (i.e case study review), 2) process needs related to core elements of SPC services Target Audience:Regional SPC staff | [12 empty] | Regional SPC Meeting
[16 empty] | Honoraria | 1200
[16 empty] | Total cost: | 1200 | 1200
2 | Indigenous Interprofessional Care Team (IIPCT) Support: Volunteer Training, other education session (? Home BP monitoring, peer support) | #1 Prevention | Format: Train the Trainer Objective: Train and support volunteer BP screeners Target Audience: Volunteer BP screeners | [12 empty] | IIPCT Support/ Volunteer Training
|  |  |  | Jun: O; Jul: N; Aug: G; Sep: O; Oct: I; Nov: N; Dec: G |  | 2000
[16 empty] | Total cost: | 2000 | 2000
3 |  |  | Format: Financial support for individuals to take San'Yas Indigenous Cultural Safety Training Objective: To foster and support spread of cultural safety awareness among stroke care practitioners in SEO Target Audience: All stroke care HCP's | [12 empty] | Indigenours Cultural Sensitivity Training
|  |  |  | Jun: O; Jul: N; Aug: G; Sep: O; Oct: I; Nov: N; Dec: G | Registration @300.00 x 4 ppl= 1200 plus hst | 1380
Indigenous Cultural Sensitivity Training Support
[16 empty] | Total cost: | 1380 | 1380
4 | Local Connection Events with Primary Care A) Lanark County B) Leeds and Grenville | #1 Prevention | Format: 3h workshop Objective: 1) Meet learning needs of primary care physicians in sub-region w.r.t primary stroke prevention, 2) promote CSBPR for stroke prevention Target Audience: primary care practitioners (50 plus 40) | [12 empty] | Primary Care Connection events | bar: Apr to Aug; Nov to Mar
[16 empty] | Venue A) Brockville Country Club | 250 | bar: Apr to Aug; Nov to Mar
[16 empty] | Venue B) Code's Mill on the Park | 750 | bar: Apr to Aug; Nov to Mar
[16 empty] | Catering A) Est. $29 pp, x 50 pll, plus hst & Gratuity | 1900 | bar: Apr to Aug; Nov to Mar
[16 empty] | Catering B) $32 pp plus hst x 40 ppl , plus gratuity | 1700 | bar: Apr to Aug; Nov to Mar
[16 empty] | Honoraria | 3000 | bar: Apr to Aug; Nov to Mar
[16 empty] | Travel for team members- | 300 | bar: Apr to Aug; Nov to Mar
[16 empty] | Total cost: | 7900 | 7900 | bar: Apr to Aug; Nov to Mar
5 | Telestroke Engagement Meeting at Brockville General Hospital | #2 Hyperacute | Format: In-person meeting Objective: To discuss opportunities and barriers to delivering telestroke care to stroke patients at Brockville General Hospital Target Audience: Telstroke stakeholders at BrGH- Leadership, DI, Critical care, ED, Internal Medicine | [12 empty] | Telestroke Engagement Meeting
Venue- on- site, $0
[16 empty] | Catering- $450 (BrGH in-house nutrition services- wrap platter with veggies tray, cookies, tea/ coffee, water)- baseed on 2019 event (VS Freshii)- ?25 ppl | 450
[16 empty] | Travel | 160
[16 empty] | Total cost: | 610 | 610
6 | Stroke Physician Education | #2 Integrated Inpatient care | Format: virtual presentation Objective: to address identified needs of local stroke care physicians Target Audience:ISU physicians engaged in stroke unit care (?open to all stroke units) | [12 empty] | Stroke Physician Education
[9 empty] | T | B | D
[16 empty] | Total Cost: | 0 | 0
7 | QH and Brockville Stroke Skills Fairs | #2 Integrated Inpatient care | Format: 1-day station-based stroke skills fair Objective: To provide a skills refresher/ training for new staff of ISU Target Audience: All nursing and allied staff working on ISU | [12 empty] | QHC and Brockville Stroke Skills Fair
2000
[16 empty] | Total cost: | 2000 | 2000
8 | Visual Processing Course | #2 Integrated Inpatient care | Format: self directed learning modules Objective: improve OT's knowledge about Visual processing and therapeutic techniques to improve it Target Audience: Occupational Therapists across continuum of care in our region | [12 empty] | Visual Processing course
2700
$2700 for 30 seats
[16 empty] | Total cost: | 2700 | 2700
9 | 1 Karen Guha course (Topic TBD) | #2 Integrated Inpatient care | Format: virtual course using Teams (Topic TBD) Objective: to increase therapists knowledge of Neurodevelopmental Treatment techniques Target Audience: OT/PT/OTA/PTA/nursing staff across region | [12 empty] | Karen Guha course
1500
[16 empty] | Total cost: | 1500 | 1500
10 | Stroke Unit Collaborative | #2 Integrated Inpatient care | Format: Teams meeting Objective: To promote sharing of information, enhance expertise of staff working in a stroke champion role (I.e Stroke Case Managers, Stroke Resource Nurse), discuss patient experience / tracers Target Audience:Staff at any site across Southeastern Ontario who play a stroke champion role in their organization | [12 empty] | Stroke Unit Collaborative
[16 empty] | Total cost: | 0 | 0
11 | Blood Pressure management in ED/ acute/ critical care post acute stroke | #2 Integrated Inpatient care | Format: webinar, ? recorded Objective: To review best practices in relation to management of hypertension in the ED, acute and critical care setting Target Audience: health care rpoviders working in those clinical areas | [12 empty] | Blood Pressure Management webinar
[16 empty] | Total cost: | 0 | 0
12 | Promotion of "SMART TIPS for Stroke Care"- Community and Long Term Care Stroke Care Resource | #3 Community | Format: TBD- webinar, email, highlight at various meetings and events Objective: distribute and educate about the new educational resource about practical stroke care tips Target Audience: PSW's in Community and LTC, informal caregivers | [12 empty] | Promotion of SMART TIPS for Stroke care
[5 empty] | O | N | G | O | I | N | G
[16 empty] | Total Cost: | 0 | 0
13 | Ongoing Training in Supportive Conversation | #3 Community | Format: Aphasia Institute Courses, Communication training (field work style) Objective: Train Stroke Champions in Supportive Conversation skills Target Audience:New PCH SLP, other front-line staff and volunteers | [12 empty] | Ongoing Training in Supportive Conversation
[16 empty] | 2-3 people for A2/A3 ($888 per person, but spots often free) | 888
[16 empty] | 1 person for D3 | 613
|  |  |  | May: O; Jun: N; Jul: G; Aug: O; Sep: I; Oct: N; Nov: G | 1 -2 people for Group Conversation course (272 per person) | 544
[16 empty] | Total cost: | 2045 | 2045
14 | Community Stroke Rehab Event A) KFLA B) HPE C) LLG | #3 Community | Format:Engagment sessions in-person, local Objective: To facilitate discussion around results of gap analysis, experience of persons with stroke and to plan for aligning service delivery with new practice model Target Audience: Leadership and representative clinicians from each local agency | [12 empty] | Community Stroke Rehab events | bar: Apr to Oct; Jan to Mar
venue- in kind, free spaces | bar: Apr to Oct; Jan to Mar
[16 empty] | catering: lunch x 60 ppl across the 3 session at $25 per meal, plus tax/ tip | 1900 | bar: Apr to Oct; Jan to Mar
[16 empty] | Travel for team (est 2 vehicles, | 250 | bar: Apr to Oct; Jan to Mar
[16 empty] | Total cost: | 2150 | 2150 | bar: Apr to Oct; Jan to Mar
15 | Special Topic Webinar: (Topic TB-; Helping Patients Develop Goals/ GRASP/ Pain management webinar/ EMS) | #3 Community | Format: Webinar Objective: To support clinicans in a specific learning need as requested and based on speaker availability Target Audience: Allied Health Professionals across the continuum | [12 empty] | Special Topic webinar
[16 empty] | Speaker Honoararia | 400
[16 empty] | Total Cost: | 400 | 400
16 | Brain, Body & You (In Person- Brockville) | #3 Community | Format: in-person (?), delivery of all 4 modules Objective: to deliver the best practice content to staff caring for stroke and other complex patients Target Audience: regulated and unregulated staff of LTC/ RH's, and community agencies | [12 empty] | Brain, Body & You
[16 empty] | $200 to support assistant for Mobility session | 200
8836.6
[16 empty] | Total cost: | 9036.6 | 9036.6
17 | Shared Work Day/ Field Experience | All/ Other | Format: one to one, or group collaborative learning Objective: To support group or individual learning needs around stroke expertise Target Audience: All health care providers across the region, across the continuum of care | [12 empty] | Shared Work Day/ Field Experience
|  |  |  | Jun: O; Jul: N; Aug: G; Sep: O; Oct: I; Nov: N; Dec: G |  | 1500
[16 empty] | Total cost: | 1500 | 1500
18 | Provincial Stroke Rounds (Hosted by SNSEO) |  | Format: Webinar (Teams) Objective: To share knowledge, expertise or recent research findings Target Audience: Any/ all stroke rehab providers across providence | [12 empty] | Pronvincial Stroke Rounds
[16 empty] | Honoraria | 200
[16 empty] | Total Cost: | 200 | 200
19 | Symposium |  | Format: In-person conference (full day) Objective: Stroke best practice care update; covering topics as identified by stakeholders across region- themes of access to care, patient experience and change in knowledge, practice over past few years Target Audience: All health care providers in region across continuum of care | [12 empty] | Symposium
[16 empty] | Venue (incl catering) | 12345.5
[16 empty] | Honoraria | 3000
printed materials
[16 empty] | Total cost: | 15345.5 | 15345.5
20 | Continuing Professional Development Fund | All/ Other | Format: Individuals may apply for funding to cover the tuition and associated expenses pertaining to a stroke-related course or program Objective: To support individuals advanced learning and enhance their stroke expertise Target Audience: Any professional working in stroke care across the region, and across the continuum of care | [12 empty] | Continuing Professional Development Fund
|  |  |  | Jun: O; Jul: N; Aug: G; Sep: O; Oct: I; Nov: N; Dec: G | Funding for individual courses | 6500
[16 empty] | Total cost: | 6500 | 6500
21 | Education Resources/ Printing | All/ Other | Format: Printing/ Pourchasing necessary materials Objective:To make availabele educational materials and resources Target Audience: All stroke care providers across continuum of care in our region | [12 empty] | Education Resources/ Printing
[16 empty] | CHEP Membership x 1 | 100
|  |  |  | Jun: O; Jul: N; Aug: G; Sep: O; Oct: I; Nov: N; Dec: G | Stroke Care Posters, Toolkits, Aphasia Institute resources | 2830
Other printing/ purchase?
[16 empty] | Total cost: | 2930 | 2930
22 | Multi-Media/ Communications | All/ Other | Format: Objective:purchase of tools and resources to support the development of online learning, information sharing, communication and evaluation Target Audience: all stroke care providers across continuum of care in our region | [12 empty] | Multi-Media/ Communications
[16 empty] | Adobe Illustrator (533 per license) | 533
|  |  |  | Jun: O; Jul: N; Aug: G; Sep: O; Oct: I; Nov: N; Dec: G | Canva (5 licenses) | 150
[16 empty] | Web Hosting/ mailgun | 1044.12
[16 empty] | Total cost: | 1727.12 | 1727.12
|  |  | Total Education Budget allottment= 61,124.00 | [12 empty] | Cost Summary: |  | 61124.22