## Read Me
STROKE NETWORK OF SOUTHEASTERN ONTARIO
Stroke Network of SEO - Regional Workplan 2019-2021
PRIORITY #1 -PREVENTION: Expand/improve timely equitable regional access to prevention supports and services PRIORITY #2 - HYPERACUTE: Improve timely regional access to hyperacute stroke treatment PRIORITY #3 - ACUTE TO REHAB TO COMMUNITY: Support providers in the clinical implementation of a patient and family-centred approach to bundled funding in acute/inpatient rehab/community stroke care PRIORITY #4 - EXPERTISE & CAPACITY: Sustain/Enhance regional stroke expertise and capacity to deliver best practice stroke care, supporting ongoing connections, recruitment and retention The workplan includes three types of actions: 1. Create 2. Improve 3. Sustain
The workplan supports the Canadian Best practice Recommendations for Stroke Care.
The workplan also aligns with Strategic Directions of CorHealth Ontario, the SE LHIN Integrated Health Service Plan (IHSP) and the MOHLTC Action Plan.
Within several worksheets there are regional and local aspects to the plan with geographic distributions as follows:
*Regional Plan for Southeastern Ontario
*Quinte District Stroke Plan for the Counties of Hastings & Prince Edward (HPE)
*Kingston, Frontenac, Lennox & Addington Counties (KFLA)
*Leeds & Grenville Counties (L&G)
*Lanark County
Please scroll through the different worksheet tabs to read each aspect of the care continuum
Please scroll within each worksheet to read regional and local plans for each aspect of the care continuum
The final 2 worksheets cover the Regional Education Workplan and Leadership & Coordination Requirements
ALIGNMENT with CorHealth Strategic Directions and Goals:
1.Drive Evidence-Informed Practice
Goal 1. Identify, develop and adapt practice standards, guidelines and programs to support integrated evidence-based care.
Goal 2. Optimize the use of standards, guidelines and programs (knowledge translation).
2.Inform Planning, Access and Resource Allocation
Goal 3. Support decision making for system design and resource allocation.
Goal 4. Advise on the effectiveness and appropriateness of services and technologies.
3. Measure and Report on Quality and Outcomes
Goal 5. Advance a measurement and reporting system across the dimensions of quality that supports improvement.
Goal 6. Support a regional and provincial performance management system.
ALIGNMENT with SE LHIN IHSP4 Programs and Initiatives - UPDATE with IHSP5 when ready
1. Support the Hospital Services Project- Health Care Tomorrow, sustainable acute care system
2. Ongoing implementation of the Addictions and Mental Health Redesign
3. Launch an Older Adult Strategy - strengthening the continuum of support care for older adults
4. Build a solid and sustainable primary care system that is well coordinated and linked to other services
5. Building on the success of Health Links, extend improvements through the entire primary and community care sectors
6. Make better use of technology for greater information flow between providers and across the system
7. Expand continuous patient engagement
8. Build comprehensive services through cooperation ( public health, municipalities, other ministries)
9. Enhance Indigenous and Francophone Health Services across our region
ALIGNMENT with MOHLTC Patients First Ontario Action Plan for Health Care - UPDATE
1. Improve access - provide faster access to the right care
2. Connect - Connect services and deliver better coordinated and integrated care in the community, closer to home.
3. Inform - Support people and patients - provide the education, information and transparency they need to make the right decisions about their health.
4. Protect: Protect the public health care system - make decisions based on value and quality to sustain the system
Plan to be reviewed annually based on changing healthcare landscape

## Primary & Secondary Prevention
RSSC Priority #1: To expand/improve timely equitable regional access to prevention supports and services
Reg | Objectives | REGIONAL and Local Implementation Activities - Prevention | Timeline | Lead/Contact
R P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs b) Improve linkages to self-management and community resources | a) COMMUNICATION/ROLES: ▪ Host a follow-up workshop from March 2018 ▪ Enhance access to stroke assessment expertise or consultation in emergency - target 90% ED TIA referral to SPC ▪ Promote transition of information for patient-centred hand-offs (use of Connecting Ontario Clinical Viewer, SHIIP, links to specialists, e-consults) b) LINKAGES: ▪ Make use of self-management programs, smoking cessation resource mapping and physical activity mapping, heart & stroke public education materials including FAST ▪ Increase linkages with www.SEhealthline.ca, community supports (support groups, aphasia programs, return to work resources, support agencies), Community Stroke Rehab Program | a) Workshop Feb 2020 b) ongoing with events | C. Murphy C. Murphy with SPC leads
R P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations b) Improve clinic efficiencies c) Build expertise and partnerships | a) TRIAGE: ▪ Adopt a common SPC triage algorithm in the South East, based on an update of the previous Ontario Triage Algorithm ▪ Establish a common understanding across clinics of triage guidelines ▪ Clarify when to admit TIA ▪ Continue to monitor wait times by triage categories ▪ Address wait times as needed b) EFFICIENCY: ▪ Maximize scope of practice of each interprofessional team member ▪ Make use of e-technology (e-documentation, e-health, e-visits) ▪ Explore strategies to improve access to cardiac testing (share cardiac monitoring devices with SPC, remote interpretation) c) EXPERTISE: ▪ Leverage SPCs as stroke champions with primary care and EDs within local communities (site visits, workshops, rounds) ▪ Address anticoagulation for atrial fibrillation as part of every education event and meeting encounter ▪ Incorporate knowledge translation specific to women and stroke prevention ▪ Spread knowledge/build partnerships with specialists (ophthalmology, vascular surgeons, internal medicine, intensivists) ▪ Build partnerships to support capacity and deliver training in vascular imaging (interpretation, contrast dye administration) ▪ Use a common tool for depression and cognition screening ▪ Make aphasia friendly materials available and continue to increase knowledge of supportive conversation techniques | a) by Feb 2020 b) plan for e-visit spread in 2019-20, initiate in 2010/21 c) Ongoing - build with planned educational events | a)C. Murphy with Local Hospital SPC Leads b)C. Murphy with Local hospital Leads c) C. Murphy and Education Coordinator
R P3 | Support the Indigenous inter-professional Primary Care Team in the regional implementation of an Indigenous vascular risk screening and management program: a) Update guidelines b) Support linkages to cultural safety c) Support education and training | a) GUIDELINES: ▪ Update Indigenous Community Hypertension Awareness Program guidelines and adapt within local communities b) CULTURAL AWARENESS: ▪ Support identification and linkages to specialists and providers with awareness of cultural safety c) EDUCATION: ▪ Support education and training in screening and management protocols to build community volunteer capacity | a) Year 1 b) Year 1 c) Q3/4 of Year 1 and into year 2 | a)C. Murphy b) C. Murphy/C. Martin c)C. Murphy /Education Coordinator
HPE | Objectives | QHC DISTRICT STROKE CENTRE - Prevention | Timeline | Lead/Contact
HPE P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs b) Improve linkages to self-management and community resources | a) COMMUNICATION ▪ participate in regional stroke prevention education activities/workshops ▪ analyze current data and develop action plan to achieve target of 90% TIA ED referral from QHC sites to Belleville SPC b) LINKAGES ▪ Update materials available within QHC SPC for patient resources including smoking cessation ▪ Utilize new physical activity map to incorporate physical activity promotion ▪ Review new heart and stroke materials and incorporate into patient education ▪ Consider referrals for Stroke Support Groups, Stroke Specific Exercise Groups and Community Stroke Rehab Programs if not already linked - consider development of standardized transition referrals | a) by March 2020 b) by December 2020 | a) M. Slapkauskas /DSC b) M. Slapkauskas
HPE P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations b) Improve clinic efficiencies c) Build expertise and partnerships | a) TRIAGE: ▪ Participate in developing and then implement a common South East SPC triage algorithm at QHC ▪ Continue to monitor wait times by triage categories and identify improvement opportunities as needed b) EFFICIENCY: ▪ Trial a different mechanism/model for follow up for inpatients to address longer wait times (e-consult, follow up by discharging IP physician) ▪ Assess feasibility and potential implementation of e-visit model to increase access ▪ Pilot use of MCards for 72 hour cardiac monitoring and reporting c) EXPERTISE: Participate in annual stroke prevention clinic meeting, regional prevention workshop and regional symposium | a. Sept 2019/Feb 2020 b. March 2020 c. June 2019 and Feb 2020 | a. M. Slapkauskas b. M. Slapkauskas c. M. Slapkauskas
KFLA | Objectives | KHSC REGIONAL STROKE CENTRE - Prevention | Timeline | Lead/Contact
K P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs b) Improve linkages to self-management and community resources | a) COMMUNICATION/ROLES: ▪ Attend and participate in planning SPC/Primary Care March 2018 follow up workshop to clarify communication/roles. ▪ Coordinate Regional SPC Nurses Working Group. ▪ Continue to sustain good relationships, awareness of SPC role, & referral processes with HDH UCC, L&ACGH and KGH EDs. ▪ Continue to follow-up and meet with UCC & ED leads regarding SPC processes. ▪ Meet with L&ACGH ED Manager to review TIA referral to SPC & diagnostics-ensure TIA packages are current. ▪ Monitor referral rate from each local ED to SPC. Aim for continued target 90% ED TIA referral to SPC, including L&ACGH. ▪ Continue to use Connecting Ontario Clinical Viewer to enhance communication of info; investigate utility of reviewing Health Links coordinated care plans on SHIIP if available. b) LINKAGES: ▪ Refer to KFL&A smoking cessation and physical activity maps as needed, refer patients to Smoker's Helpline, & update smoking cessation info package. ▪ Continue to update TIA info package with most current heart & stroke resources. Continue to educate patients on FAST. ▪ Provide patients with info on community support services- KFL&A stroke resources located on SEhealthline.ca, support groups, aphasia program, return to work resources, community exercise program. Link patients to Community Stroke Rehab Program. Continue to update TIA info packages with latest community support materials. | a) Workshop Feb 2020 Ongoing sustaining relationships L&ACH Meeting May 2019 b) Ongoing | P. Christie/ Dr. Appireddy
K P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations b) Improve clinic efficiencies c) Build expertise and partnerships | a) TRIAGE: ▪ Advise on common SPC triage algorithm in South East, based on updated Ontario Triage Algorithm. ▪ Host a SPC RN meeting to discuss common understanding of triage guidelines. ▪ Update current SPC CCP to reflect current Canadian Stroke Best Practice Triage guidelines ▪ Continue to review Stroke Distinction data on volume of TIA patients being admitted-participate in review of cases as needed ▪ Collect and report wait times by triage categories and per referral source. Target within 48 hours for Priority 2 patients. ▪ Continue to support daily M-F half day clinics and keeping clinic spot open each day for urgent patients. Troubleshoot a plan for physician coverage during vacation, sabbatical time away. b) EFFICIENCY: ▪ Continue to follow medical directives and update every 3 years. Continue to coordinate triage with physicians. ▪ Update current SPC and TIA D'ced from ED CCP to new Care Guideline format and current best practices. Work with ED lead on EDIS or other regional HIS to update TIA orders. ▪ Expand use of e-visits for any appropriate follow-up patients, develop e-visit eligibility checklist; phase in all SPC physicians/team members and build an interprofessional approach ▪ Spread learnings of e-visits to internal medicine service and share learning for potential spread to other SEO SPC clinics. ▪ Publish pilot findings and present on e-Visit project at May provincial Stroke Rounds. ▪ Expand use of paperless chart-use and refer to e-documentation as possible; build fillable pdf team assessment form. ▪ Monitor ECHO wait times. Monitor processes for patients being referred for outpatient echo post discharge & new option for patients at OP echocardiography lab, Queen's School of Medicine. c) EXPERTISE: ▪ Continue to offer advice & act as stroke champions on TIA management with primary care and EDs (workshops, rounds) ▪ Participate in supporting education event at Primary Care/SPC Feb 2020 session. Consider presenting and/or advising on session on women and stroke prevention & anticoagulation. ▪ Mentor new SPC nurses and physicians (including other SPCs in south east) as needed. Continue to provide educational sessions based on learning needs of EDs and primary care. ▪ Examine data related to anticoagulation. Examine delays in starting anticoagulation. Continue to perform med reconciliation & address patient compliance. Review of barriers to anticoagulation at June 2019 SPC meeting. ▪ Continue to maintain good relationship & connect with other specialists such as diabetes education, vascular surgeons, internal medicine, intensivists and review cases as needed. Meet with ophthalmologists re TIA management. ▪ Continue participation in Stroke Distinction Interprofessional Committee. ▪ Test use of depression and cognition screening DOC components on small subset; test related referral to primary care. ▪ Examine outcome of depression study when completed. Continue to use MOCA when needed. ▪ Modify aphasia friendly materials available at both KHSC SPC sites, as needed. | a) by Feb 2020 Ongoing collecting, reporting data q 3 mos b) Update CCP & order set by Dec 2019 E-visit spread 2019/20. Present May 2019 Rounds; publication in 2019; fillable pdf team assessment form by March 2020 c) Ongoing SPC meeting June 2019 & 2020 | a)P. Christie P. Christie/K.Gray-data b)P. Christie, K. Gray/ Dr. Appireddy/M. Foss/P. Christie/ J. Lalonde c) SPC Physicians/ P. Christie/Jeff Lalonde
K P3 | Support the Indigenous inter-professional Primary Care Team in the regional implementation of an Indigenous vascular risk screening and management program: a) Update guidelines b) Support linkages to cultural safety c) Support education and training | ▪ Continue to support patients of Indigenous ancestry presenting to ED or in transfer (Moose Factory). Continue to maintain well-established referral process from Moose Factory area. ▪ Participate in face-to-face and/or on-line Indigenous cultural sensitivity and safety training to provide culturally safe linkages for the Deseronto and Kingston Indigenous Blood pressure screening program with expansion to region as needed | Ongoing March 2020 | SPC Physicians/P. Christie
L&G | Objectives | LEEDS & GRENVILLE - Prevention | Timeline | Lead/Contact
LG P1 | Enhance timely access to the Stroke Prevention Clinic (SPC) demonstrated by: a) 90% referral rate from the ED b) All referrals reviewed and triaged within 48 hours of receiving | a) Referral from ED ▪ Clinic staff will participate in workshops hosted by the Stroke Network of SEO ▪ Provide regular feedback to the ED physicians and staff re: referrals received, follow-up and outcome to encourage referrals Triage of referral b) ▪ Support staffing model that ensures referrals are triaged in a timely manner to ensure appropriate follow-up. | a) Workshop 2020 Ongoing | D. Henson (contact) D. Henson/ D. Andress/Dr. Riaz D. Henson
LG P2 | Support and implement recommendations made for best practices relating to SPC triage | ▪ Development and implementation of a "Stroke/TIA" lab work panel to ensure appropriate tests are complete for follow-up with SPC ▪ Support staff to attend learning opportunities related to best practice stroke care | In Progress | D. Henson
Lanark | Objectives | LANARK - Prevention | Timeline | Lead/Contact
L P1 | Improve linkages amongst ED, primary and secondary prevention providers | ▪ Improve linkages and referral process to the PSFDH VPC from Brockville General Hospital for patients from Lanark county | 2019 - 2020 | Crystal Newman
L P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice | A) Triage: Decrease number of referrals to Brockville General Hospital for TIA cases where symptoms have resolved by: ▪ Continue regular case review; build communication between PSFDH ED leads and BrGH Hospitalist lead B) Efficiency: Make best use of Imaging Capacity - Improve appropriate use of CTA (and Doppler) for TIA workup in the ED by: ▪ Deliver education for the ED physicians - key concepts on history, physical examination, and appropriateness of CTA. ▪ Consider developing/testing a TIA care pathway or order set for PSFDH with simple poster for the ED. ▪ Provide a template for ordering CTA from the ED, with details on the patient symptoms on the requisition. ▪ Collaborate: KHSC neuroradiology to provide rapid interpretation of Smiths Falls CTA when needed. C) Expertise: Review patient education materials on Rehab floor to ensure consistent information about VPC Clinic and application of evidence based secondary prevention guidelines | a) 2019-2020 ongoing b) by 2021 c) 2019-10 | a) Crystal Newman & Dr C. Duvernet b) Dr Parikh, Dr Islam, with Dr Del Grande, Dr Jin, Dr Duvernet, Imaging, VPC and ED teams c) Crystal Newman

## Hyperacute & Stroke Recognition
RSSC PRIORITY #2: To improve timely regional access to hyperacute stroke treatment
REG | Objectives | REGIONAL and Local Implementation Activities - Emergency | Timeline | Lead/Contact
R E1 | Continuously improve the Endovascular Treatment (EVT) Service within KHSC a) monitor service and ensure quality data b) use data to direct quality improvements | a) MONITORING/DATA QUALITY ● Ensure Data Quality: collaborate with CorHealth, KHSC Medical Records, acute stroke team, IVR team and Information Management in the collection and submission of quality administrative data and creation of accurate outcome reports to accurately monitor the EVT Service b) QUALITY IMPROVEMENT (QI) ● Lead/Deliver QI as needed based on outcomes using standard QI methodology ● Coordinate/lead debriefs when needed to assist process learning and coordination | a) ongoing quarterly outcome reports b) ongoing planning at quarterly EVT workgroup meetings | a) C. Martin/C. Murphy b) C. Martin/Dr. Jin
R E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging b) Implement triage tools within the EDs for the expanded time window; consider findings from pre-hospital screening pilots in other regions | a) RAPID IMAGING: ● Implement RAPID advanced CT perfusion imaging in Kingston ● Implement RAPID advanced CT perfusion imaging in Belleville b) TRIAGE TOOLS: ● Support teaching of large vessel occlusion triage tool within KHSC ED ("ACT-FAST") ● Test the ACT-FAST triage protocol in the KHSC ED and ● Plan & spread the use of a screening tool to other EDs in the region based on learning from the KHSC Pilot ● Consider findings from Champlain/SWO pre-hospital pilots of large vessel screening tools | a) KHSC Q1 2019/20 QHC Q3 2019/20 b) KHSC Q1 2019/20 Region Q4 2019/20 | a) Dr. Jin b) C. Martin/C. Murphy with each ED
R E3 | Create/develop telestroke readiness and an implementation plan with Brockville: a) Support the building of imaging capacity b) Engage stakeholders in readiness planning c) Develop and initiate an implementation plan | a) IMAGING: ● Support capacity and delivery of training in vascular imaging for implementation of 24/7 mCTA b) ENGAGEMENT/SUPPORT: ● Engage stakeholders in readiness planning (CorHealth Ontario, Ontario Telemedicine Network, LHIN, SECHEF, the public, paramedic & pre-hospital services, hospital leaders and providers including physicians) ● Build LHIN-wide support for Brockville telestroke program c) PROJECT PLAN: ● Develop a project implementation plan in year 1 ● Initiate the plan in year 2 | a) Q4 2019/20 b) Q3 2019/20 c) plan by Q4 2019/20 initiate plan in 2020/21 | a) C. Murphy b) C. Murphy c) C. Murphy/Dr Jin
R E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time of <30 mins at KHSC and <45 mins at QHC b) Door-In-Door-Out DIDO transfer time 45 mins | a) DOOR-TO-NEEDLE (DTN): (National target = 30 minute door-to-needle (DTN) time) ● Sustain < 30 minutes at KHSC ● Support progress toward <45 minutes at QHC ● Support QHC to conduct, implement and sustain change ideas from QHC Kaizen Event b) DOOR-IN-DOOR-OUT (DIDO): ● Support progress toward a 45 minute door-in-door-out (DIDO) transfer time at QHC ● Support QHC to conduct, implement and sustain change ideas from QHC Kaizen Event | a) KHSC ongoing QHC start in Q1 2019/20 b) QHC start in Q1 2019/20 | a) Dr. Jin/C. Murphy /D. Damron b) Dr. Jin/ Dr. Samis/ D. Damron
R E5 | Support/Advise KHSC - KGH Interventional Neuro-Radiology (INR) in the planning of a Regional Aneurysm Coiling Service | a) PLAN: Share Learning from EVT work to assist in creation of ● Flow map ● Business case ● Project plan b) ENGAGEMENT: Participate in a coiling workgroup led by Interventional neuroradiology c) REGIONAL ACCESS: When ready, consider plan for spread across region | a) Q1 2019/20 b) Q2/3 2019/20 c) March 2021 | C. Martin/C. Murphy (with D. Tampieri and K. Pearson)
HPE | Objectives | QUINTE DISTRICT - Emergency |  | Lead/Contact
HPE E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging b) Implement triage tools within the EDs for the expanded time window | a) RAPID IMAGING: ● Implement RAPID advanced CT perfusion imaging in Belleville b) TRIAGE TOOLS: ● Implement screening tool in QHC ED (ACT - FAST) to support triage for expanded time window | a. TBD b. Q4 2019/20 | a. M. Coulter/TBD b. M. Roblin
HPE E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time <45 mins at QHC b) Door-In-Door-Out DIDO transfer time 45 mins | a) DOOR-TO-NEEDLE (DTN): (National target = 30 minute door-to-needle (DTN) time) ● Conduct Kaizen quality improvement event in Q1 of 2019/20 to support progress toward <45 mins at QHC ● Implement and sustain change ideas from QHC Kaizen Event/QI improvement mapping ● Address delays in DTN related to nurse assignment for tPA bolus b) DOOR-IN-DOOR-OUT (DIDO): ● Conduct Kaizen/quality improvement event in Q1 of 2019/20 to support progress toward a 45 minute DIDO transfer time at QHC ● Implement and sustain change ideas from QHC Kaizen Event 45 minute door-in-door-out (DIDO) transfer time at QHC | a. Q1 2019/20 start with follow up activities b. Q1 2019/20 start with follow up activities | a.QHC QI Project Lead/M. Roblin/A. Samis b.QHC QI Project Lead/M. Roblin/A. Samis
KFLA | Objectives | KFLA COUNTY - Emergency | Timeline | Lead/Contact
KFLA E1 | Continuously improve the Endovascular Treatment (EVT) Service within KHSC a) monitor service and ensure quality data b) use data to direct quality improvements | a) MONITORING//DATA QUALITY ● Participate in Quality Data Collection with acute stroke team, IVR team, KHSC Medical Records and Information Management for submission of quality administrative data and creation of accurate outcome reports b) QUALITY IMPROVEMENT (QI) ● Continue to monitor the EVT Service ● Participate in QI as needed based on outcomes using standard QI methodology ● Continue to hold debriefs to clarify process as needed and update documents accordingly | a) ongoing quarterly outcome reports and CIHI submission b) ongoing planning at quarterly EVT workgroup meetings | a) A. Dube/E. Brunet b) C. Martin/ C. Murphy/Dr. Jin with EVT Workgroup
KFLA E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging b) Implement triage tools within the EDs for the expanded time window | a) RAPID IMAGING: ● Implement and improve knowledge of RAPID advanced CT perfusion imaging in Kingston ● Support Belleville in learning RAPID advanced CT perfusion when ready b) TRIAGE TOOLS: ● Teach the use of large vessel occlusion triage tool within KHSC ED ("ACT-FAST"); KGH site, then UCC ● Test the ACT-FAST triage protocol in the KHSC ED and make changes based on learning ● Incorporate teaching into ongoing triage orientation at KHSC ED and UCC ● Share learning with region to help with spread other EDs | a) KHSC Q1 2019-20 (QHC Q1 2020-21) b) KHSC Q1 2019/20 | a) Dr. Jin/D. Tampieri Dr Patel b) C. Murphy/ J. Donaldson/ L. McDonough
KFLA E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time of <30 mins at KHSC | a) DOOR-TO-NEEDLE (DTN): (National target = 30 minute door-to-needle (DTN) time) ● Sustain < 30 minutes at KHSC with ongoing reinforcement of acute stroke protocol processes | a) KHSC ongoing | a) Dr. Jin/C. Murphy/J. Donaldson
KFLA E5 | Support/Advise KHSC - KGH Interventional Neuro-Radiology (INR) in the planning of a Regional Aneurysm Coiling Service | a) PLAN: Use learning shared from EVT work to assist in creation of ● Flow map ● Business case ● Project plan b) ENGAGEMENT: Create and lead a coiling workgroup (led by Interventional neuroradiology) c) REGIONAL ACCESS: When INR ready, support KHSC to create a plan for spread across region | a) Q1 2019/20 b) Q2/3 2019/20 c) March 2021 | D. Tampieri/ K. Pearson D. Tampieri/ K. Pearson C. Martin/C. Murphy
L&G | Objectives | LEEDS & GRENVILLE COUNTIES - Emergency | Timeline | Lead/Contact
LG E2 | Support the use of the ACT-FAST triage protocol as appropriate at the completion of the KHSC pilot. | ● Participate in training required to effectively use the triage protocol. | Q4 2020 | N. Valade (Contact)
LG E3 | Create business case for a Telestroke Program at BGH a) Support the building of imaging capacity b) Engage stakeholders in readiness planning c) Develop and initiate an implementation plan | a) IMAGING: ● Support staff in attending training opportunities in vascular imaging for implementation of 24/7 mCTA b) ENGAGEMENT/SUPPORT: ● Engage stakeholders in readiness planning (CorHealth Ontario, Ontario Telemedicine Network, LHIN, SECHEF, the public, paramedic & pre-hospital services, hospital leaders and providers including physicians) ● Build LHIN-wide support for Brockville telestroke program c) PROJECT PLAN: ● Develop a project implementation plan in year 1 ● Initiate the plan in year 2 | a) Q4 2019/20 b) Q3 2019/20 c) plan by Q4 2019/20 initiate plan in 2020/21 | a) B. Yam b) C. Murphy/J. Caffin c)J. Caffin/C. Murphy with Dr. Shenfield and Dr Jin
Lanark | Objectives | LANARK COUNTY - Emergency | Timeline | Lead/Contact
L E2 | Implement triage tools within the Eds for the expanded time window at PSFDH | Adopt and implement the triage screening tool in both emergency departments of PSFDH | Q4 2019/20 | J. Drynan

## Acute-Rehab-Community Pathway
RSSC Priority #3: Support providers in the clinical implementation of a patient and family-centred approach to bundled funding in acute/inpatient rehab/community stroke care
REG | Objectives | REGIONAL and Local Implementation Activities - Acute-Rehab-Community | Timeline | Lead/Contact
HPE |  | QUINTE DISTRICT - Acute-Rehab-Community
KFLA |  | KFLA COUNTY - Acute-Rehab-Community
L&G |  | LEEDS & GRENVILLE COUNTIES - Acute-Rehab-Community
Lanark |  | LANARK COUNTY - Acute-Rehab-Community
R A-R-C 1 | Participate in provincial CorHealth Ontario Bundled Funding Stroke Workgroup and link to provincial and local Communities of Practice a) Build provincial links b) Establish regional links | a) PROVINCIAL ● Participate in CorHealth Workgroup ● Participate in provincial Communities of Practice relevant to stroke bundled funding b) REGIONAL ● Establish two-way communication links with our regional partners to support regional/provincial implementation | ongoing participation in workgroup and any new forums | C. Martin/S. Huffman
R A-R-C 2 | Adapt the provincial Bundled Funding Pathways and related expectations for our region to enable implementation of common components and parameters of regional transition protocols and services a) Develop a SE Stroke Pathway with common components and parameters in alignment with bundled funding/QBP standards. b) Translate into local pathways for west, central, east | a) SOUTH EASTSTROKE PATHWAY(S) (algorithm for who goes where when and how that is supported) i. Admission to Acute Stroke Unit Care ii. Acute to Home without Rehab needs ● i.e., Secondary stroke prevention, community supports iii. Acute transition to rehabilitation (inpatient, early supported discharge, outpatient, home-based rehab) ● i.e., standardized use of Alpha FIM, standardized timeframes for acceptance and transition to rehab service iv. Inpatient Rehabilitation transition to Community Based Rehabilitation (outpatient or in-home) ● i.e., standardized wait time to first rehab visit; standardized service model v. Community Supports to stay well when transitioning from any of the above ● i.e., Stroke Support Groups including Indigenous Supports, stroke-specific exercise group, aphasia conversation group and self-management groups b) LOCAL PATHWAYS as above | a) May 2019 b) May 2019 for bundled funding sites | a) S. Huffman b) S. Huffman
R A-R-C 3 | Deliver Local/Regional Forum(s) and Education to facilitate clinical implementation of bundled funding. This will: a) Inform providers of current state, expectations and gaps b) Identify priorities for change/action c) Deliver a Regional Forum to support knowledge translation in bundled care and local action plans | a) CURRENT STATE, EXPECTATIONS, GAPS ● Use the SE LHIN Rehab Capacity Assessment to inform current state ● Use provincial bundled funding self-assessment tools b) IDENTIFY PRIORITIES for CHANGE ● Identify priorities for change in each local area to meet bundled funding expectations c) REGIONAL FORUM ● deliver education on bundled funding highlighting experience of early adopters ● invite speakers to support learning in identified areas of change priorities ● support QI approach to facilitating implementation of local priorities for changes | a) June 2019 b) June 2019 c) Regional Forum in Sept 2019 | a) S. Huffman b) S. Huffman with local leads c) S. Huffman and Education Coordinator
R A-R-C 4 | Pilot change opportunities to support local pathway adoption (i.e., key changes in delivery models or transitions in each local area) | LOCAL ADOPTION ● Confirm selected priorities for change within each local area ● Develop local plans to address necessary changes ● Implement, test and modify at least one key change opportunity per local area ● Plan for sustainability and spread of positive changes | June 2019 to March 2021 | S. Huffman with local leads

## Expertise & Capacity
#4 EXPERTISE & CAPACITY: Sustain/Enhance regional stroke expertise/capacity to deliver best practice stroke care, supporting ongoing connections, recruitment and retention
REG | Objectives | REGIONAL and Local Implementation Activities - Knowledge Translation | Timeline | Lead/Contact
R KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Contribute to human resource recruitment and retention within stroke care b. Support champions and staff in relevant learning needs c. Collaborate with partners in learning (e.g. ABI, Behavioural Support Teams, Learning Collaboratives) d. Utilize on-line learning strategies Detailed in Local Plans | Ongoing | Regional Team
R KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Sustain Stroke Distinction program at KHSC (EVT, oral health, aphasia etc) b. Support QHC in applying to Stroke Distinction Program; initiating self assessment and survey preparation c. Support stroke teams to identify best practice initiatives e.g. acute and integrated stroke unit best practices, rehabilitation best practices, community rehabilitation best practices Detailed in Local Plans | a. Ongoing b. Apply by Sept 2020 c. Ongoing/See Local Plans | a. C. Murphy b. D. Damron/DSC c. Regional Team
R KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Gather information on these roles in other parts of the province. b. Support local providers in practice changes and local implementation pilots Detailed in Local Plans | a. March 2020 b. March 2021 | a. G. Brown/S. Huffman b. G. Brown/S. Huffman
R KT4 | Ensure access to Aphasia Conversation Groups across the region | a. Sustain the Kingston and Belleville aphasia conversation groups b. Support SE LHIN Home and Community Care in the evaluation of new aphasia conversation groups (Kingston) c. Support the spread of the aphasia conversation groups region-wide | a. March 2020 b. June 2019 c. March 2021 | a. G. Brown b. G. Brown c. G. Brown
R KT5 | Community & LTC - Enable stroke survivors & caregivers to live in the community supported by programs & services that optimize quality of life in these domains: a. Person-Centred Skilled Stroke Care & Rehabilitation b. Community Co-Navigation c. Individual Well-Being & Meaningful Engagement d. Access to Supports & Services e. Supported Mobility in the Community | a. Person-Centred Skilled Stroke Care & Rehabilitation ● Integrate patient/client experience/outcomes into the Community Stroke Rehabilitation Program (CSRP) evaluation ● Present findings of CCC/LTC Report in LTC venues (e.g. Behavioural Support Networks); collate feedback to identify learning opportunities ● Support the regional implementation of Stroke Information Packages ● Support the SE Learning Collaborative sessions ● Promote uptake of LTC Stroke Care Plans, Brain, Body & You, Education Posters, TACLS & other resources ● Promote use of Shared Work Day b. Community Co-Navigation ● Evaluate effectiveness of Kingston Community Stroke Expo with potential to offer similar event in HPE and LLG ● Complete and implement Patient Journey Map to support navigation and effective transitions ● Community Reintegration Leadership Team to review provincial navigation models; explore/leverage findings within SE ● Complete pilot of Community Reintegration Questionnaires and evaluate findings to identify next steps ● Pilot the integration of a Transitions Checklist into the Community Stroke Rehab Program ● Support connections to support groups and community services after discharge ● Raise awareness of website resources: Healthline Stroke Resources and Stroke Network Community Supports c. Individual Well-Being & Meaningful Engagement ● Support changes to supports groups in response to changing demographics (e.g. younger age, growing volumes, need for 'graduate' social-recreational groups) ● Coordinate & facilitate regional teleconferences for SE Stroke Support Group Facilitators ● Support re-establishing Stroke Specific Exercise Program in Brockville and sustain existing SE programs ● Support evaluation of Kingston aphasia buddies program and potential to expand to other areas of the SE ● Support expansion of stroke support group services both on-site (e.g. Napanee) and via Telemedicine using OTN ● Sustain peer visiting in Brockville & Perth and expand to Belleville & Kingston ● With Indigenous communities, explore stroke survivor & caregiver support group concept starting with Quinte ● Collate regional data and deliver Annual Stroke Support Group Evaluation Reports with recommendations to SE LHIN ● Support delivery of Self Management Programs including the Living with Stroke (LWS) Program annually in each area ● Promote awareness and uptake of SE Return to Work Toolkit d. Access to Supports & Services ● Continue to advocate for referrals to social work for assistance with financial supports and services ● Include information/presentations on financial supports & services in relevant workshops/education sessions e. Supported Mobility in the Community ● Continue to advocate for transportation supports ● Promote awareness of SWO Driving Resource and adapt resource to SE | March 2020 March 2020 December 2019 Ongoing Ongoing April 2019 January 2020 March 2020 October 2019 September 2019 Ongoing Ongoing Ongoing Ongoing September 2019/Ongoing September 2019 Ongoing March 2020 March 2020 Ongoing Ongoing Ongoing Ongoing Ongoing Ongoing Ongoing/April 2019 | a. G. Brown b. G. Brown c. G. Brown d. G. Brown e. G. Brown
HPE | Objectives | HPE COUNTIES/QUINTE DISTRICT - Knowledge Translation | Timeline | Lead/Contact
HPE KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Assess needs and deliver follow up education for nursing staff on the Integrated Stroke Unit (IISU) b. QHC sending PT and PTA staff to participate in PT Neuro 101 Clinical Education Course c. Participate in Regional Stroke Symposium in Nov 2019 through planning committee and facilitating staff attendance (ISU nursing and allied team members) | a. Winter /Spring 2020 b. May 2019 c.. May - Nov 2019 | a. M. Roblin b. D. Damron c. M. Roblin/DSC
HPE KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Implement standardized process for patient education and stroke information packages on the ISU for acute and rehab patients b. Plan and implement stroke peer visiting service with Community Care for South Hastings c. Maintain Alpha FIM certification of therapy staff including those covering ISU on weekends to achieve improvements to align with Regional/Provincial Alpha FIM completion target (?? increase to 90% when excluding those discharged/die in 2 days or less). d. Complete a readiness assessment to apply for Accreditation Canada Stroke Distinction including access to data for required indicators e. Implement standardized process for community linkages during and following Day Rehab f. Apply for Stroke Distinction for Acute and Rehabilitation Program | a. May 2019 - Dec 2019 b. June 2019 c. April 2019 training & quarterly monitoring d. June 2020 e. DSC f. Sept 2020 | a. D. Damron/M. Roblin/OT Lead b. D. Damron/M. Roblin/OT Lead/DSC/ L. Pyle c. J. Levy/D. Damron/DSC/S. Huffman d. DSC/D. Damron e. DSC f. DSC/ D. Damron
HPE KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Assess therapy pairs model and utilization of therapy assistants on the ISU. | a. Dec 2019 | a. D. Damron and therapy leads
KFLA | Objectives | KFLA COUNTY - KHSC Knowledge Translation | Timeline | Lead/Contact
KFLA-KHSC KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Contribute to human resource recruitment and retention within stroke care • Emphasize retention of new stroke team members through ongoing interprofessional collaboration & mentorship • Evaluate schedule of added allied health resource and case manager support: OT (0.4 FTE), OTA Assistant (0.2 FTE), PT (0.4 FTE), RD (0.2 FTE) & SLP (0.5 FTE) and Case Manager/Stroke Specialist (0.6 FTE) • Submit and follow up on business cases/funding opportunities for a) new stroke neurologist and b) hospitalist b. Support champions and staff in relevant learning needs • Use the Stroke Distinction self-assessment findings to identify the focus for enhancing stroke care competencies • Deliver education inservices targeting specific/top needs (see below under KT2) • Continue to host annual KHSC Neurosciences Workshop in Q4 • Continue to support orientation of new staff to best practice stroke care (e.g., internal stroke protocol, ED/IVR/CC/Kidd 7 orientation) • Send at least one stroke team member to congress annually and support interprofessional team stroke education • Promote local Brain, Body and You and shared work day resources, provincial interprofessional stroke competency resources & national resources - Canadian Stroke Best Practice Recommendations, TACLS c. Collaborate with partners in learning • Collaborate in planning & delivery of knowledge translation activities (e.g., regional stroke symposium Nov 2019, Acute Care Collaborative Follow-up & development of resources such as posters and pocket cards) d. Utilize on-line learning strategies • Continue use of LMS modules (e.g., dysphagia screening) • Develop one additional stroke related LMS module (e.g. oral health, falls prevention, smoking cessation or mobilization) • Pursue use of IPAD technology as SLP and OT stroke treatment tool • Review Partners in Stroke Recovery iBook for currency | a. stroke team schedule decisions by June 2019; medical staff business cases by fall 2019 b. Ongoing c. Ongoing d. March 2021 | a. Professional Practice Leaders and Dr Jin b. ASU team, Clinical Learning Specialists for each relevant area c. ASU team, Regional Stroke Education Coordinator d. ASU team and Jennifer Rogers
KFLA-KHSC KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Sustain Stroke Distinction program at KHSC • Develop a more streamlined plan with Decision Support Specialist for more automated quarterly data • Inform regional HIS project team of required information and decision support tools • Continue collective review of stroke indicators every 6 months; publish annual KHSC Stroke Distinction Data Infographic • Emphasize monitoring ASU utilization. Target ≥ 75% ASU Utilization. • Incorporate stroke unit patient/family satisfaction survey • Complete self-assessment against Stroke Distinction Standards every 2 years (spring 2021) b. Support QHC in applying to Stroke Distinction Program; initiating self assessment and survey preparation • Share key documents and learnings c. Identify, prioritize and deliver best practice/QI initiatives • Review and update Stroke Distinction action priorities every 6 months (using Distinction data, self-assessment, 2018 Report). • Participate in QI initiatives based on currently ranked Stroke Distinction action priorities with a focus on: • Acute stroke unit utilization & patient flow - expand stroke unit capacity and improve transition options • Dysphagia screening process - consider how to capture intubated patients in ICU; continue education beyond Kidd7 • Oral health guideline implementation • Aphasia friendly patient resources • Hemorrhagic stroke project findings • Mobilization cues including falls prevention • Update CCPs, Order Sets in 2021. Investigate updating of CCP to new KHSC care guideline format | a. Ongoing with automated reports by March 2020; self assessment Spring 2021 b. March 2020 c. March 2021 | a. C. Murphy, KHSC Stroke Distinction Committee b. C. Murphy c. ASU team with ED and Critical Care leads
KFLA-KHSC KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | • Consider introducing rehab assistants at KHSC including related labour implications | March 2020 | Kim Smith and professional practice leaders
KFLA | Objectives | KFLA COUNTY - PCH Knowledge Translation | Timeline | Lead/Contact
KFLA-PCH KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Partnering with Stroke Network to host Neuro Physio 101 (2 day clinical course for up to 50 PT and PTAs from across the region) with neuro experts b. Participate in regional stroke network activities and education opportunities such as Regional Stroke Symposium c. Participate in shared work day program as opportunities arise and link stroke team expertise with others in the region d. Develop Art Therapy program and toolkit for therapy. Includes Field experience training session with Marta Scythes for introductory art therapy training with volunteers to develop summer program (2019) with spread to PTA/OTAs to support adjunct therapy tool (2019/20). Plan to explore making an educational video to share with community/LHIN/stakeholders. e. Follow up to Supportive Conversation (SCA course in Dec 2018) for Aphasia to sustain the learning, toolkits are being developed for patients/family and staff to use. | a. May 2019; b. Nov 2019 and ongoing; c . Ongoing d. June 2019 for volunteer program; Jan 2020 for PT/OTA e. Initial toolkit June 2019 with ongoing follow up/training | a. P. Harvey/S. Huffman b. Stroke team c. Stroke Team d. B. Ritsma/M. Scythes/Stroke Team e. J. Bouchard/K. Colwell
KFLA-PCH KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. GRASP Program (Hand Rehab program) for Stroke patients that PCH is now offering CVA patients. PCH OT's have trained assistants who are delivering the program. b. Rehab Intensity Therapy refresher in May 2019 with quarterly reporting transferred to stroke team c. Mental Health Peer Support in community reintegration expanding to CVA population d. Mindfulness based meditation will be explored to be offered to CVA patients (currently provided to SCI patients). e. Participate and co-lead patient flow quality improvement workgroup to identify and test process changes to improve onset to rehab time and flow through PCH (ie development of short form for stroke rehab referrals and communication tool with neurology/physiatry) | a. March 2020 b. May 2019 and ongoing c. June 2020 d. June 2020 e. April 2019 - ongoing through 2 year plan | a.. P. Harvey/OT b. K. Colwell/S. Huffman c. K. Colwell d. K. Colwell e. K. Colwell/B. Ritsma/J. Mels-Dyer
KFLA-PCH KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | Exploring the ability to enhance role for rehabilitation assistants with stroke patient by training and developing protocols for assistants in in Functional Electrical Stimulation (Bioness) to assistants | a. March 2020 | a. P. Harvey/B. Ritsma/ MJ Demers
L&G | Objectives | LEEDS & GRENVILLE COUNTIES - Knowledge Translation | Timeline | Lead/Contact
LG KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Contribute to human resource recruitment and retention within stroke care • Recruit new champions and staff to prepare for the move of some stroke-related services to our new patient tower • Build up staffing to support increased activity associated with Telestroke and an Integrated Stroke Unit b. Support champions and staff in relevant learning needs • STAND: Plan process for STAND orientation, monitoring, and sustaining • CNS: Determine process for CNS monitoring • Hemi-Arm: Deliver knowledge exchange on key points of hemi-arm protocol. Investigate communication tools such as poster, more use of white boards • Acute Stroke Protocol: Review what is done when witnessing inpatient with signs of stroke. Learn about updated Acute Stroke Protocol from Regional Team c. Collaborate with partners in learning • Support new team members to attend educational opportunities including shared learning days at KHSC • Participate in planning Regional Stroke Symposium Nov 2019 • Identify knowledge gaps and inform regional team to help populate the education plan d. Utilize on-line learning strategies • Provide time for staff to use on-line learning strategies as they are made available (e.g., on-line dysphagia screening modules) | Ongoing | BGH Managers/Local team
LG KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Integrated Stroke Unit (ISU): • Develop project plan for Integrated Stroke Unit in our new patient tower as part of our Operational Readiness work to be ready for implementation as we take occupancy. Engage stakeholders as plans start to be developed (e.g.., physicians, internal medicine, nursing, allied & other ISU leads/experts). Project plan to also include communication strategy, implementation (e.g., recruitment-see LG KT1 a., education, training, equipment ) - and evaluation & sustainability. • Implement project plan for ISU • Monitor b. Deliver best practice/QI initiatives • Decrease volume of TIA admissions by 5% • Conduct case reviews between PSFDH ED Physician Lead and Hospitalist Lead • Revisit repatriation processes to PSFDH Rehab | a.Develop Project Plan Dec 2019 Implement ISU April 2020 b. Case Reviews-Ongoing Repatriation to PSFDH-Apr 2020 | a. T. Wing/J. Caffin with Regional Stroke Team b. Case Reviews: Dr. Duvernet (PSF), Dr. Sharma PSFDH Repatriation: BGH/PSFDH Managers/Flow Coordinators/S. Huffman
LG KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Review models for rehabilitation assistants related to Integrated Stroke Units and consider options for change for BrGH (may include possible CDA role, and new ways to use assistants across acute and rehab) b. Plan and implement any identified change opportunities for rehab assistant models in conjunction with launch of ISU c. Monitor and sustain use of rehabilitation assistants in contributing to rehabilitation intensity minutes and ensure data quality consistency for rehab assistant time collected with any changing staff or roles. | a. Dec 2019 b. Sept 2020 c. Ongoing | a. T. Wing and S. Huffman b. T. Wing/A. Rodgers c. A. Rodgers b. Case Reviews: Dr. Duvernet (PSF), Dr. Sharma PSFDH Repatriation: BGH/PSFDH Managers/Flow Coordinators/S. Huffman
Lanark | Objectives | LANARK COUNTY - Knowledge Translation | Timeline | Lead/Contact
L KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. All team members participate in local stroke education as available and relevant to roles. b. Team members to consider use of shared work day or field training to provide learning related to stroke care across the continuum. c. Utilizing our Learning Management System (LMS), work with KGH and BGH to determine the feasibility for common educational modules for education and ongoing training that can be shared in order to ensure consistent practices | a. Ongoing b. As required with new staff or changes to practice c. develop timelines at next regional meetings | J.Torode, K.Kehoe, K.Stolee
L KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Review inpatient admissions from Brockville and identify any process improvements to improve transitions and work in collaboration with BGH to jointly problem solve any issues that arise. b. Participate in adopting any changes to the Community Stroke Rehabilitation Program and provide feedback on program. c. Utilizing experience and learnings from the implementation of Patient Oriented Discharge (PODs), improve the content and utilization of patient discharge packages etc. d. Build a better understanding of patients' therapy experience in terms of intensity of treatment, frequency and other treatment factors for community PT (ie Community Stroke Rehab Program ) to better inform referrals. e. Sustain peer stroke support volunteers linked with the Perth Stroke Support Group | a. Ongoing b. As required c. Complete a consultation of patients through follow up phone calls and support service stakeholders for feedback from September -December 2019 d. Ongoing e. Ongoing | J.Torode, K.Kehoe, K.Stolee
L KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Participate in gathering information on these roles across the province by providing details related to our own hospital practices. b. Participate in practice changes and local implementation pilots as required. | a. As required b. As required | J.Torode, K.Kehoe, K.Stolee

## Education Plan 2019-20
SOUTHEASTERN ONTARIO KNOWLEDGE TRANSLATION PLAN 2019/2020 ($68,215) Updated February 16, 2019 FINAL
Program/Project |  |  | Task | Timelines | [11 empty] | Budget
| Regional |  |  | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20
| Priorities |  |  | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar
PROJECT 1 |  | Target Audience: | [13 empty] | Project 1: Primary Care/SPC Collaborative
|  | Stroke Prevention Clinic and targeted primary care providers | Needs Survey
|  | from across Southeastern Ontario | Plan workshop | [12 empty] | Venue & Catering 58$/person x 85 | 4930
Primary Care | Primary & | Objective: | Registration | [12 empty] | CME (20$ x 85ppl) | 1700
Stroke Prevention Clinic | Secondary | Enhance implementation of secondary stroke prevention between primary care and Secondary Prevention Clinics through | Workshop Delivery | Feb: TBD | Honorariums | 2400
Collaborative Update | Prevention |  | Evaluation | [12 empty] | Teleconference | 30
|  | best practice and collaboration. | [13 empty] | Printing/supplies | 250
[16 empty] | Travel, hotel and meals | 250
[16 empty] | Advertising CME office | 350
|  | Date: TBD February | [13 empty] | Total Cost: | 9910
PROJECT 2 |  | Target Audience: Blood Pressure screeners | [13 empty] | Project 2: Deseronto Indigenous Blood Pressure Screening Program
|  | Objective: Train and support blood pressure screeners. | Workshop delivery | [12 empty] | Supplies, printing and promotion | 300
Deseronto Indigenous | Primary & |  | Screening program planning | [12 empty] | Venue/meeting space | 400
Blood Pressure | Secondary |  | Screen program advertising | Aug: Ongoing | Catering | 400
Screening Program | Prevention |  | Screening program delivery | [12 empty] | Travel | 400
Evaluation
|  | Date: Ongoing | [13 empty] | Total Cost | 1500
PROJECT 3 |  | Target Audience: Regional Stroke Prevention Clinic Staff | [13 empty] | Project 3: Regional SPC Best Practice & Process Meetings
Objective: One half day meeting designed to meet 1) best
| Primary & | practice learning needs (e.g. case study review); and 2) process | Planning Meeting | [12 empty] | Catering (25$ x 16) | 400
Regional | Secondary | needs related to the core elements self-assessment & clinic data. | Confirm speakers | [12 empty] | Holiday Inn Express Room Rental | 375
Stroke Prevention Clinic | Prevention |  | Meeting Delivery | [12 empty] | Honorarium | 1000
Best Practice & Clinic |  |  | Evaluation | [12 empty] | Teleconference | 20
Process Update Meeting | [15 empty] | Printing/supplies | 150
[16 empty] | Travel | 300
[16 empty] | QHC Covering 2 physician honorariums (800$) | 0
|  | Date: June 2019 | [13 empty] | Total Cost | 2245
PROJECT 4 |  | Target Audience: Radiology Technologists at Brockville | [13 empty] | Project 4 Diagnostic Imaging Training
General Hospital
| Primary & | Objective: Support training Radiology Technologists | [13 empty] | Michener Institute Tuition 599$ x 2 participants | 1198
Diagnostic Imaging | Secondary | at Brockville General Hospital to perform administration of | Contrast Injection Dye Course | [12 empty] | Text Books for CAMRT | 400 | bar: Apr to May; July to Sept; Nov to Feb
Training | Prevention | contrast dye for CT and CTA during vascular | 2 Online CAMRT Courses | [12 empty] | CAMRT online courses 375 x 2 courses | 750
| & | imaging required for EVT and secondary stroke prevention.
| Hyperacute | Note: Registrants are encouraged to apply to Allied Health Fund
to maximize coverage of additional expenses (e.g. Travel, hotel)
|  | Date: Spring, Fall or Winter (dates TBD) | [13 empty] | Total Cost | 2348
PROJECT 5 |  | Target Audience: BrGH, PSFDH, & QHC Physicians | [13 empty] | Project 5: Physician Update
|  | Objective: Develop medical skills in acute stroke unit care at BrGH and PSFDH. | Identify learning needs
Physician Updates | Primary & |  | Plan sessions | Aug: Ongoing | Participant bursary (~200$pp) | 1200
Acute Stroke Unit, ED | Secondary | May include site visits, Physician Champion | Deliver sessions | [12 empty] | Lunch $15/person x 40 | 600
& Critical Care | Prevention | mentoring, and skill training (e.g. tPA, telestroke, and | Evaluation | [12 empty] | Travel | 300
| & | acute complications)
Hyperacute
|  | Date: TBD | [13 empty] | Total Cost | 2100
PROJECT 6 |  | Target Audience: BrGH ED & Critical Care teams | [13 empty] | Project 6: Telestroke Planning
|  | Objective: Engagement/planning for Telestroke at BrGH | [13 empty] | Speaker honorarium | 400
|  |  | Planning meetings | Aug: Ongoing | Printing | 245
Telestroke Planning | Hyperacute | [14 empty] | Lunch $15/person x 25 | 375
[16 empty] | Travel/parking | 600
[16 empty] | Telephone | 60
|  | Date: TBD | [13 empty] | Total Cost | 1680
PROJECT 7 |  | Target Audience: Acute-rehab-comm staff developing | [13 empty] | Project 7: Integrated Transition Pathway Development
|  | integrated transition pathways in SEO. | Planning meetings | [12 empty] | Venue & Catering (39$ + tax/gratuities)x75ppl+AV) | 4824
Integrated Transition | Integrated | Objective: Support the implementation of integrated | Think Tank Event | Sept: TBD | Honoraria | 1000
Pathway Development | Pathway | transition acute-rehab-community pathways across SEO | Evaluation Monitoring | [12 empty] | Travel/Parking | 700
Support & Education | Acute - Rehab - | [14 empty] | Printing & supplies | 200
"Think Tank" | Community | [14 empty] | Teleconference | 100
|  | Date: September TBD | [13 empty] | Total Cost | 6824
PROJECT 8 | Expertise | Target Audience: 1 SLP BrGH & Front line Staff | [13 empty] | Project 8: Training in Supportive Conversation
Objective: Train Stroke Champions in Supportive
|  | Conversation skills. | [13 empty] | A2 & A3 Registration (paid by Aphasia Institute) | 0
|  | Projects Offered: | [13 empty] | Travel and accommodations x1 for A2 and A3 | 600
Training in Supportive |  | 1) Aphasia Institute Training: 1 BrGH SLP stroke champion | Confirm registrant
Conversation |  | A2, & A3 | Course participation | [12 empty] | Field Training (100$/hour) | 1000
2) Communication Training (Field Training Format)
|  | Date: June 7 Ongoing | [13 empty] | Total Cost | 1600
PROJECT 9 |  | Target Audience: PTs & PTAs (primarily focused on newer | [13 empty] | Project 9: Neuro Physio 101
grads/less experienced PTs and PTAs in acute, rehab and
|  | community. | Session planning | [12 empty] | Presenter Fee (4750$-1500$=$3250) | 3250
Neuro Physio 101 | Expertise | Objective: Highlight current thinking and evidence-informed | Confirm location | [12 empty] | Catering 65 ppl x2 days breaks | 500
|  | practice that touches on different treatment approaches, and | Advertising | [12 empty] | Printing | 200
|  | covers a variety of clinical conditions and functional impairments. | Session delivery | [12 empty] | Telephone | 60
|  | Co-hosted by SEO Stroke Network & PCH | Evaluation | [12 empty] | Travel/Parking | 370
[16 empty] | Accommodation/meals | 980
|  | Date: May 25 & 26 | [13 empty] | Total Cost | 5360
PROJECT 10 |  | Target Audience: Members of the Interprofessional | [13 empty] | Project 10: University of Alberta Stroke Rehab Certificate
Rehabilitation Team at Brockville General Hospital (OT & PT)
|  | Completing course #3 of 3. | [13 empty] | 600$ x 2 participants x 1 course | 1200
University of Alberta | Expertise | Objective: This online graduate level credit certificate is an | Register & begin courses
Certificate in Stroke |  | inter-disciplinary stroke rehabilitation program designed to
Rehabilitation |  | address the learning needs of rehabilitation clinicians across
the continuum of care. This will support quality improvement and
leadership skill development at BrGH.
|  | Date: Fall 2019 | [13 empty] | Total Cost | 1200
PROJECT 11 |  | Target Audience: Nursing, Allied Health and PSW’s working | [13 empty] | Project 11 : Brain, Body & You
in Acute, Complex Continuing Care, Community,
Retirement Homes, and LTC
Objective: Interactive modules
|  | designed to teach regulated and unregulated care providers | Select dates and location | [12 empty] | Run 2 Modules - SLC cost 80$x48 registrants | 3840
Brain, Body & You | Expertise | caring for stroke survivors and other complex patient | Confirm presenters
Modules |  | populations. Delivered through St. Lawrence College | Circulate registrations
|  | Based on the H&S manual "Taking Action for Optimal | Workshop delivery
|  | Community & Long-Term Stroke Care" (TACLS). | Evaluation
|  | Date: March 2020 | [13 empty] | Total Cost: | 3840
PROJECT 12 |  | Target Audience: Health care providers working in | [13 empty] | Project 12: LTC & Community Collaborative "Pain & Behaviour"
Community & LTC
|  | Objective: Introduction to Pain, manifestations of pain, | Plan workshop
LTC & Community | Expertise | assessment tools and non pharmacological interventions. | Advertising/Registration
Collaborative |  | Topics include pain in stroke, the 3 D's, pain and behaviour, | Workshop Delivery | bar: Apr to Mar
"Pain & Behaviour" |  | common sources of pain, assessment tools and | Evaluation | [12 empty] | Refreshment | 200
|  | non pharmacological interventions. | [13 empty] | Printing | 100
[16 empty] | Travel | 420
|  | Date: April 11 (HPE), 12 (KFL&A), 25 L&G,30 (Lanark) | [13 empty] | Total Cost: | 720
PROJECT 13 |  | Target Audience: Health care providers from across the | [13 empty] | Project 13: Southeastern Ontario Stroke Symposium
|  | continuum of care | Needs Survey
| All Priorities |  | Plan workshop | [12 empty] | Sound (1400) | 1400
Southeastern Ontario | & | Objective: Stroke Best Practice Update. Covering topics | Advertising/ Registration | [12 empty] | Venue 150 x 75$/person +AV (100) | 11500
Stroke Symposium | Expertise | identified from across the continue of care. | Workshop Delivery | [12 empty] | Honorariums | 4000
|  |  | Evaluation | [12 empty] | Teleconference | 100
[16 empty] | Printing/supplies | 1000
[16 empty] | Travel, & accommodations | 1400
[16 empty] | Parking | 220
[16 empty] | Poster boards | 150
|  | Date: Nov 27 | [13 empty] | Total Cost: | 19770
PROJECT 14 |  | Target Audience: Health care providers working in | [13 empty] | Project 14: Shared Work Day & Field Experience
stroke care in SEO. Includes Retirement Home Staff.
Shared Work Day & | Expertise | Objective: To support individual or group education needs | Advertise Program | Aug: Ongoing | Incentive to cover honoraria and costs for trainers | 4500
Field Experience |  |  | Learning Events
Evaluation Monitoring
|  | Date: Ongoing | [13 empty] | Total Cost | 4500
PROJECT 15 |  | Target Audience: All health care providers | [13 empty] | Project 15: Education Resource, Posters & Printing
across the continuum of care
|  | Objective: Make available education print materials, | Print/purchase as required | Aug: Ongoing | TACLS (T&T Manual) B&W spiral $10.66x50 | 533
Educational Resources | Expertise | and resources.
& Printing
[16 empty] | Annual CHEP membership | 100
|  | Date: Ongoing | [13 empty] | Total Cost | 633
PROJECT 16 |  | Target Audience: Health care providers working | [13 empty] | Project 16: Multi Media & Communication
across the continuum of care
|  | Objective: Website support, tools and resources needed to | Plan projects | Aug: Ongoing | Program development support:
Multi Media |  | support the development of online learning, communication | Identify supports needed | [12 empty] | Website hosting | 1250
& | Expertise | and evaluation. | [13 empty] | Infographic training & Support (25$/hr x 12 hrs) | 300
Communication | [15 empty] | Infographic program (illustrator 31 US /mos) | 480
[16 empty] | Online Meeting Software (Adobe Connect ) | 640.57
[16 empty] | Survey Monkey Team Package annual cost | 1314
|  | Date: Ongoing | [13 empty] | Total Cost | 3984.57
SUMMARY OF ACTUAL EXPENSES
[16 empty] | Project 1 | 9910
[16 empty] | Project 2 | 1500
[16 empty] | Project 3 | 2245
[16 empty] | Project 4 | 2348
[16 empty] | Project 5 | 2100
[16 empty] | Project 6 | 1680
[16 empty] | Project 7 | 6824
[16 empty] | Project 8 | 1600
[16 empty] | Project 9 | 5360
[16 empty] | Project 10 | 1200
[16 empty] | Project 11 | 3840
[16 empty] | Project 12 | 720
[16 empty] | Project 13 | 19770
[16 empty] | Project 14 | 4500
[16 empty] | Project 15 | 633
[16 empty] | Project 16 | 3984.57
|  |  |  | Sept: AVAILABLE BUDGET 68,215.00 | Total Cost | 68214.57

## Leadership & Coordination
Leadership & Coordination
REG | Objectives | REGIONAL and Local Implementation Activities- Leadership & Coordination | Timeline | Lead/Contact
R L&C1 | A. Plan Successions to build and mentor new leaders within the regional stroke program B. Develop Stroke Team Leadership Skills and Sustain Engagement | A. Develop and support leadership knowledge and skills as change agents (change and project management, quality improvement, evaluation). Watch for opportunities to recruit new leaders for succession planning. B. Develop Stroke Team Leadership Skills and Sustain Engagement • Sustain funded stroke centre/SPC human resource infrastructure; recruit, retain, develop staff • Support achievement of Professional Development/Goal Setting and Engagement Plans by RSC/DSC/SPC staff • Ensure each team member has opportunities to develop leadership/QI/KT/Project management skills • Continuously develop stroke team best practice knowledge through annual participation in national stroke congress; and other relevant stroke conferences - deliver at least 3 posters/presentations annually • Make use of narrative practice to communicate patient-centred care, interprofessional team expertise • Share professional development, best practice and leadership information amongst stroke teams | Ongoing Ongoing as detailed in professional development plans | C. Martin
R L&C2 | Sustain a resilient Stroke Network that is flexible and responsive to a changing provincial context. | • Sustain strong communication links with CorHealth • Remain aware of the recommendations to the MOHLTC by CorHealth Ontario in relation to the Regional reviews, potential redeployment of stroke infrastructure, • Advise on plans for changes to sustain stroke network and apply learnings to cardiac and vascular care. • Revisit the workplan to accommodate changes | expected in Year 1 with ongoing adjustments in Yr 2 | C. Martin
R L&C3 | Develop, monitor and implement Regional Stroke Workplan based on RSSC priorities and program mandate | Develop, monitor and deliver Regional Stroke Workplan Implement, monitor and sustain system change; build capacity for interprofessional expertise and knowledge translation in Best Practice Stroke Care; build transitions and connections across the continuum of care; promote use of a standard CQI approach; Support Clinical Implementation of Bundled Funding in stroke care • Report on workplan progress at each RSSC meeting (using workplan progress report and briefing notes) • Engage and support stakeholders in reporting on local aspects of workplan including bundled funding for stroke care • Sustain infrastructure required to oversee workplan • Deliver on Education/Knowledge Translation plan embedded in workplan building capacity for best practice • Continuously review evaluation data and adjust workplan accordingly with stakeholders • Set new priorities and develop next two year plan with stakeholders in 2021 | Ongoing as detailed in workplan | C. Martin
R L&C4 | Engage stakeholders in workplan priorities through an effective communication strategy | Engage stakeholders in workplan priorities through a communication strategy: • Ensure website is current and communication strategy is linked with workplan priorities • Direct stakeholders to website resources through regular updates to news page and quarterly e-news • Invest in Adobe illustrator and learn to create infographics for communication of performance and project reports • Increase photography archive for use on SE website • look for opportunities to use narrative practice and create one to two more patient stories • continue to make use of videotapes and on-line learning modules • Develop a new logo with graphic design support [HOLD until regional review changes with CorHealth] • Maintain current contact lists - check annually • Internal team communication - monthly team meetings and workplan review | Ongoing E-news quarterly Invest in Adobe Illustrator in Year 1 | C. Martin
R L&C5 | Sustain governance infrastructure for effective program oversight and stakeholder engagement | Sustain governance infrastructure for effective program oversight and stakeholder engagement • Coordinate strategic focus of Regional Stroke Steering Committee (RSSC) • Coordinate Sustain RSSC Planning Subcommittee to guide meeting planning • Maintain membership of RSSC and subcommittees/workgroups per terms of reference (TOR) • Review and revise TOR for each committee/workgroup in 2019 • Sustain stroke survivor patient advisor membership and active engagement in RSSC and related committees • Provide orientation for every new member of RSSC • Evaluate RSSC meetings using survey monkey • Perform a full evaluation of steering committee in 2019 and respond accordingly • Sustain Subcommittees and develop Workgroups as required to deliver workplan • Provide support as needed to District Stroke Advisory Council (DSAC) | Ongoing RSSC meetings 5X /year Evaluate RSSC and Revise TOR in 2019 | C. Martin
R L&C6 | Build Communication and Accountability Links with SE LHIN | Build Stroke Program Communication and Accountability Links with SE LHIN/Regional Planning Body • Sustain relationship with SE LHIN/New Regional Planning Body and connect as needed with planning & performance teams • Continue to use LHIN/Regional Planning team meetings as mechanism for effective information flow and planning for collaborative system change • Sustain LHIN/Regional Planning membership on RSSC • Ensure alignment of Stroke Network workplan with LHIN/Regional Planning Infrastructure, CorHealth Ontario and MOHLTC Priorities e.g. Bundled Funding; EVT and QBP implementation; Rehabilitation Alliance activity; LHIN IHSP; Health Links; Sub-regions • Meet annually with LHIN/Regional Planning Infrastructure senior leadership team re SE LHIN Stroke Report Card, SE Dashboard, interpretation, progress and workplan • Sustain communication with LHIN/Regional Planning Infrastructure, Designated Stroke Centres and Stroke Prevention Clinics to meet stroke HSAA accountabilities; send annual letters after SE Stroke Report Card is publicly released, highlighting HSAA indicators | Ongoing Report Card meeting May/June each year HSAA letter July each year | C. Martin
R L&C7 | Monitor and evaluate stoke care in the SE against provincial and national standards | Quality Monitoring and Evaluation (As embedded in each section of the stroke workplan) • Disseminate annual Stroke Report Card and Ontario Stroke Evaluation Report; LHIN and Sub-LHIN analysis • Ensure all stakeholders are aware of Stroke Report Card and QBP indicator reports - provincial and facility- based • Continue to develop and make use of Regional Stroke Dashboard - report quarterly and use to plan and sustain local quality improvement initiatives • Assist with data interpretation and use of data in bundled funding models • Use data to inform workplan activities and best practice implementation priorities at regional and local levels • Support data quality in CIHI project #340, #640, #740 and CIHI NRS Rehab Intensity measures • Continue to collect SPC activity and wait times on a regional basis. • [Trial NACRS lite for SPC data collection - on hold until supported by CorHealth Ontario/MOHLTC] • Sustain collaboration with RPPEO for pre-hospital data and Stroke Report • Support and Sustain annual evaluation and monitoring of Enhanced Community Stroke Rehab Program, Stroke Support Group Evaluation and Community Aphasia Conversation Groups • Consider how South East Integrated Information Portal (SHIIP) and Connecting Ontario might assist the Stroke Network and its stakeholders in informing stroke care transitions; make use of SE Data Centre • Leverage findings of CCC/LTC Evaluation Report including potential to link with research initiatives in LTC (e.g. QUILT research initiative) | Ongoing as indicated in Workplan | C. Martin
R L&C8 | Manage fiscal and human resources within given parameters | Fiscal Planning & Human Resource Management • Monitor fiscal resources and variances associated with designated stroke funding at each centre • Deliver on HAPS accountabilities for mandated stroke services • Ensure designated stroke staff deliver on Performance Agreements/Professional Development Plans and Workplan accountabilities | Ongoing | C. Martin
R L&C9 | Link with/contribute to Regional, Provincial and National Networks & Organizations regarding workplan activity; link learning back to regional activity | Provincial and National Collaboration and Linkages • Support strategic plan and workplans of CorHealth Ontario • Participate in HQO Bundled Funding Communities of Practice • Participate in Provincial Priority Workgroups (Secondary Prevention in 2019/20) • Maintain membership in Stroke Evaluation and Quality Committee and subcommittees • Participate in other provincial committees and workgroups such as Stroke Leadership Council, CorHealth EVT Steering Committee and workgroups, CorHealth Bundled Funding Workgroup, Ontario Regional Education Group-OREG, Regional Director/DSC Advisory Council, Regional Rehabilitation Coordinators,CLTC Coordinators Workgroups, Best Practice Coordinators Workgroup • Transition from Chair role on Regional Director/DSC Advisory Council and support succession plan for new Chair • Consider supporting provincial collaboration in LTC (Think Research, QUILT) • Participate in the work of the Provincial Rehabilitative Care Alliance and other provincial bodies such as RNAO • Contribute to development of new provincial resources and to updates of Educational Resource and Guidelines • Sustain partnership with Heart and Stroke Canada and contribute to National Guidelines Updates as invited • Facilitate awareness of and dissemination of resources • Maintain close communication with all stroke regions with focus on shared learning | Ongoing | C. Martin and team
R L&C10 | Contribute to innovation in stroke care | Contribute to innovation in stroke care • Attend to opportunities for funding to address quality improvement opportunities ( e.g. business case development and spread of aphasia conversation group, Indigenous Blood Pressure Screening, I-Dynaform, e-visits, EVT, Coiling) • Engage and support stakeholders in responding to these funding opportunities/calls for proposals • Support partners in stroke project implementation, evaluation and dissemination of project findings • Sustain and spread project learning to promote knowledge translation and practice change • Maintain awareness of current funded research and Clinical Trials related to stroke best practice and apply findings to workplan activities as they become relevant ( e.g.EVT, Screening Tools, TIA triage algorithms, Stroke unit utilization, Rehabilitation Intensity, Community Based Rehabilitation/Early Supported Discharge; e-health etc) • Collaborate with Queen's School of Rehab in following up on rehabilitation provider research surveys | Ongoing | C. Martin