## Read Me
STROKE NETWORK OF SOUTHEASTERN ONTARIO
Stroke Network of SEO - Regional Workplan 2019-2021
PRIORITY #1 -PREVENTION: Expand/improve timely equitable regional access to prevention supports and services PRIORITY #2 - HYPERACUTE: Improve timely regional access to hyperacute stroke treatment PRIORITY #3 - ACUTE TO REHAB TO COMMUNITY: Create/develop patient and family-centred regional transition protocols for acute to rehab to community* care (*community includes retirement homes, LTC) #4 - EXPERTISE & CAPACITY: Sustain/Enhance regional stroke expertise and capacity to deliver best practice stroke care, supporting ongoing connections, recruitment and retention The workplan includes three types of actions: 1. Create 2. Improve 3. Sustain
The workplan supports the Canadian Best practice Recommendations for Stroke Care.
The workplan also aligns with Strategic Directions of CorHealth Ontario, the SE LHIN Integrated Health Service Plan (IHSP) and the MOHLTC Action Plan.
This alignment is indicated in a column highlighting the relationship of the stated objective to the IHSP and CorHealth plans noted below.
Within several worksheets there are regional and local aspects to the plan with geographic distributions as follows:
*Regional Plan for Southeastern Ontario
*Quinte District Stroke Plan for the Counties of Hastings & Prince Edward (HPE)
*Kingston, Frontenac, Lennox & Addington Counties (KFLA)
*Leeds & Grenville Counties (L&G)
*Lanark County
Please scroll through the different worksheet tabs to read each aspect of the care continuum
Please scroll within each worksheet to read regional and local plans for each aspect of the care continuum
The final 2 worksheets cover the Regional Education Workplan and Leadership & Coordination Requirements
ALIGNMENT with CorHealth Strategic Directions and Goals:
1.Drive Evidence-Informed Practice
Goal 1. Identify, develop and adapt practice standards, guidelines and programs to support integrated evidence-based care.
Goal 2. Optimize the use of standards, guidelines and programs (knowledge translation).
2.Inform Planning, Access and Resource Allocation
Goal 3. Support decision making for system design and resource allocation.
Goal 4. Advise on the effectiveness and appropriateness of services and technologies.
3. Measure and Report on Quality and Outcomes
Goal 5. Advance a measurement and reporting system across the dimensions of quality that supports improvement.
Goal 6. Support a regional and provincial performance management system.
ALIGNMENT with SE LHIN IHSP4 Programs and Initiatives (including alignment with Patients First Ontario Action Plan)- UPDATE with IHSP5 when ready
1. Support the Hospital Services Project- Health Care Tomorrow, sustainable acute care system
2. Ongoing implementation of the Addictions and Mental Health Redesign
3. Launch an Older Adult Strategy - strengthening the continuum of support care for older adults
4. Build a solid and sustainable primary care system that is well coordinated and linked to other services
5. Building on the success of Health Links, extend improvements through the entire primary and community care sectors
6. Make better use of technology for greater information flow between providers and across the system
7. Expand continuous patient engagement
8. Build comprehensive services through cooperation ( public health, municipalities, other ministries)
9. Enhance Indigenous and Francophone Health Services across our region
ALIGNMENT with MOHLTC Patients First Ontario Action Plan for Health Care - UPDATE
1. Improve access - provide faster access to the right care
2. Connect - Connect services and deliver better coordinated and integrated care in the community, closer to home.
3. Inform - Support people and patients - provide the education, information and transparency they need to make the right decisions about their health.
4. Protect: Protect the public health care system - make decisions based on value and quality to sustain the system

## Read Me Symbols
CHOOSE from LIST
improved; likely to achieve target
achieving target
worsening; target may still be achieved
improved; may achieve target
unchanged; may or may not achieve target
worsening; may not achieve target
improved; not likely to achieve target
unchanged; not achieving target
worsening; not likely to achieve target

## Progress Report
2019-21Regional Stroke Workplan PROGRESS Report - March 2020
Priority / Area |  | Objectives | Status | Progress Notes
RSSC Priority #1: To expand/improve timely equitable regional access to prevention supports and services | R P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs | achieving target | ▪ Primary Care/ (PC)/Stroke Prevention Clinic (SPC) CME event delivered successfully in February 2020. Evaluation feedback indicating that event highly satisfied learning needs. 57 providers attended event. Summary of the event under development for dissemination broadly via e-news to facilitate further linkage to resources. Learning from break-out discussion sessions will be included. Event helped to further link primary care with local SPCs especially in KFL&A which had highest proportion attending. ▪ Promoted use of Connecting Ontario ClinicalViewer at PC/SPC event and annual regional SPC meeting as this platform provides visual view of consult and clinic notes, dispensed medications, and diagnostics. ▪ Worked with provincial group to develop an Infographic for Primary Care Providers about SPC role and essential stroke prevention best practices. SPCs provided feedback on the Infographic; shared at CME in Feb; final version to be posted on website;. ▪ Referral rates from ED to SPCs improved. ▪ Volumes in all 4 Clinics increased in Q1 -Q3 (KHSC=935; BrGH=146; PSFDH=302; QHC=459) compared to Q1-Q3 last fiscal. ▪ Referral rate at Brockville was higher upon removal of acute hospital transfers (e.g., on Acute Stroke Protocol). Examination of regional dashboard definition underway.
|  | b) Improve linkages to self-management and community resources | achieving target | ▪ At all Stroke/TIA events & meetings, continued to promote awareness of South East self-management program, smoking cessation and physical activity resource maps, Heart & Stroke public education materials including FAST, the www.SEhealthline.ca, community supports (support groups, aphasia programs, stroke-specific exercise programs, return to work & driving resources, support agencies), & Community Stroke Rehab Program . SPCs sent "Your Patient Journey Map" for use in Patient Information Packages.
| R P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations | improved; may achieve target | ▪ Provincial Prevention Group has not updated the SPC triage algorithm. The south east SPCs continue to follow the OSN algorithm. The updated KHSC SPC Care Guidelines and updated best practices were shared with other SPCs. Worked with PSFDH in drafting their TIA Collaborative Care Plan for patients discharged from ED. ▪ Worked with provincial group to develop SPC referral criteria. SPCs provided feedback on the referral form template. ▪ Developed guide with KHSC neurologists and DI team for early outpatient MRI to avoid admission for TIA patients. ▪ Admission of TIA patients discussed with BrGH hospitalists and PSFDH ED physicians - reinforced LLG Stroke Unit Care algorithm. ▪ Continued to monitor wait times of 4 SPCs by triage category, reporting at RSSC meetings & at June annual regional SPC meeting. ▪ Wait times improved but 3/4 Clinics not reaching target of 3 days for urgent patients (KHSC: 3.5 days; BrGH: 4.9 days; PSFDH: 1.1. days; QHC 4.7 days).
|  | b) Improve clinic efficiencies | improved; likely to achieve target | ▪ See KFLA P2. Supported successful implementation of OTN E-Visits at KHSC for follow-up patients; spread to all SPC neurologists and to PCH for Stroke Rehab inpatient follow up appts. KHSC Pilot Project results and OTN e-visit platform shared with 3 SPCs by Dr Appireddy in May 2019 at Provincial Stroke Rounds and in June 2019 at annual regional SPC meeting; recent interest from QHC. ▪ SPCs shared different strategies to improve timely cardiac testing at June 2019 annual regional SPC meeting. If cardiac testing is not done as an inpatient, SPCs arrange outpatient testing and related follow up. ▪ PFO referral process guide developed for use by SPCs
|  | c) Build expertise and partnerships | improved; likely to achieve target | ▪ SPCs contributed to planning and delivery of PC/SPC event in February 2020 and Stroke Symposium in Nov 2019. ▪ SPCs continued to connect with local EDs re stroke prevention practices including ordering of blood work and diagnostic imaging. ▪ Anticoagulation for atrial fibrillation was focus at June SPC meeting, November Stroke Symposium, PC/SPC event in Feb 2020. Learnings re barriers/opportunities from 3 events were summarized with plans for broad distribution via spring e-news. ▪ Promoted awareness of women and stroke prevention at the November Stroke Symposium and PC/SPC event in Feb 2020, highlighting that women may not be treated to target and receive lower dose of anticoagulation. Have yet to incorporate into process changes. ▪ Supported training in contrast dye administration for vascular imaging with 2 CT techs at BrGH. ▪ Annual SPC meeting reviewed screening tools for Depression, Obstructive Sleep Apnea, & Cognition, including DOC tool ▪ Connected SPCs to Aphasia Institute and aphasia friendly materials. KHSC shared their aphasia friendly materials at the annual SPC meeting.
| R P3 | Support the Indigenous inter-professional Primary Care Team in the regional implementation of an Indigenous vascular risk screening and management program: a) Update guidelines | improved; likely to achieve target | ▪ Deseronto Indigenous Blood Pressure (BP) program is on hold at the clinic related to staff turnover. Continuing at community events (e.g., Diners Club). No new volunteers trained this fiscal. Meetings held with new manager of the Indigenous Interprofessional Primary Care Team (IIPCT) to review background & processes of the Indigenous BP program. IIPCT is interested in using the model and spreading throughout the region in other Indigenous communities. ▪ Reviewed updated guidelines from Cardiovascular Health Awareness Program (CHAP) in March 2020 for adaptation with the Indigenous BP protocol. • Participated in provincial annual CHAP meeting to review the Indigenous BP program in Deseronto.
|  | b) Support linkages to cultural safety | achieving target | ▪ Best Practice Coordinator completed the Provincial Health Services Authority (BC): San’yas on-line Indigenous cultural safety training program for Ontario. Learnings shared with team & used to assist with development of case study at Feb PC/SPC event. ▪ See KFLA P3 re supporting cultural training sessions at Kingston CHC. ▪ Promoted Cultural Safety Course at Stroke/TIA related events and meetings. Incorporated link to on-line Cancer Care Ontario Indigenous Cultural Safety Course in materials related to the PC/SPC event; materials uploaded on Stroke Network website.
|  | c) Support education and training | improved; likely to achieve target | • Supported/organized an education training workshop about the Deseronto Indigenous BP program with the IIPCT for March 2020. Content by KCHC Indigenous Community Development Worker/Elder & an Indigenous NP who previously developed the program to include key learnings and advice re spread to other Indigenous communities. (Update: to be rescheduled due to COVID)
| HPE P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs | unchanged; not achieving target | ED referral rate steady at 60% for FY1920 Q2; consistent year to year production below target On advice from experience in Brockville, will review ED referral data to consider whether site to site transfers should be removed from denominator to accurately assess referral rates. Reviewing options to change referral from paper to EMR to improve access Looking at FY2020/21 meeting with ED admin & physicians to review practices for ED referrals to make process easier Looking at FY2020/21 meeting with QHC coders to improve data capture Improving consistency for physicians & nursing hopeful to provide improvement in 2020 & 2021 Unable to attend Feb 2020 Primary Care prevention event
|  | b) Improve linkages to self-management and community resources | achieving target | Supporting Living with Stroke education series in community SPC leading smoking cessation activities for QHCs IP units Stroke journey map & other education materials being incorporated into SPC in 2020
| HPE P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations | improved; likely to achieve target | Following OSN triage algorithm Increased number of SPC RNs, clerks & physicians working in or with SPC
|  | b) Improve clinic efficiencies | unchanged; may or may not achieve target | Clinic wait times improving in F1920 Q1 & 2 for L1/L2 referrals As of Oct 2019 - 11% above 1819 pace for # clinics Up to 5 IM MDs working in the Clinic as of Feb 2020 Primary SPC RN off work for 3 months Dec 2019 to Feb 2020 creating challenges with SPC workflow, data collection & efficiency
|  | c) Build expertise and partnerships | improved; likely to achieve target | Increasing SPC RN numbers (1 to 3) and expertise ISU nursing staff now working in SPC for broader expertise on ISU and increased flexibility in SPC April 2020 lunch and learn meeting planned for QHC SPC and SNSEO regional team Increasing IM resident training in F2019/20 and 2020/21
| KFLA P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs | achieving target | • Continue to coordinate Regional Stroke Prevention Clinic Nurses Group meetings. • Continue to monitor referral rates from ED to the Stroke Prevention Clinic on a monthly basis. • Unable to meet with the L&ACGH ED Manager. • Increased use of ConnectingOntario ClinicalViewer to obtain timely information enhancing triage decision making & clinical efficiency.
|  | b) Improve linkages to self-management and community resources | achieving target | • Continue to refer patients to KFLA Smoking Cessation programmes - information is available in cessation folder. • Smoker's Helpline is no longer available; MOHLTC revising the program. Physical activity maps are available. • Clinic TIA package is updated as required. Community resource information is available in package. • Patient Journey Map laminated for use in the Clinic.
| KFLA P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations | achieving target | SPC Collaborative Care Plan, now identified as TIA SPC Follow Up Care Guidelines, was updated & implemented February 2020 reflecting Canadian Stroke Best Practices. Continue to report wait times by current triage categories and per referral source. Attempting to maintain target for priority # 2 patients to be seen within 48 - 72 hours. Continue to hold M-F half day clinics - keeping 1 spot available for urgent patients.
|  | b) Improve clinic efficiencies | achieving target | Medical Directive update due 2020. Continued triage coordination with physicians. TIA ED Collaborative Care Plan updated to Care Guideline format EDIS Dec 2019. ED/UCC High Risk TIA Order sets approved July 2019. Dr. Drover/ ERP discussions were to occur to arrange EDIS placement. Echo - status quo. Same day event monitor application/clinic appointment. OTN E-Visits implemented for follow-up patients with leadership from Dr Ramana Appireddy. Expanded use to all SPC neurologists and to PCH Stroke Rehab inpatients. Evaluation indicated positive feedback from patients with efficiencies for the patients and the health system. Dr Appireddy presented at May 2019 Provincial Stroke Round, KHSC Department of Medicine, Oct 2019 Canadian Stroke Congress, Nov 2019 Stroke Symposium & Feb 2020 Primary Care/SPC event. Results published in 2019 Journal of Medical Internet Research: "Home Virtual Visits for Outpatient Follow-Up Stroke Care: Cross Sectional Study." Recent OHA newsletter highlighted the findings. Dr Appireddy received 2 research grants in 2019-20 to expand/spread the learning from the e-visit project.
|  | c) Build expertise and partnerships | achieving target | Attended Primary Care/SPC Collaborative Feb. 5/20. Continue to perform medication reconciliation for all medications including anticoagulants. Continue Stroke Distinction Interprofessional Committee participation. Exploring cognitive & depression screening methods. MOCA is being administered to appropriate patients.
| KFLA P3 | Support the Indigenous inter-professional Primary Care Team in the regional implementation of an Indigenous vascular risk screening and management program: a) Update guidelines | achieving target | See Regional Update for information on CHAP Guidelines and work with the Indigenous Interprofessional Primary Care Team. Updated Guidelines shared with Kingston CHC.
|  | b) Support linkages to cultural safety | achieving target | • Maintain established referral process from Moose Factory area. • KHSC Stroke Neurologist, Case Manager/Stroke Specialist completed the Provincial Health Services Authority (BC): San’yas on-line Indigenous cultural safety training program for Ontario. • Stroke Network supported Kingston CHC-Napanee site in the delivery of 2 cultural safety training sessions
|  | c) Support education and training | improved; likely to achieve target | • New Indigenous NP at KCHC-Napanee Site received orientation about Deseronto Indigenous BP program. • Hosting education session about the Deseronto Indigenous BP program with the Indigenous Interprofessional Primary Care Team (IIPCT) in March 2020. Content to be delivered by KCHC Indigenous Community Development Worker/Elder & an Indigenous NP who previously developed the program. • Declining number of community volunteers trained re Indigenous BP program; Screening sessions continued at community events (e.g., Pow Wow's).
| LG P1 | Enhance timely access to the Stroke Prevention Clinic (SPC) demonstrated by: a) 90% referral rate from the ED | improved; may achieve target | Currently our referral rate is improving to SPC, however we are including patients that are being sent to KHSC on stroke protocol. With the increased time window that patients can be sent, this is negatively impacting our stats. If we remove the patients transferred from BGH ED to KGH ED, we are close to target.
|  | b) All referrals reviewed and triaged within 48 hours of receiving | improved; not likely to achieve target | Currently our SPC is operational on Monday, Wednesday, and Friday. When referrals are sent Friday evening they are not reviewed until Monday am (60hour window, and with stat holidays, there is an 84 hour timeframe that consults are not reviewed), otherwise this target is being met.
| LG P2 | Support and implement recommendations made for best practices relating to SPC triage | improved; may achieve target | Referrals to SPC are following Ontario Stroke Network Ambulatory Care Triage Algorithm for Patients with Suspected or Confirmed Transient Ischemic Attack (TIA) or Stroke.
| L P1 | Improve linkages amongst ED, primary and secondary prevention providers | achieving target | VPC- RN, Crystal went down to BrGH, met with team and provided referral packages to ensure referrals are made
| L P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice | achieving target | a. Triage- We are currently working on a method to capture all stroke patients for regular case review. b. Efficiency- working on TIA pathway. Dr Del Grande discussing CTAs with DI; Doppler use for TIA workup is being monitored to ensure appropriate timing. Both ED Chiefs have attended the ACT-FAST education session provided by the stroke network. c. Rehab/VPC in constant contact regarding discharged patients and education required per patient.
RSSC Priority #2: To improve timely regional access to hyperacute stroke treatment | R E1 | Continuously improve the Endovascular Treatment (EVT) Service within KHSC a) monitor service and ensure quality data | achieving target | See KFLA E1. ▪ EVT volumes increased this fiscal to 55 Anterior Cases YTD + 2 posterior case, doubling the volumes from 19-20 ▪ Continued to lead quarterly EVT workgroup meetings, sharing process and outcome data and supporting follow up actions. ▪ Q1- Q3 Outcomes indicate improvements: 50% of cases leaving hospital with mRS of 0-2; mortality rate below provincial rate at 15.9%. Good region wide distribution now extended to Campbellford. Process times all within provincial targets as per review of CorHealth Reports. ▪ Making use of discharge CIHI 440 EVT data. Data collection processes refined. ▪ Worked with Dr Appireddy to update IVR data collection sheet & Neurology Admission note. ▪ Plan in place with Decision Support at KHSC to develop graphical display to better visualize trends. ▪ Preparing for participating in Optimize Trial-registry of EVT data. ▪ Participated in provincial EVT Implementation work group and Hyperacute Steering Committee
|  | b) use data to direct quality improvements | achieving target | ▪ RAPID implemented at KHSC in January and QHC in February (see R E2 below) ▪ Extended time window for EVT processes developed (see R E3 below) ▪ To augment EMS pre-notification, developed process guide with paramedic services & KHSC ED manager for patient information to be called ahead to KHSC allowing Neurologists to review chart ahead of arrival to help with rapid decision-making. ▪ Planning is underway for annual MOCK to take place at KHSC in June-July to sustain process. ▪ Working on EVT referral process with CE Stroke Network for Campbellford hospital ED patients presenting between 6-24hours. ▪ Debriefs with EVT group were not needed last fiscal. Continue to make connections with QHC & KHSC re EVT & use of RAPID. Issues were followed up promptly and continue to be reviewed.
| R E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging | achieving target | RAPID implemented successfully at KHSC and QHC. Neurologists note RAPID helps with timely decision-making for appropriate patient selection. KHSC neurointerventional radiologist provided support for QHC radiologists during implementation. QHC RAPID results are reported through OntarioConnect ClinicalViewer assisting clinical teams to review mutual patient information.
|  | b) Implement triage tools within the EDs for the expanded time window; consider findings from pre-hospital screening pilots in other regions | achieving target | ▪ Use of Large Vessel Occlusion Screening Tool-ACT-FAST & related processes implemented in each ED region wide. Process continues to be monitored. ▪ 6 cases received EVT in expanded time window this fiscal; 3/6 were discharged with MRS 0-2. ▪ Qualitative feedback received from local EDs has been positive with providers indicating the tool is simple to use & has expedited activation of Acute Stroke Protocol. Any concerns related to process were communicated to regional team and followed up promptly with reinforcement of Acute Stroke Protocol process. ▪ In-hospital stroke protocols across region modified to include the extended time window; education continuing. ▪ Presented the ACT-FAST work at national Stroke Congress in October & November Regional Stroke Symposium. Refresher education offered and provided at KHSC at Knowledge Café & at BrGH and QHC Skills Fairs. ▪ Shared materials re ACT-FAST implementation and education with Stroke Networks across the province.
| R E3 | Create/develop telestroke readiness and an implementation plan with Brockville: a) Support the building of imaging capacity | achieving target | ▪ Participated in meeting August 2019 with Provincial Telestroke Leads & Brockville GH VP to discuss Readiness Application. The main initial barrier discussed was not having 24/7 CT Angiography (CTA) in place. Information regarding volumes and what it would take to provide 24/7 CTA was forwarded to VP & manager of imaging. BrGH received notice in January 2020 that their proposal for 24/7 CT Angiography (CTA) on call hours was approved. ▪ Supported education of 2 techs with CAMRT courses and plans in place to support techs in readiness for expanded coverage
|  | b) Engage stakeholders in readiness planning | improved; may achieve target | ▪ Engaged senior leaders in readiness assessment led by BrGH VP. Readiness plan updated in August 2019. DI engaged and worked towards overcoming imaging barriers. Met with BrGH VP monthly re stroke care including telestroke readiness planning. ▪ With BrGH VPs and COS, set up and facilitated Feb 2020 meeting with physician leads of ED, critical care, DI and Stroke Unit to discuss medical concerns. Concerns from physician leads were documented; main points summarized and shared back with physician leads & senior leaders. Dr Jin participated in meeting with ED physician leads in March to discuss concerns. Plans underway to re-group with senior leaders to discuss next steps.
|  | c) Develop and initiate an implementation plan | unchanged; may or may not achieve target | Main high-level elements for a telestroke implementation project plan have been drafted. To be successful, the plan will need to include an increase in BrGH medical support in the ED, efficient handover to Critical Care and internal medicine support to hospitalists.
| R E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time of <30 mins at KHSC and <45 mins at QHC | achieving target | DTN times continue to be monitored. ▪ KHSC DTN times were Q1=24 min, Q2=27 min and Q3=31 min. See Regional Dashboard. ▪ Participated in QHC Kaizen activities held in May & July aimed to decrease DTN times. QHC DTN decreased to 46 min this fiscal from 60 min last fiscal; Q4 DTN is approaching target; lowest recorded DTN is 35 min- a significant achievement
|  | b) Door-In-Door-Out DIDO transfer time 45 mins | improved; may achieve target | Participated in Kaizen events which also targeted process improvements regarding DIDO for EVT transfer to KGH. Last reported 54 minutes as lowest recorded DIDO time.
| R E5 | Support/Advise KHSC - KGH Interventional Neuro-Radiology (INR) in the planning of a Regional Aneurysm Coiling Service | achieving target | See KFLA E5. Regional Team worked with INR to lead the development of a business case for approval of KHSC-KGH coiling service. KHSC applied for coiling designation with Provincial Neurosurgical Advisory Committee of Critical Care Services Ontario. In March 2020, KHSC received notice that it would become a designated coiling centre with associated funding letters.
| HPE E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging | achieving target | RAPID imaging installed at QHC in late 2019 and "live" in early 2020; regional feedback notes good imaging and a successful implementation
|  | b) Implement triage tools within the EDs for the expanded time window | achieving target | Physicians and nurses educated on ACT-FAST tool use in SE region; regional and local (QHC) resources involved in initial and ongoing education and feedback.
| HPE E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time <45 mins at QHC | improved; may achieve target | QHC held a FY 1920 QI event and ongoing imitative for improving door to needle times in Quinte. Improvements have been seen in nursing and physician role clarity; IP Code Stroke processes and unit to unit and Paramedic Services communication. Timing of calls to telestroke consults remains an outstanding item to improve. Recent changes of adding a 2nd day shift ICU physician have seen 50% of door to needle times below 35 minutes over the last month. Data improving: % of cases below 30 minutes 6% (1819) to 15% (1920 YTD) % of cases below 45 minutes 29% (1819) to 47% (1920 YTD) Median D2N 59.5 minutes (1819) to 47 (1920 YTD) Median D2N for 1920 Q4 YTD = 39.5 minutes
|  | b) Door-In-Door-Out DIDO transfer time 45 mins | improved; not likely to achieve target | see above
| KFLA E1 | Continuously improve the Endovascular Treatment (EVT) Service within KHSC a) monitor service and ensure quality data | achieving target | EVT Workgroup Continues to review process and outcome data quarterly. 44 cases were treated to end of Q3 with expected number of 55 to 60 cases by year-end. Mortality rate to Q3 was 15.9% which continues to be below provincial average of 18%. The percent with Modified Rankin Scores of 0 to 2 (minimal to no disability) was 50%, above the HERMES trial rate of 43.5%. Process times continue to be well under provincial targets.
|  | b) use data to direct quality improvements | achieving target | • Main 2 process improvements this year have been: 1. Use of RAPID Advanced Perfusion imaging to improve patient selection at KHSC; pocket card for interpretation. 2. Use of ACT-FAST in the ED to improve identification of eligible candidates for EVT - as noted below • Participating in hyperacute stroke clinical trials involving use of TNK-thrombolysis: 1)Tempo-2 underway since Sept 2019 involving mild stroke ineligible for tPA; 2)planning underway for AcT trial looking at tPA vs TNK. • Updated Acute Stroke Protocol Packages; streamlined physician Stroke Assessment Form per feedback.
| KFLA E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging | achieving target | RAPID Advanced Perfusion imaging has been in use in 2019 at KHSC on all stroke protocols and has improved the ability of the team to select cases for EVT, including those presenting in the delayed time window of 6 to 24 hours. QHC has also implemented RAPID as part of their hyperacute imaging protocol making it easier for telestroke and KHSC team to select cases for transfer.
|  | b) Implement triage tools within the EDs for the expanded time window | achieving target | ACT-FAST Large Vessel Occlusion Screening tool was implemented at KHSC at the end of FY 2018-9 and reinforced with continued teaching this fiscal. Poster on this work delivered at Canadian Congress Oct 2019, Stroke Symposium, Kingston Nursing Conference. The same screening tool was implemented across all EDs in the region by Q2. To date this fiscal, 6 cases were treated with EVT in the extended 6 to 24 hour time window with similar outcomes to those treated under 6 hours.
| KFLA E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time of <30 mins at KHSC | achieving target | DTN time at KHSC has been monitored every quarter and reported on the regional dashboard with Q1 to Q3 times of 24, 27 and 31 respectively. The team is currently deciding if a change could be made in the process for blood work to save further on ED door to CT time.
| KFLA E5 | Support/Advise KHSC - KGH Interventional Neuro-Radiology (INR) in the planning of a Regional Aneurysm Coiling Service | achieving target | The KHSC Coiling Workgroup approved moving forward with a request for designation in October 2019. The Critical Care Services Ontario, Provincial Neurosurgical Advisory Committee and subcommittees reviewed KHSC's requests/presentations and approved a formal request to the MOHLTC for KHSC Coiling Designation. In March 2020, KHSC received formal notice that it would be a designated coiling centre with associated funding letters. Planning is now underway to revisit the KHSC business case to determine funding allocations.
| LG E2 | Support the use of the ACT-FAST triage protocol as appropriate at the completion of the KHSC pilot. | achieving target | ACT-FAST protocol is in place and has been used to successfully identify and transfer relevant patients to KHSC for hyperacute EVT assessment/Rx.
| LG E3 | Create business case for a Telestroke Program at BGH a) Support the building of imaging capacity | improved; may achieve target | Plans in place to increase imaging capacity and increased access to CT and CTA 24/7 with added evening and on-call night shifts. Will be implemented over the next several months.
|  | b) Engage stakeholders in readiness planning | achieving target | Held first meeting with stakeholders in February. Compiled a list of questions/concerns and have a commitment to continue meeting to discuss. Dr Jin meeting with ED physicians in March.
|  | c) Develop and initiate an implementation plan | unchanged; may or may not achieve target | A plan will be developed as we build more stakeholder buy-in and commitment from the teams.
| L E2 | Implement triage tools within the EDs for the expanded time window at PSFDH | achieving target | ACT-FAST triage screening tool is being implemented in both ERs.
RSSC Priority #3: To create/develop patient and family-centred regional transition protocols for acute to inpatient rehab to community care | R A-R-C1 | Participate in provincial CorHealth Ontario Bundled Funding Stroke Workgroup and link to provincial and local Communities of Practice a) Build provincial links | achieving target | Regional Director and Rehab Coordinator participate in weekly CorHealth Provincial Advisory group. SNSEO representation on all CorHealth bundled indicator and PROM workgroups. Rehab Coordinator, S. Huffman participated in sub-group completing in-home stroke rehabilitation pricing model to be submitted to MOH in March 2020. S. Huffman invited to speak with CorHealth at GTA Rehab Best Practices Day on Stroke Bundled Care update. S. Huffman is a participant on the RCA Bundled Funding Advisory Group which provides linkages to existing bundled partner experience. This will help to inform future planning for stroke.
|  | b) Establish regional links | achieving target | ▪ Updates provided regularly to RSSC, potential bundle holders and bundle partner leaders through existing forums. Local teams linking across the region on initiatives related to transitions and in some cases with teams outside the SE region. ▪ Regular meetings held between District and Regional stroke teams to remain updated on mutual Bundled Care preparation and projects. ▪ Kingston area Bundled Stroke Care Clinical Task Group formed in 2019 to focus on improving access to best practice care through efficient patient flow. Regional team supports this task group, the associated workplan priorities and the monitoring of joint metrics. QI activities are recorded in local reports under KT2 below. Learning from this Task Group is shared at Regional Meetings.
| R A-R-C2 | Adapt the provincial Bundled Funding Pathways and related expectations for our region to enable implementation of common components and parameters of regional transition protocols and services a) Develop a SE Stroke Pathway with common components and parameters in alignment with bundled funding/QBP standards. | achieving target | Regional Acute - Community-Rehabilitation Stroke Services and Transitions pathway was created and used as basis for a self assessment process and identification of key opportunities to focus and improve on transitions across the continuum. Pathway created aligns with best practices and anticipated bundled care expectations as of fall 2019. Local process considerations were incorporated into the pathway to help achieve best practice.
|  | b) Translate into local pathways for west, central, east | unchanged; may or may not achieve target | Local teams across the continuum used the regional pathway to conduct a self assessment and select local quality improvement activities to focus on for 2020-21. These QI activities will be added to year 2 of the regional workplan with local goals for next report.
| R A-R-C3 | Deliver Local/Regional Forum(s) and Education to facilitate clinical implementation of bundled funding. This will: a) Inform providers of current state, expectations and gaps | achieving target | Regional forum was conducted in September 2019 as planned with follow up activities underway. Report on project to date completed and shared in January 2020. This activity informed priorities for action noted below.
|  | b) Identify priorities for change/action | improved; likely to achieve target | Planning and support for ongoing local and regional follow-up activities to include: a) delivery of a Navigation workshop in 2020; b) compilation of a Transition Toolkit to support teams and c) support to local teams in developing and implementing action plans associated with their self-assessment and learning
|  | c) Deliver a Regional Forum to support knowledge translation in bundled care and local action plans | achieving target | Self-assessment follow up check -ins conducted with each local team or site between February and March 2020. This provided an opportunity for team to reflect on their self assessment and on any learnings to date. Teams shared key opportunities that they were working on putting in place to improve consistency in practice. These opportunities will be a focus over the coming months.
| R A-R-C4 | Pilot change opportunities to support local pathway adoption (i.e., key changes in delivery models or transitions in each local area) | improved; likely to achieve target | Regional team is available to support local teams in a variety of ways including but not limited to acting as a project lead or resource to help pull teams together across sites (ie KHSC - PCH Fast Track project),and linking across sites for learning from others (ie BrGH linking to QHC for Integrated Stroke Unit planning; PCH linking to BrGH to learn key elements for implementing peer visiting with a rehab unit setting.)
RSSC Priority #4: EXPERTISE & CAPACITY: Sustain/Enhance regional stroke expertise and capacity to deliver best practice stroke care, supporting ongoing connections, recruitment and retention | R KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | improved; likely to achieve target | See more details in Local Plans. a. Supported recruitment of new KHSC Acute Stroke Team members. Supported retention strategies with KHSC Stroke Team (e.g., educational opportunities, review of scheduling). Assisted in development of joint SEAMO proposal for added stroke care hospitalists at KHSC and PCH. b. Supported champions and staff in relevant learning needs per Education Plan (e.g., ISU site visits for BrGH planning, QHC ISU refresh, regional Acute Stroke Collaborative, November Stroke Symposium, physician stroke school for BrGH, CTA dye training with BrGH DI, training in Supportive Conversation, University of Alberta Certificate in Stroke Rehab, Neuro Physio 101) and continuous education through provincial stroke rounds, and shared work/field experience opportunities. Supported mentorship of new Stroke Team members. Provided orientation of Stroke Network related activities/work with new staff and managers across the region. c. Collaborated with partners in learning (e.g. ABI, LTC Learning Collaboratives) d. Supported on-line learning strategies-IPAD technology re communication at KHSC. Reviewed dysphagia screening/management on-line learning for updates.
| R KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | improved; likely to achieve target | See more details in Local Plans. See also, KT5 a. Continued coordination to sustain Stroke Distinction program at KHSC including submission of data to portal every 6 months. quarterly Committee meetings and follow-up on actions. Met with new Accreditation Canada Coordinator in December to discuss updated Standards & use of new optional indicator-median time to IP rehab to align with current work related to ARC & bundled care. Continued to offer advice to Accreditation Canada & provincial Stroke Network counterparts regarding Stroke Distinction process and benefits. b. Discussed Stroke Distinction Program with QHC District Stroke Coordinator and provided updated Standards documents for Acute + Rehab. c. Supported stroke teams to identify best practice initiatives: Examples include: -KHSC: Updated Action priorities using priority setting exercise. Worked with KHSC team to document and strategize main priority of improving Stroke Unit Utilization and associated actions including project with PCH on FAST TRACK admission process (see A-R-C), coordinated oral health initiative meetings with workgroup & actions, promptly addressed issues related to dysphagia screening and order set updates, supported SLP updating of aphasia materials and Case Manager/Stroke Specialist updating of Stroke Information Packages; - QHC: Supported ISU refresher, updating of Stroke Information Packages, see A-R-C; -BrGH: Coordinated LLG Evaluation Meeting with actions; supporting planning for ISU, see A-R-C.
| R KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | improved; likely to achieve target | Discussions have occurred with SE LHIN Home & Community Care (HCC) with respect to the potential integration of Rehab Assistants (RA) into the Community Stroke Rehab Program. The role of RA in other community-based stroke rehab programs has been explored and findings have been shared with HCC. Further discussions with HCC and community rehab providers is anticipated.
| R KT4 | Ensure access to Aphasia Conversation Groups across the region | achieving target | Aphasia Supportive Conversation Groups (ASCG) are now in place in Belleville, Brockville and Kingston. Recruitment for Brockville groups includes the Perth/Smiths Falls area. Exploration will continue re the potential to offer an ASCG in Perth/Smiths Falls. Regional meetings of all ASCG providers are now in place.
| R KT5 | Community & LTC - Enable stroke survivors & caregivers to live in the community supported by programs & services that optimize quality of life in these domains: a. Person-Centred Skilled Stroke Care & Rehabilitation | improved; may achieve target | ▪ Work continues to integrate patient experience and outcome measures into the annual Community Stroke Rehab Program (CSRP) evaluation process. A draft Patient Experience Tool has been developed. An initial meeting was held with community providers to discuss potential outcome tools. Work continues on both of these initiatives. ▪ Findings of the provincial CCC/LTC Report have been shared at meetings (e.g. HCC LTC Meeting) and during one-to-one introductory meetings with new LTC contacts. ▪ Stroke Information Packages are now in place within southeast hospitals and respective teams have identified the best processes within their facilities to ensure that the packages are provided to all patients. Additionally, information on the packages has been shared with community providers (e.g. Rapid Resource Nurses and community rehab providers) ▪ Two Learning Collaboratives were held in each area during fiscal 19/20 including a session on ABI and Stroke presented in partnership with the ABI System Navigator. This session was also offered in Bancroft. ▪ Shared Work Day has been used to support training of exercise providers in Brockville and Perth and to support SW expertise in the creation of an education booklet for young children of stroke survivors developed by the Belleville Stroke Support Group.
|  | b. Community Co-Navigation | achieving target | ▪ In response to the success of the Kingston Community Expo, decision has been made to offer similar sessions in both Brockville and Belleville in coming years. ▪ The Patient Journey Map has been finalized and focus has been on raising awareness of this new patient education tool. The Map has been highlighted at the Stroke Symposium, ARC Transitions Event, local and regional meetings and is now included in the Stroke Information Package. As well, the Map has been offered in both wall poster format and laminated handout to stroke care providers. ▪ The role of navigation and navigators has been explored by the CRLT and a decision has been made to offer a Navigation Workshop in fiscal 20/21. It was recognized that, rather than a stand alone role, navigation is assumed by various health care providers and, as such, this workshop will support their understanding of what navigation is and how they can support this stroke care process in their respective roles. ▪ The Community Reintegration Questionnaires underwent further iterations and, following a review of the findings of a small pilot, the decision was made to leverage the questionnaires as self-assessment tools that can be used by patients, caregivers and health care providers to evaluate client needs and progress. The questionnaires now titled Your Stroke Journey Check-In) are being shared. ▪ A draft Transitions Checklist has been created to support linkages to community supports and services prior to discharge from the CSRP. The checklist is currently being evaluated by the community rehab providers. ▪ Consent processes are now in place for Belleville, Brockville and Kingston to facilitate linkages between Stroke Support Facilitators and stroke survivors following their discharge from hospital.
|  | c. Individual Well-Being & Meaningful Engagement | achieving target | ▪ Several new support groups have been initiated including an introductory group in Belleville, a young stroke survivors group in Kingston and groups in Picton, Napanee, Trenton. ▪ A Stroke Specific Exercise Program has been re-initiated in Brockville, one has been started in Napanee and all others have been sustained. ▪ Peer visiting has been sustained (and expanded) in Brockville and active planning is now underway to initiate in Kingston, Belleville and Perth. ▪ Initial contact has been established with Indigenous communities to explore stroke survivor & caregiver support group concept starting with Quinte. Process was on hiatus due to absence of key player but is to be refreshed in the spring. ▪ Sustaining of various processes including regional Stroke Support Group Facilitator meetings, annual stroke support group evaluation reports and Living with Stroke Programs.
|  | d. Access to Supports & Services | achieving target | Promoting the value of social work referrals has continued to be a focus in all relevant education sessions and regional/local meetings. Information has been provided at all educational events to link stroke care providers to relevant community services.
|  | e. Supported Mobility in the Community | achieving target | Return to Driving resource aligned with southeast supports and services has been completed and is posted on the SNSEO website. This tool has been promoted through SNSEO e-news, regional meetings and workshops and is included on the regional resource listing.
| HPE KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | achieving target | Supported staff education for ISU Sent people for Regional Stroke Symposium - presented on QHC ISU and Code Stroke QI Therapy leading rehab rounds to help with time to IPR bed Therapy leading process for AFIM documentation
| HPE KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | achieving target | QHCs Code Stroke QI project has reduced door to needle times Ongoing support of QHCs ISU with a formal FY 20/21 project for bundled care & Stroke Distinction - discussions underway regarding assessment of stroke distinction readiness Expansion of QHCs SPC with more physicians and nurses Implementation of RAPID software in QHC DI
| KFLA KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | achieving target | Continuing to focus on IP Rehab and Integrated Stroke Unit processes to achieve the best outcomes including use of Therapy Assistants for direct stroke time and direct time with non strokes. FY 1920 saw a trial of a QHC CDA working in the OP Rehab Day Hospital to free up SLP time on the ISU.
| KFLA-KHSC KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | improved; likely to achieve target | a. Contribute to human resource recruitment and retention within stroke care • Recruited & retained OT (0.5 FTE), PT services (0.5 FTE), RD (0.2 FTE) & SLP (0.5 FTE) and Case Manager/Stroke Specialist (CMSS) (0.6 FTE) (See KT3 re OTA trial). • Schedule set for OT & PT coverage of Fridays & Saturdays. OT coverage not consistent with Fri/Sat coverage; PT coverage going well. CMSS schedule revised for coverage later in the day based on trial. • Business case approved by SEAMO for hospitalist - awaiting news on MOHLTC Funding by summer 2020. • 3 Stroke Neurologists continue to be in place. b. Support champions and staff in relevant learning needs & c. Collaborate with Partners in Learning • New stroke team members received stroke education education; ASU team provided mentorship. • Stroke team participated in Acute Stroke Collaborative in June 2019, national Stroke Congress in October 2019, Stroke Symposium in Nov 2019 and Stroke Team attended monthly provincial stroke rounds. • Dysphagia screening/management orientation continuing with Critical Care, ED & new K7 nursing staff. Mentoring of staff in dysphagia best practices ongoing by SLP, CLS, CMSSs, and nurse champions. Dysphagia topic delivered at Knowledge Café by CLS & at Emergency Skills Extravanza by CMSSs. • Internal Stroke Protocol updated with Extended Time Window in September 2019. CMSSs continued to support monthly orientation of new staff to internal stroke protocol. d. Utilize on-line learning strategies • Continued use of LMS module for dysphagia screening/management. Discussed updating to include oral health. • IPAD technology being used by SLP as stroke treatment tool. Explored other communication apps.
| KFLA-KHSC KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | improved; may achieve target | a. Sustain Stroke Distinction program at KHSC • Work underway with Decision Support Specialist for more automated quarterly data. Working on graphical display for Stroke Unit utilization, mortality rates and discharge disposition. • Stroke Distinction Committee continues to review stroke indicators every 6 months and publishing Infographic targeting front-line teams for year end. b. Support QHC in applying to Stroke Distinction Program; initiating self assessment and survey preparation • Updated Stroke Distinction documents shared with QHC. c. Identify, prioritize and deliver best practice/QI initiatives • Stroke Distinction QI action priorities updated in December 2019. • Participated in QI initiatives with a focus on: • Stroke Unit Utilization - rate had declined well below 70%; Q3 rate improved to 78% with following QI efforts: • Successful launch with PCH of FAST-TRACK project in Sept - those with ALPHA FIM 60+ transferred using automatic rehab referral. Results of 28 cases indicate referral to decision well under 4 hours • Median onset to rehab trsf of 6 days (at provincial target) for FAST Track patients • Education & Key messages developed for senior leaders re importance of Stroke Unit care shared with ATU, ED, Administration Coordinators, and Admitting • Neurologists reviewing elective admissions to K7 • Improved coordination and guide developed between GIM and Stroke Service re complex patients • Facilitated early outpatient MRI to avoid unnecessary TIA admissions • Stroke Information Packages fully implemented and provided to all K7 stroke patients. Extension of info beyond K7 in progress • Oral health assessment & care protocol drafted & trialed. Baseline data collected to inform implementation • Aphasia friendly patient resource implemented & guide developed for staff & families. • Stroke/TIA discharge order set in use and plans in place to extend beyond K7.
| KFLA-KHSC KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | achieving target | A trial of a part time OT Assistant was implemented in the KHSC stroke unit in 2019-20. After a review of this trial, the decision was that OT time was more critical than assistant time and the funding was reallocated to OT time. The trial revealed that OT assistants can be valuable in acute care to assist in the careplan, but at this time, OT time more essential due to the need for continual assessment and reassessment in the acute setting. PTA time is already available on the KHSC stroke unit.
| KFLA-PCH KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | achieving target | Successful Neuro 101 course held with SNSEO at PCH. PCH participation on symposium planning committee. Several staff, manager and physicians participated at September Transitions event and November symposium. Stroke team continues to share expertise by hosting shared work day for rehab assistants, acute care PT, and community OT this past year. Volunteers trained as planned to conduct art therapy over summer 2019 - further spread with therapy staff under consideration. PCH hosted an aphasia workshop through the Aphasia Institute last year and have followed up with a toolkit for staff/patients on the unit available since May 2019.
| KFLA-PCH KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | achieving target | GRASP Program continues on the unit with training of rehabilitation assistants. Stroke team staff participated in Rehab Intensity refresher in May 2019 with some follow up for therapists and assistants covering, particularly on the ABI service, to ensure complete stroke data. PCH partnered with KHSC to test process changes for Fast Track admission to rehabilitation for patients with Alpha FIM 60+ and recent review of 28 referrals shows team achieving target for less than 4 hours to decision to admit, 1.5 days from rehab referral to admission and a median total stroke onset to admission to rehab of 6 days for this patient group. In addition, have worked with Dr. Appireddy and stroke prevention clinic to pilot e-visits for rehab inpatients needing to be seen in follow up for stroke prevention clinic with excellent patient feedback. Dr. Ritsma and Dr. Appireddy are working together on a research project to further evaluate the program. Initial meetings held to explore improved connections to peer support including onsite peer support for inpatient rehabilitation patients and families. A pilot of the medical Stroke Neurology handover form was successful in facilitating safe patient handover. Stroke patients have had access to weekend physiotherapy since fall 2019. Piloting the revised RM&R Form with the acute Stroke team. Mindfulness Based Meditation therapy offered and a Resilience training group being formed.
| KFLA-PCH KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | improved; likely to achieve target | Exploring the ability to enhance role for rehabilitation assistants with stroke patient by training and developing protocols for assistants in in Functional Electrical Stimulation (Bioness) to assistants. Volunteers trained as planned to conduct art therapy over summer 2019- considering training rehab assistant staff. Offering Designing Adaptive Exercise Programs training to Assistants in May 2020.
| LG KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | achieving target
| LG KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | achieving target | Updating clinical pathway based on best practices, integrated stroke working group ensuring best practices will be implemented into the new building
| LG KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | improved; may achieve target | A request has been sent across the province through PPO asking for insight into the role of Rehabilitation Assistants in ISU. Also a meeting is scheduled March 23rd with Quinte regarding exploring all aspects of ISU development and management.
| L KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | improved; may achieve target | Rehabilitation staff participate in the bi-annual stroke symposium; monthly webinars hosted via provincial stroke rounds; utilize shared work day; attend workshops hosted by the regional stroke network. This helps bring evidence-based practices back to the rehab program. We have 5 stroke champions across the organization, one nurse attended the Prevention Stroke day on Feb 5th. Med/Surg manager is restarting HELLP program, which could provide assistance with stroke patients in the future. Currently, use of LMS is a gap - we need to improve on how to get stroke education to the staff on a timely basis. Mental health support continues to be a gap.
| L KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | unchanged; may or may not achieve target | A, B:. BGH stroke unit has not been referring patients post-discharge to our Day Hospital program. The number of referrals is low. A joint teleconference was held in November to discuss and identify barriers. Patients accessing the in-home Community Stroke Rehabilitation Program may or may not be referred to Day Hospital at discharge. If admitted, there is communication between community therapists and our hospital therapists. Collaboration is acceptable. C: Patient-oriented discharges (POD) are being used. There is constant communication between rehab and VPC regarding discharges. D&E:. Patient satisfaction surveys are handed out upon discharge from Day hospital, however this practice is not consistent and the survey should be reviewed and revised (looking at implementing the WatLX™) There is a potential to increase our partnership with Perth Stroke Support Group
| L KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | achieving target | PSFDH currently uses rehabilitation assistants/PTAs and they work within scope as defined by the College of Physiotherapists of Ontario. Rehab assistants are not currently part of the Home and Community Care Community Stroke Rehab Program.
Leadership & Coordination | R L&C1 | A. Plan Successions to build and mentor new leaders within the regional stroke program | improved; likely to achieve target | Recruited new Regional Stroke Education Coordinator in May 2019 and additional Regional Case Manager Stroke Specialist in Sept 2020. Experienced team is augmented by these talented new leaders. New District Stroke Coordinator also hired in 2019 by QHC with strong links to the leadership team at QHC, given previous QHC management experience.
|  | B. Develop Stroke Team Leadership Skills and Sustain Engagement | achieving target | All regional staff contribute to leadership of respective provincial workgroups, contributing to Chairing workgroup meetings as needed. Dr Jin attended Rotman leadership course winter 2020. Regional Stroke Team presented 5 presentations at Canadian Stroke Congress in 2019. Regional Stroke Team Engagement Plan is developed and underway.
| R L&C2 | Sustain a resilient Stroke Network that is flexible and responsive to a changing provincial context. | improved; may achieve target | Team is working to stay informed on all activities related to MOHLTC's Transformation Agenda and Integrated Care; engaged in Bundled Care initiatives, leading change at local, regional and provincial levels. Team has been working to keep in touch with OHT plans in each part of the region. Working closely with CorHealth. Participated in provincial audit of Stroke, Cardiac and Vascular care in March 2020.
| R L&C3 | Develop, monitor and implement Regional Stroke Workplan based on RSSC priorities and program mandate | improved; likely to achieve target | Workplan progress reports reported at regional level quarterly with full workplan report, including local workplans, completed March 2020.
| R L&C4 | Engage stakeholders in workplan priorities through an effective communication strategy | achieving target | Strokenetworkseo.ca website is kept updated on a continual basis. E-news delivered quarterly. Regional Stroke Steering Committee provided with quarterly briefing note update, workplan progress report and regional dashboard. Contact lists kept updated on a continuous basis. Infographics used in 2019-20 to more effectively communicate annual performance reports ( e.g. Stroke Report Card, Community Stroke Rehab Program Report, Stroke Support Group Evaluation, Stroke Distinction Accreditation Performance)
| R L&C5 | Sustain governance infrastructure for effective program oversight and stakeholder engagement | improved; likely to achieve target | RSSC vacancies have been filled and orientation provided as new members join. RSSC continues to meet regularly to oversee the program and advise on priorities, risks, emerging trends and future strategies. The regional Community Stroke Reintegration Leadership Team functions as Patient Advisory Council and has been very active this year, providing the region with critical input on Navigation and Transition tools, advising on Stroke Information Packages, a Patient Journey Map, and integrated care. This group has also successfully advocated for support for region-wide Aphasia Conversation Groups.
| R L&C6 | Build Communication and Accountability Links with SE LHIN | worsening; may not achieve target | With significant changes in Ontario Health and the 5 new regions, relationships will need to be re-built over the coming year(s).
| R L&C7 | Monitor and evaluate stoke care in the SE against provincial and national standards | improved; likely to achieve target | Although the provincial Stroke Report has been delayed in its annual release, the team expects to present annual data at the May RSSC. Meanwhile, the Regional Dashboard has been released quarterly and allowed the stroke teams across the region and across the care continuum to monitor, interpret and respond to performance data. A provincial Bundled Care Baseline Indicator Report was released in Jan 2020 and reviewed with local Bundled Care Task Groups. Each local stroke group has been using data to review progress, identify gaps and deliver on QI initiatives ( e.g., Kingston area Bundled Stroke Care Clinical Task Group Performance Report, KHSC-PCH Fast-Track Workgroup, KHSC Stroke Distinction Reports, QHC ISU Data, QHC hyperacute Kaizen QI work; LLG Annual Stroke Evaluation, CSRP Annual Report, Stroke Support Group Annual Report.) The team has been successful in working on new ways of communicating performance through infographics as noted under communication strategy.
| R L&C8 | Manage fiscal and human resources within given parameters | achieving target | Expenses as budgeted, no significant variances. Vacancies successfully filled. Regional Education Budget had to be reduced by 5K for 2020-21 due to budget constraints applied across KHSC. An identified risk is that EVT funding is currently well below actual volumes delivered given significant growth this fiscal; however, dialogue is underway regarding reallocations.
| R L&C9 | Link with/contribute to Regional, Provincial and National Networks & Organizations regarding workplan activity; link learning back to regional activity | achieving target | Strong participation and leadership in regional and provincial CorHealth Ontario advisory groups and councils. All team members liaise with regional counterparts for collaborative work and sharing of learning in relation to key priorities. Southeast Network has recently shared the following examples of our work with other networks: Regional Dashboard approach, Hyperacute ACT-FAST protocols, SPC E-Visit Pilot Results, Acute-Rehab-Community Stroke Services and Transitions plan and related activities, Fast-Track project information and Stroke Distinction plans.
| R L&C10 | Contribute to innovation in stroke care | achieving target | With the recruitment of 2 added stroke neurologists, a new physiatrist and a new neuro-interventional radiologist to our region, there has been significant growth in the opportunities to contribute to research and innovation. KHSC is participating in several hyperacute and acute research trials (e.g., ACT, Tempo-2, Easi-TOC). Dr Appireddy, stroke neurologist, has secured two large research grants to study virtual medicine in follow up to his E-Visit pilot in the Stroke Prevention Clinic. He is also working on studying social determinants of health in relation to stroke care. Peer-reviewed publications were released this year on rurality in stroke care and on e-visits in stroke prevention clinics.

## Primary & Secondary Prevention
RSSC Priority #1: To expand/improve timely equitable regional access to prevention supports and services
Reg | Objectives | REGIONAL and Local Implementation Activities - Prevention | Timeline | Lead/Contact
R P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs b) Improve linkages to self-management and community resources | a) COMMUNICATION/ROLES: ▪ Host a follow-up workshop from March 2018 ▪ Enhance access to stroke assessment expertise or consultation in emergency - target 90% ED TIA referral to SPC ▪ Promote transition of information for patient-centred hand-offs (use of Connecting Ontario Clinical Viewer, SHIIP, links to specialists, e-consults) b) LINKAGES: ▪ Make use of self-management programs, smoking cessation resource mapping and physical activity mapping, heart & stroke public education materials including FAST ▪ Increase linkages with www.SEhealthline.ca, community supports (support groups, aphasia programs, return to work resources, support agencies), Community Stroke Rehab Program | a) Workshop Feb 2020 b) ongoing with events | C. Murphy C. Murphy with SPC leads
R P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations b) Improve clinic efficiencies c) Build expertise and partnerships | a) TRIAGE: ▪ Adopt a common SPC triage algorithm in the South East, based on an update of the previous Ontario Triage Algorithm ▪ Establish a common understanding across clinics of triage guidelines ▪ Clarify when to admit TIA ▪ Continue to monitor wait times by triage categories ▪ Address wait times as needed b) EFFICIENCY: ▪ Maximize scope of practice of each interprofessional team member ▪ Make use of e-technology (e-documentation, e-health, e-visits) ▪ Explore strategies to improve access to cardiac testing (share cardiac monitoring devices with SPC, remote interpretation) c) EXPERTISE: ▪ Leverage SPCs as stroke champions with primary care and EDs within local communities (site visits, workshops, rounds) ▪ Address anticoagulation for atrial fibrillation as part of every education event and meeting encounter ▪ Incorporate knowledge translation specific to women and stroke prevention ▪ Spread knowledge/build partnerships with specialists (ophthalmology, vascular surgeons, internal medicine, intensivists) ▪ Build partnerships to support capacity and deliver training in vascular imaging (interpretation, contrast dye administration) ▪ Use a common tool for depression and cognition screening ▪ Make aphasia friendly materials available and continue to increase knowledge of supportive conversation techniques | a) by Feb 2020 b) plan for e-visit spread in 2019-20, initiate in 2010/21 c) Ongoing - build with planned educational events | a)C. Murphy with Local Hospital SPC Leads b)C. Murphy with Local hospital Leads c) C. Murphy and Education Coordinator
R P3 | Support the Indigenous inter-professional Primary Care Team in the regional implementation of an Indigenous vascular risk screening and management program: a) Update guidelines b) Support linkages to cultural safety c) Support education and training | a) GUIDELINES: ▪ Update Indigenous Community Hypertension Awareness Program guidelines and adapt within local communities b) CULTURAL AWARENESS: ▪ Support identification and linkages to specialists and providers with awareness of cultural safety c) EDUCATION: ▪ Support education and training in screening and management protocols to build community volunteer capacity | a) Year 1 b) Year 1 c) Q3/4 of Year 1 and into year 2 | a)C. Murphy b) C. Murphy/C. Martin c)C. Murphy /Education Coordinator
HPE | Objectives | QHC DISTRICT STROKE CENTRE - Prevention | Timeline | Lead/Contact
HPE P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs b) Improve linkages to self-management and community resources | a) COMMUNICATION ▪ participate in regional stroke prevention education activities/workshops ▪ analyze current data and develop action plan to achieve target of 90% TIA ED referral from QHC sites to Belleville SPC b) LINKAGES ▪ Update materials available within QHC SPC for patient resources including smoking cessation ▪ Utilize new physical activity map to incorporate physical activity promotion ▪ Review new heart and stroke materials and incorporate into patient education ▪ Consider referrals for Stroke Support Groups, Stroke Specific Exercise Groups and Community Stroke Rehab Programs if not already linked - consider development of standardized transition referrals | a) by March 2020 b) by December 2020 | a) M. Slapkauskas /DSC b) M. Slapkauskas
HPE P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations b) Improve clinic efficiencies c) Build expertise and partnerships | a) TRIAGE: ▪ Participate in developing and then implement a common South East SPC triage algorithm at QHC ▪ Continue to monitor wait times by triage categories and identify improvement opportunities as needed b) EFFICIENCY: ▪ Trial a different mechanism/model for follow up for inpatients to address longer wait times (e-consult, follow up by discharging IP physician) ▪ Assess feasibility and potential implementation of e-visit model to increase access ▪ Pilot use of MCards for 72 hour cardiac monitoring and reporting c) EXPERTISE: Participate in annual stroke prevention clinic meeting, regional prevention workshop and regional symposium | a. Sept 2019/Feb 2020 b. March 2020 c. June 2019 and Feb 2020 | a. M. Slapkauskas b. M. Slapkauskas c. M. Slapkauskas
KFLA | Objectives | KHSC REGIONAL STROKE CENTRE - Prevention | Timeline | Lead/Contact
K P1 | Improve linkages amongst ED, primary and secondary prevention providers: a) Enhance communication and clarity of roles between primary providers, ED, and Stroke Prevention Clinics; target=90% TIA ED referral to SPCs b) Improve linkages to self-management and community resources | a) COMMUNICATION/ROLES: ▪ Attend and participate in planning SPC/Primary Care March 2018 follow up workshop to clarify communication/roles. ▪ Coordinate Regional SPC Nurses Working Group. ▪ Continue to sustain good relationships, awareness of SPC role, & referral processes with HDH UCC, L&ACGH and KGH EDs. ▪ Continue to follow-up and meet with UCC & ED leads regarding SPC processes. ▪ Meet with L&ACGH ED Manager to review TIA referral to SPC & diagnostics-ensure TIA packages are current. ▪ Monitor referral rate from each local ED to SPC. Aim for continued target 90% ED TIA referral to SPC, including L&ACGH. ▪ Continue to use Connecting Ontario Clinical Viewer to enhance communication of info; investigate utility of reviewing Health Links coordinated care plans on SHIIP if available. b) LINKAGES: ▪ Refer to KFL&A smoking cessation and physical activity maps as needed, refer patients to Smoker's Helpline, & update smoking cessation info package. ▪ Continue to update TIA info package with most current heart & stroke resources. Continue to educate patients on FAST. ▪ Provide patients with info on community support services- KFL&A stroke resources located on SEhealthline.ca, support groups, aphasia program, return to work resources, community exercise program. Link patients to Community Stroke Rehab Program. Continue to update TIA info packages with latest community support materials. | a) Workshop Feb 2020 Ongoing sustaining relationships L&ACH Meeting May 2019 b) Ongoing | P. Christie/ Dr. Appireddy
K P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice: a) Improve adherence to best practice triage recommendations b) Improve clinic efficiencies c) Build expertise and partnerships | a) TRIAGE: ▪ Advise on common SPC triage algorithm in South East, based on updated Ontario Triage Algorithm. ▪ Host a SPC RN meeting to discuss common understanding of triage guidelines. ▪ Update current SPC CCP to reflect current Canadian Stroke Best Practice Triage guidelines ▪ Continue to review Stroke Distinction data on volume of TIA patients being admitted-participate in review of cases as needed ▪ Collect and report wait times by triage categories and per referral source. Target within 48 hours for Priority 2 patients. ▪ Continue to support daily M-F half day clinics and keeping clinic spot open each day for urgent patients. Troubleshoot a plan for physician coverage during vacation, sabbatical time away. b) EFFICIENCY: ▪ Continue to follow medical directives and update every 3 years. Continue to coordinate triage with physicians. ▪ Update current SPC and TIA D'ced from ED CCP to new Care Guideline format and current best practices. Work with ED lead on EDIS or other regional HIS to update TIA orders. ▪ Expand use of e-visits for any appropriate follow-up patients, develop e-visit eligibility checklist; phase in all SPC physicians/team members and build an interprofessional approach ▪ Spread learnings of e-visits to internal medicine service and share learning for potential spread to other SEO SPC clinics. ▪ Publish pilot findings and present on e-Visit project at May provincial Stroke Rounds. ▪ Expand use of paperless chart-use and refer to e-documentation as possible; build fillable pdf team assessment form. ▪ Monitor ECHO wait times. Monitor processes for patients being referred for outpatient echo post discharge & new option for patients at OP echocardiography lab, Queen's School of Medicine. c) EXPERTISE: ▪ Continue to offer advice & act as stroke champions on TIA management with primary care and EDs (workshops, rounds) ▪ Participate in supporting education event at Primary Care/SPC Feb 2020 session. Consider presenting and/or advising on session on women and stroke prevention & anticoagulation. ▪ Mentor new SPC nurses and physicians (including other SPCs in south east) as needed. Continue to provide educational sessions based on learning needs of EDs and primary care. ▪ Examine data related to anticoagulation. Examine delays in starting anticoagulation. Continue to perform med reconciliation & address patient compliance. Review of barriers to anticoagulation at June 2019 SPC meeting. ▪ Continue to maintain good relationship & connect with other specialists such as diabetes education, vascular surgeons, internal medicine, intensivists and review cases as needed. Meet with ophthalmologists re TIA management. ▪ Continue participation in Stroke Distinction Interprofessional Committee. ▪ Test use of depression and cognition screening DOC components on small subset; test related referral to primary care. ▪ Examine outcome of depression study when completed. Continue to use MOCA when needed. ▪ Modify aphasia friendly materials available at both KHSC SPC sites, as needed. | a) by Feb 2020 Ongoing collecting, reporting data q 3 mos b) Update CCP & order set by Dec 2019 E-visit spread 2019/20. Present May 2019 Rounds; publication in 2019; fillable pdf team assessment form by March 2020 c) Ongoing SPC meeting June 2019 & 2020 | a)P. Christie P. Christie/K.Gray-data b)P. Christie, K. Gray/ Dr. Appireddy/M. Foss/P. Christie/ J. Lalonde c) SPC Physicians/ P. Christie/Jeff Lalonde
K P3 | Support the Indigenous inter-professional Primary Care Team in the regional implementation of an Indigenous vascular risk screening and management program: a) Update guidelines b) Support linkages to cultural safety c) Support education and training | ▪ Continue to support patients of Indigenous ancestry presenting to ED or in transfer (Moose Factory). Continue to maintain well-established referral process from Moose Factory area. ▪ Participate in face-to-face and/or on-line Indigenous cultural sensitivity and safety training to provide culturally safe linkages for the Deseronto and Kingston Indigenous Blood pressure screening program with expansion to region as needed | Ongoing March 2020 | SPC Physicians/P. Christie
L&G | Objectives | LEEDS & GRENVILLE - Prevention | Timeline | Lead/Contact
LG P1 | Enhance timely access to the Stroke Prevention Clinic (SPC) demonstrated by: a) 90% referral rate from the ED b) All referrals reviewed and triaged within 48 hours of receiving | a) Referral from ED ▪ Clinic staff will participate in workshops hosted by the Stroke Network of SEO ▪ Provide regular feedback to the ED physicians and staff re: referrals received, follow-up and outcome to encourage referrals Triage of referral b) ▪ Support staffing model that ensures referrals are triaged in a timely manner to ensure appropriate follow-up. | a) Workshop 2020 Ongoing | D. Henson (contact) D. Henson/ D. Andress/Dr. Riaz D. Henson
LG P2 | Support and implement recommendations made for best practices relating to SPC triage | ▪ Development and implementation of a "Stroke/TIA" lab work panel to ensure appropriate tests are complete for follow-up with SPC ▪ Support staff to attend learning opportunities related to best practice stroke care | In Progress | D. Henson
Lanark | Objectives | LANARK - Prevention | Timeline | Lead/Contact
L P1 | Improve linkages amongst ED, primary and secondary prevention providers | ▪ Improve linkages and referral process to the PSFDH VPC from Brockville General Hospital for patients from Lanark county | 2019 - 2020 | Crystal Newman
L P2 | Enhance expertise and capacity of prevention providers to support core elements of best practice | A) Triage: Decrease number of referrals to Brockville General Hospital for TIA cases where symptoms have resolved by: ▪ Continue regular case review; build communication between PSFDH ED leads and BrGH Hospitalist lead B) Efficiency: Make best use of Imaging Capacity - Improve appropriate use of CTA (and Doppler) for TIA workup in the ED by: ▪ Deliver education for the ED physicians - key concepts on history, physical examination, and appropriateness of CTA. ▪ Consider developing/testing a TIA care pathway or order set for PSFDH with simple poster for the ED. ▪ Provide a template for ordering CTA from the ED, with details on the patient symptoms on the requisition. ▪ Collaborate: KHSC neuroradiology to provide rapid interpretation of Smiths Falls CTA when needed. C) Expertise: Review patient education materials on Rehab floor to ensure consistent information about VPC Clinic and application of evidence based secondary prevention guidelines | a) 2019-2020 ongoing b) by 2021 c) 2019-10 | a) Crystal Newman & Dr C. Duvernet b) Dr Parikh, Dr Islam, with Dr Del Grande, Dr Jin, Dr Duvernet, Imaging, VPC and ED teams c) Crystal Newman

## Hyperacute & Stroke Recognition
RSSC PRIORITY #2: To improve timely regional access to hyperacute stroke treatment
REG | Objectives | REGIONAL and Local Implementation Activities - Emergency | Timeline | Lead/Contact
R E1 | Continuously improve the Endovascular Treatment (EVT) Service within KHSC a) monitor service and ensure quality data b) use data to direct quality improvements | a) MONITORING/DATA QUALITY ● Ensure Data Quality: collaborate with CorHealth, KHSC Medical Records, acute stroke team, IVR team and Information Management in the collection and submission of quality administrative data and creation of accurate outcome reports to accurately monitor the EVT Service b) QUALITY IMPROVEMENT (QI) ● Lead/Deliver QI as needed based on outcomes using standard QI methodology ● Coordinate/lead debriefs when needed to assist process learning and coordination | a) ongoing quarterly outcome reports b) ongoing planning at quarterly EVT workgroup meetings | a) C. Martin/C. Murphy b) C. Martin/Dr. Jin
R E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging b) Implement triage tools within the EDs for the expanded time window; consider findings from pre-hospital screening pilots in other regions | a) RAPID IMAGING: ● Implement RAPID advanced CT perfusion imaging in Kingston ● Implement RAPID advanced CT perfusion imaging in Belleville b) TRIAGE TOOLS: ● Support teaching of large vessel occlusion triage tool within KHSC ED ("ACT-FAST") ● Test the ACT-FAST triage protocol in the KHSC ED and ● Plan & spread the use of a screening tool to other EDs in the region based on learning from the KHSC Pilot ● Consider findings from Champlain/SWO pre-hospital pilots of large vessel screening tools | a) KHSC Q1 2019/20 QHC Q3 2019/20 b) KHSC Q1 2019/20 Region Q4 2019/20 | a) Dr. Jin b) C. Martin/C. Murphy with each ED
R E3 | Create/develop telestroke readiness and an implementation plan with Brockville: a) Support the building of imaging capacity b) Engage stakeholders in readiness planning c) Develop and initiate an implementation plan | a) IMAGING: ● Support capacity and delivery of training in vascular imaging for implementation of 24/7 mCTA b) ENGAGEMENT/SUPPORT: ● Engage stakeholders in readiness planning (CorHealth Ontario, Ontario Telemedicine Network, LHIN, SECHEF, the public, paramedic & pre-hospital services, hospital leaders and providers including physicians) ● Build LHIN-wide support for Brockville telestroke program c) PROJECT PLAN: ● Develop a project implementation plan in year 1 ● Initiate the plan in year 2 | a) Q4 2019/20 b) Q3 2019/20 c) plan by Q4 2019/20 initiate plan in 2020/21 | a) C. Murphy b) C. Murphy c) C. Murphy/Dr Jin
R E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time of <30 mins at KHSC and <45 mins at QHC b) Door-In-Door-Out DIDO transfer time 45 mins | a) DOOR-TO-NEEDLE (DTN): (National target = 30 minute door-to-needle (DTN) time) ● Sustain < 30 minutes at KHSC ● Support progress toward <45 minutes at QHC ● Support QHC to conduct, implement and sustain change ideas from QHC Kaizen Event b) DOOR-IN-DOOR-OUT (DIDO): ● Support progress toward a 45 minute door-in-door-out (DIDO) transfer time at QHC ● Support QHC to conduct, implement and sustain change ideas from QHC Kaizen Event | a) KHSC ongoing QHC start in Q1 2019/20 b) QHC start in Q1 2019/20 | a) Dr. Jin/C. Murphy /D. Damron b) Dr. Jin/ Dr. Samis/ D. Damron
R E5 | Support/Advise KHSC - KGH Interventional Neuro-Radiology (INR) in the planning of a Regional Aneurysm Coiling Service | a) PLAN: Share Learning from EVT work to assist in creation of ● Flow map ● Business case ● Project plan b) ENGAGEMENT: Participate in a coiling workgroup led by Interventional neuroradiology c) REGIONAL ACCESS: When ready, consider plan for spread across region | a) Q1 2019/20 b) Q2/3 2019/20 c) March 2021 | C. Martin/C. Murphy (with D. Tampieri and K. Pearson)
HPE | Objectives | QUINTE DISTRICT - Emergency | Timeline | Lead/Contact
HPE E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging b) Implement triage tools within the EDs for the expanded time window | a) RAPID IMAGING: ● Implement RAPID advanced CT perfusion imaging in Belleville b) TRIAGE TOOLS: ● Implement screening tool in QHC ED (ACT - FAST) to support triage for expanded time window | a. TBD b. Q4 2019/20 | a. M. Coulter/TBD b. M. Roblin
HPE E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time <45 mins at QHC b) Door-In-Door-Out DIDO transfer time 45 mins | a) DOOR-TO-NEEDLE (DTN): (National target = 30 minute door-to-needle (DTN) time) ● Conduct Kaizen quality improvement event in Q1 of 2019/20 to support progress toward <45 mins at QHC ● Implement and sustain change ideas from QHC Kaizen Event/QI improvement mapping ● Address delays in DTN related to nurse assignment for tPA bolus b) DOOR-IN-DOOR-OUT (DIDO): ● Conduct Kaizen/quality improvement event in Q1 of 2019/20 to support progress toward a 45 minute DIDO transfer time at QHC ● Implement and sustain change ideas from QHC Kaizen Event 45 minute door-in-door-out (DIDO) transfer time at QHC | a. Q1 2019/20 start with follow up activities b. Q1 2019/20 start with follow up activities | a.QHC QI Project Lead/M. Roblin/A. Samis b.QHC QI Project Lead/M. Roblin/A. Samis
KFLA | Objectives | KFLA COUNTY - Emergency | Timeline | Lead/Contact
KFLA E1 | Continuously improve the Endovascular Treatment (EVT) Service within KHSC a) monitor service and ensure quality data b) use data to direct quality improvements | a) MONITORING//DATA QUALITY ● Participate in Quality Data Collection with acute stroke team, IVR team, KHSC Medical Records and Information Management for submission of quality administrative data and creation of accurate outcome reports b) QUALITY IMPROVEMENT (QI) ● Continue to monitor the EVT Service ● Participate in QI as needed based on outcomes using standard QI methodology ● Continue to hold debriefs to clarify process as needed and update documents accordingly | a) ongoing quarterly outcome reports and CIHI submission b) ongoing planning at quarterly EVT workgroup meetings | a) A. Dube/E. Brunet b) C. Martin/ C. Murphy/Dr. Jin with EVT Workgroup
KFLA E2 | Create and implement a regional protocol for the expanded 6-to-24 hour time window for hyperacute treatment a) Implement "RAPID" Imaging b) Implement triage tools within the EDs for the expanded time window | a) RAPID IMAGING: ● Implement and improve knowledge of RAPID advanced CT perfusion imaging in Kingston ● Support Belleville in learning RAPID advanced CT perfusion when ready b) TRIAGE TOOLS: ● Teach the use of large vessel occlusion triage tool within KHSC ED ("ACT-FAST"); KGH site, then UCC ● Test the ACT-FAST triage protocol in the KHSC ED and make changes based on learning ● Incorporate teaching into ongoing triage orientation at KHSC ED and UCC ● Share learning with region to help with spread other EDs | a) KHSC Q1 2019-20 (QHC Q1 2020-21) b) KHSC Q1 2019/20 | a) Dr. Jin/D. Tampieri Dr Patel b) C. Murphy/ J. Donaldson/ L. McDonough
KFLA E4 | Improve efficiency of timely assessment, rapid decision-making and transfer processes for hyperacute treatment a) Door-to-Needle DTN time of <30 mins at KHSC | a) DOOR-TO-NEEDLE (DTN): (National target = 30 minute door-to-needle (DTN) time) ● Sustain < 30 minutes at KHSC with ongoing reinforcement of acute stroke protocol processes | a) KHSC ongoing | a) Dr. Jin/C. Murphy/J. Donaldson
KFLA E5 | Support/Advise KHSC - KGH Interventional Neuro-Radiology (INR) in the planning of a Regional Aneurysm Coiling Service | a) PLAN: Use learning shared from EVT work to assist in creation of ● Flow map ● Business case ● Project plan b) ENGAGEMENT: Create and lead a coiling workgroup (led by Interventional neuroradiology) c) REGIONAL ACCESS: When INR ready, support KHSC to create a plan for spread across region | a) Q1 2019/20 b) Q2/3 2019/20 c) March 2021 | D. Tampieri/ K. Pearson D. Tampieri/ K. Pearson C. Martin/C. Murphy
L&G | Objectives | LEEDS & GRENVILLE COUNTIES - Emergency | Timeline | Lead/Contact
LG E2 | Support the use of the ACT-FAST triage protocol as appropriate at the completion of the KHSC pilot. | ● Participate in training required to effectively use the triage protocol. | Q4 2020 | N. Valade (Contact)
LG E3 | Create business case for a Telestroke Program at BGH a) Support the building of imaging capacity b) Engage stakeholders in readiness planning c) Develop and initiate an implementation plan | a) IMAGING: ● Support staff in attending training opportunities in vascular imaging for implementation of 24/7 mCTA b) ENGAGEMENT/SUPPORT: ● Engage stakeholders in readiness planning (CorHealth Ontario, Ontario Telemedicine Network, LHIN, SECHEF, the public, paramedic & pre-hospital services, hospital leaders and providers including physicians) ● Build LHIN-wide support for Brockville telestroke program c) PROJECT PLAN: ● Develop a project implementation plan in year 1 ● Initiate the plan in year 2 | a) Q4 2019/20 b) Q3 2019/20 c) plan by Q4 2019/20 initiate plan in 2020/21 | a) B. Yam b) C. Murphy/J. Caffin c)J. Caffin/C. Murphy with Dr. Shenfield and Dr Jin
Lanark | Objectives | LANARK COUNTY - Emergency | Timeline | Lead/Contact
L E2 | Implement triage tools within the Eds for the expanded time window at PSFDH | Adopt and implement the triage screening tool in both emergency departments of PSFDH | Q4 2019/20 | J. Drynan

## Acute-Rehab-Community Pathways
RSSC Priority #3: To create/develop patient and family-centred regional transition protocols for acute to inpatient rehab to community care
REG | Objectives | REGIONAL and Local Implementation Activities - Acute-Rehab-Community | Timeline | Lead/Contact
HPE |  | QUINTE DISTRICT - Acute-Rehab-Community
KFLA |  | KFLA COUNTY - Acute-Rehab-Community
L&G |  | LEEDS & GRENVILLE COUNTIES - Acute-Rehab-Community
Lanark |  | LANARK COUNTY - Acute-Rehab-Community
R A-R-C 1 | Participate in provincial CorHealth Ontario Bundled Funding Stroke Workgroup and link to provincial and local Communities of Practice a) Build provincial links b) Establish regional links | a) PROVINCIAL ● Participate in CorHealth Workgroup ● Participate in provincial Communities of Practice relevant to stroke bundled funding b) REGIONAL ● Establish two-way communication links with our regional partners to support regional/provincial implementation | ongoing participation in workgroup and any new forums | C. Martin/S. Huffman
R A-R-C 2 | Adapt the provincial Bundled Funding Pathways and related expectations for our region to enable implementation of common components and parameters of regional transition protocols and services a) Develop a SE Stroke Pathway with common components and parameters in alignment with bundled funding/QBP standards. b) Translate into local pathways for west, central, east | a) SOUTH EASTSTROKE PATHWAY(S) (algorithm for who goes where when and how that is supported) i. Admission to Acute Stroke Unit Care ii. Acute to Home without Rehab needs ● i.e., Secondary stroke prevention, community supports iii. Acute transition to rehabilitation (inpatient, early supported discharge, outpatient, home-based rehab) ● i.e., standardized use of Alpha FIM, standardized timeframes for acceptance and transition to rehab service iv. Inpatient Rehabilitation transition to Community Based Rehabilitation (outpatient or in-home) ● i.e., standardized wait time to first rehab visit; standardized service model v. Community Supports to stay well when transitioning from any of the above ● i.e., Stroke Support Groups including Indigenous Supports, stroke-specific exercise group, aphasia conversation group and self-management groups b) LOCAL PATHWAYS as above | a) May 2019 b) May 2019 for bundled funding sites | a) S. Huffman b) S. Huffman
R A-R-C 3 | Deliver Local/Regional Forum(s) and Education to facilitate clinical implementation of bundled funding. This will: a) Inform providers of current state, expectations and gaps b) Identify priorities for change/action c) Deliver a Regional Forum to support knowledge translation in bundled care and local action plans | a) CURRENT STATE, EXPECTATIONS, GAPS ● Use the SE LHIN Rehab Capacity Assessment to inform current state ● Use provincial bundled funding self-assessment tools b) IDENTIFY PRIORITIES for CHANGE ● Identify priorities for change in each local area to meet bundled funding expectations c) REGIONAL FORUM ● deliver education on bundled funding highlighting experience of early adopters ● invite speakers to support learning in identified areas of change priorities ● support QI approach to facilitating implementation of local priorities for changes | a) June 2019 b) June 2019 c) Regional Forum in Sept 2019 | a) S. Huffman b) S. Huffman with local leads c) S. Huffman and Education Coordinator
R A-R-C 4 | Pilot change opportunities to support local pathway adoption (i.e., key changes in delivery models or transitions in each local area) | LOCAL ADOPTION ● Confirm selected priorities for change within each local area ● Develop local plans to address necessary changes ● Implement, test and modify at least one key change opportunity per local area ● Plan for sustainability and spread of positive changes | June 2019 to March 2021 | S. Huffman with local leads

## Expertise & Capacity
#4 EXPERTISE & CAPACITY: Sustain/Enhance regional stroke expertise/capacity to deliver best practice stroke care, supporting ongoing connections, recruitment and retention
REG | Objectives | REGIONAL and Local Implementation Activities - Knowledge Translation | Timeline | Lead/Contact
R KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Contribute to human resource recruitment and retention within stroke care b. Support champions and staff in relevant learning needs c. Collaborate with partners in learning (e.g. ABI, Behavioural Support Teams, Learning Collaboratives) d. Utilize on-line learning strategies Detailed in Local Plans | Ongoing | Regional Team
R KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Sustain Stroke Distinction program at KHSC (EVT, oral health, aphasia etc) b. Support QHC in applying to Stroke Distinction Program; initiating self assessment and survey preparation c. Support stroke teams to identify best practice initiatives e.g. acute and integrated stroke unit best practices, rehabilitation best practices, community rehabilitation best practices Detailed in Local Plans | a. Ongoing b. Apply by Sept 2020 c. Ongoing/See Local Plans | a. C. Murphy b. D. Damron/DSC c. Regional Team
R KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Gather information on these roles in other parts of the province. b. Support local providers in practice changes and local implementation pilots Detailed in Local Plans | a. March 2020 b. March 2021 | a. G. Brown/S. Huffman b. G. Brown/S. Huffman
R KT4 | Ensure access to Aphasia Conversation Groups across the region | a. Sustain the Kingston and Belleville aphasia conversation groups b. Support SE LHIN Home and Community Care in the evaluation of new aphasia conversation groups (Kingston) c. Support the spread of the aphasia conversation groups region-wide | a. March 2020 b. June 2019 c. March 2021 | a. G. Brown b. G. Brown c. G. Brown
R KT5 | Community & LTC - Enable stroke survivors & caregivers to live in the community supported by programs & services that optimize quality of life in these domains: a. Person-Centred Skilled Stroke Care & Rehabilitation b. Community Co-Navigation c. Individual Well-Being & Meaningful Engagement d. Access to Supports & Services e. Supported Mobility in the Community | a. Person-Centred Skilled Stroke Care & Rehabilitation ● Integrate patient/client experience/outcomes into the Community Stroke Rehabilitation Program (CSRP) evaluation ● Present findings of CCC/LTC Report in LTC venues (e.g. Behavioural Support Networks); collate feedback to identify learning opportunities ● Support the regional implementation of Stroke Information Packages ● Support the SE Learning Collaborative sessions ● Promote uptake of LTC Stroke Care Plans, Brain, Body & You, Education Posters, TACLS & other resources ● Promote use of Shared Work Day b. Community Co-Navigation ● Evaluate effectiveness of Kingston Community Stroke Expo with potential to offer similar event in HPE and LLG ● Complete and implement Patient Journey Map to support navigation and effective transitions ● Community Reintegration Leadership Team to review provincial navigation models; explore/leverage findings within SE ● Complete pilot of Community Reintegration Questionnaires and evaluate findings to identify next steps ● Pilot the integration of a Transitions Checklist into the Community Stroke Rehab Program ● Support connections to support groups and community services after discharge ● Raise awareness of website resources: Healthline Stroke Resources and Stroke Network Community Supports c. Individual Well-Being & Meaningful Engagement ● Support changes to supports groups in response to changing demographics (e.g. younger age, growing volumes, need for 'graduate' social-recreational groups) ● Coordinate & facilitate regional teleconferences for SE Stroke Support Group Facilitators ● Support re-establishing Stroke Specific Exercise Program in Brockville and sustain existing SE programs ● Support evaluation of Kingston aphasia buddies program and potential to expand to other areas of the SE ● Support expansion of stroke support group services both on-site (e.g. Napanee) and via Telemedicine using OTN ● Sustain peer visiting in Brockville & Perth and expand to Belleville & Kingston ● With Indigenous communities, explore stroke survivor & caregiver support group concept starting with Quinte ● Collate regional data and deliver Annual Stroke Support Group Evaluation Reports with recommendations to SE LHIN ● Support delivery of Self Management Programs including the Living with Stroke (LWS) Program annually in each area ● Promote awareness and uptake of SE Return to Work Toolkit d. Access to Supports & Services ● Continue to advocate for referrals to social work for assistance with financial supports and services ● Include information/presentations on financial supports & services in relevant workshops/education sessions e. Supported Mobility in the Community ● Continue to advocate for transportation supports ● Promote awareness of SWO Driving Resource and adapt resource to SE | March 2020 March 2020 December 2019 Ongoing Ongoing April 2019 January 2020 March 2020 October 2019 September 2019 Ongoing Ongoing Ongoing Ongoing September 2019/Ongoing September 2019 Ongoing March 2020 March 2020 Ongoing Ongoing Ongoing Ongoing Ongoing Ongoing Ongoing/April 2019 | a. G. Brown b. G. Brown c. G. Brown d. G. Brown e. G. Brown
HPE | Objectives | HPE COUNTIES/QUINTE DISTRICT - Knowledge Translation | Timeline | Lead/Contact
HPE KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Assess needs and deliver follow up education for nursing staff on the Integrated Stroke Unit (IISU) b. QHC sending PT and PTA staff to participate in PT Neuro 101 Clinical Education Course c. Participate in Regional Stroke Symposium in Nov 2019 through planning committee and facilitating staff attendance (ISU nursing and allied team members) | a. Winter /Spring 2020 b. May 2019 c.. May - Nov 2019 | a. M. Roblin b. D. Damron c. M. Roblin/DSC
HPE KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Implement standardized process for patient education and stroke information packages on the ISU for acute and rehab patients b. Plan and implement stroke peer visiting service with Community Care for South Hastings c. Maintain Alpha FIM certification of therapy staff including those covering ISU on weekends to achieve improvements to align with Regional/Provincial Alpha FIM completion target (?? increase to 90% when excluding those discharged/die in 2 days or less). d. Complete a readiness assessment to apply for Accreditation Canada Stroke Distinction including access to data for required indicators e. Implement standardized process for community linkages during and following Day Rehab f. Apply for Stroke Distinction for Acute and Rehabilitation Program | a. May 2019 - Dec 2019 b. June 2019 c. April 2019 training & quarterly monitoring d. June 2020 e. DSC f. Sept 2020 | a. D. Damron/M. Roblin/OT Lead b. D. Damron/M. Roblin/OT Lead/DSC/ L. Pyle c. J. Levy/D. Damron/DSC/S. Huffman d. DSC/D. Damron e. DSC f. DSC/ D. Damron
HPE KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Assess therapy pairs model and utilization of therapy assistants on the ISU. | a. Dec 2019 | a. D. Damron and therapy leads
KFLA | Objectives | KFLA COUNTY - Knowledge Translation | Timeline | Lead/Contact
KFLA-KHSC KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Contribute to human resource recruitment and retention within stroke care • Emphasize retention of new stroke team members through ongoing interprofessional collaboration & mentorship • Evaluate schedule of added allied health resource and case manager support: OT (0.4 FTE), OTA Assistant (0.2 FTE), PT (0.4 FTE), RD (0.2 FTE) & SLP (0.5 FTE) and Case Manager/Stroke Specialist (0.6 FTE) • Submit and follow up on business cases/funding opportunities for a) new stroke neurologist and b) hospitalist b. Support champions and staff in relevant learning needs • Use the Stroke Distinction self-assessment findings to identify the focus for enhancing stroke care competencies • Deliver education inservices targeting specific/top needs (see below under KT2) • Continue to host annual KHSC Neurosciences Workshop in Q4 • Continue to support orientation of new staff to best practice stroke care (e.g., internal stroke protocol, ED/IVR/CC/Kidd 7 orientation) • Send at least one stroke team member to congress annually and support interprofessional team stroke education • Promote local Brain, Body and You and shared work day resources, provincial interprofessional stroke competency resources & national resources - Canadian Stroke Best Practice Recommendations, TACLS c. Collaborate with partners in learning • Collaborate in planning & delivery of knowledge translation activities (e.g., regional stroke symposium Nov 2019, Acute Care Collaborative Follow-up & development of resources such as posters and pocket cards) d. Utilize on-line learning strategies • Continue use of LMS modules (e.g., dysphagia screening) • Develop one additional stroke related LMS module (e.g. oral health, falls prevention, smoking cessation or mobilization) • Pursue use of IPAD technology as SLP and OT stroke treatment tool • Review Partners in Stroke Recovery iBook for currency | a. stroke team schedule decisions by June 2019; medical staff business cases by fall 2019 b. Ongoing c. Ongoing d. March 2021 | a. Professional Practice Leaders and Dr Jin b. ASU team, Clinical Learning Specialists for each relevant area c. ASU team, Regional Stroke Education Coordinator d. ASU team and Jennifer Rogers
KFLA-KHSC KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Sustain Stroke Distinction program at KHSC • Develop a more streamlined plan with Decision Support Specialist for more automated quarterly data • Inform regional HIS project team of required information and decision support tools • Continue collective review of stroke indicators every 6 months; publish annual KHSC Stroke Distinction Data Infographic • Emphasize monitoring ASU utilization. Target ≥ 75% ASU Utilization. • Incorporate stroke unit patient/family satisfaction survey • Complete self-assessment against Stroke Distinction Standards every 2 years (spring 2021) b. Support QHC in applying to Stroke Distinction Program; initiating self assessment and survey preparation • Share key documents and learnings c. Identify, prioritize and deliver best practice/QI initiatives • Review and update Stroke Distinction action priorities every 6 months (using Distinction data, self-assessment, 2018 Report). • Participate in QI initiatives based on currently ranked Stroke Distinction action priorities with a focus on: • Acute stroke unit utilization & patient flow - expand stroke unit capacity and improve transition options • Dysphagia screening process - consider how to capture intubated patients in ICU; continue education beyond Kidd7 • Oral health guideline implementation • Aphasia friendly patient resources • Hemorrhagic stroke project findings • Mobilization cues including falls prevention • Update CCPs, Order Sets in 2021. Investigate updating of CCP to new KHSC care guideline format | a. Ongoing with automated reports by March 2020; self assessment Spring 2021 b. March 2020 c. March 2021 | a. C. Murphy, KHSC Stroke Distinction Committee b. C. Murphy c. ASU team with ED and Critical Care leads
KFLA -KHSC KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | • Consider introducing rehab assistants at KHSC including related labour implications | March 2020 | Kim Smith and professional practice leaders
KFLA | Objectives | KFLA COUNTY - PCH Knowledge Translation | Timeline | Lead/Contact
KFLA-PCH KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Partnering with Stroke Network to host Neuro Physio 101 (2 day clinical course for up to 50 PT and PTAs from across the region) with neuro experts b. Participate in regional stroke network activities and education opportunities such as Regional Stroke Symposium c. Participate in shared work day program as opportunities arise and link stroke team expertise with others in the region d. Develop Art Therapy program and toolkit for therapy. Includes Field experience training session with Marta Scythes for introductory art therapy training with volunteers to develop summer program (2019) with spread to PTA/OTAs to support adjunct therapy tool (2019/20). Plan to explore making an educational video to share with community/LHIN/stakeholders. e. Follow up to Supportive Conversation (SCA course in Dec 2018) for Aphasia to sustain the learning, toolkits are being developed for patients/family and staff to use. | a. May 2019; b. Nov 2019 and ongoing; c . Ongoing d. June 2019 for volunteer program; Jan 2020 for PT/OTA e. Initial toolkit June 2019 with ongoing follow up/training | a. P. Harvey/S. Huffman b. Stroke team c. Stroke Team d. B. Ritsma/M. Scythes/Stroke Team e. J. Bouchard/K. Colwell
KFLA-PCH KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. GRASP Program (Hand Rehab program) for Stroke patients that PCH is now offering CVA patients. PCH OT's have trained assistants who are delivering the program. b. Rehab Intensity Therapy refresher in May 2019 with quarterly reporting transferred to stroke team c. Mental Health Peer Support in community reintegration expanding to CVA population d. Mindfulness based meditation will be explored to be offered to CVA patients (currently provided to SCI patients). e. Participate and co-lead patient flow quality improvement workgroup to identify and test process changes to improve onset to rehab time and flow through PCH (ie development of short form for stroke rehab referrals and communication tool with neurology/physiatry) | a. March 2020 b. May 2019 and ongoing c. June 2020 d. June 2020 e. April 2019 - ongoing through 2 year plan | a.. P. Harvey/OT b. K. Colwell/S. Huffman c. K. Colwell d. K. Colwell e. K. Colwell/B. Ritsma/J. Mels-Dyer
KFLA-PCH KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | Exploring the ability to enhance role for rehabilitation assistants with stroke patient by training and developing protocols for assistants in in Functional Electrical Stimulation (Bioness) to assistants | a. March 2020 | a. P. Harvey/B. Ritsma/ MJ Demers
L&G | Objectives | LEEDS & GRENVILLE COUNTIES - Knowledge Translation | Timeline | Lead/Contact
LG KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. Contribute to human resource recruitment and retention within stroke care • Recruit new champions and staff to prepare for the move of some stroke-related services to our new patient tower • Build up staffing to support increased activity associated with Telestroke and an Integrated Stroke Unit b. Support champions and staff in relevant learning needs • STAND: Plan process for STAND orientation, monitoring, and sustaining • CNS: Determine process for CNS monitoring • Hemi-Arm: Deliver knowledge exchange on key points of hemi-arm protocol. Investigate communication tools such as poster, more use of white boards • Acute Stroke Protocol: Review what is done when witnessing inpatient with signs of stroke. Learn about updated Acute Stroke Protocol from Regional Team c. Collaborate with partners in learning • Support new team members to attend educational opportunities including shared learning days at KHSC • Participate in planning Regional Stroke Symposium Nov 2019 • Identify knowledge gaps and inform regional team to help populate the education plan d. Utilize on-line learning strategies • Provide time for staff to use on-line learning strategies as they are made available (e.g., on-line dysphagia screening modules) | Ongoing | BGH Managers/Local team
LG KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Integrated Stroke Unit (ISU): • Develop project plan for Integrated Stroke Unit in our new patient tower as part of our Operational Readiness work to be ready for implementation as we take occupancy. Engage stakeholders as plans start to be developed (e.g.., physicians, internal medicine, nursing, allied & other ISU leads/experts). Project plan to also include communication strategy, implementation (e.g., recruitment-see LG KT1 a., education, training, equipment ) - and evaluation & sustainability. • Implement project plan for ISU • Monitor b. Deliver best practice/QI initiatives • Decrease volume of TIA admissions by 5% • Conduct case reviews between PSFDH ED Physician Lead and Hospitalist Lead • Revisit repatriation processes to PSFDH Rehab | a.Develop Project Plan Dec 2019 Implement ISU April 2020 b. Case Reviews-Ongoing Repatriation to PSFDH-Apr 2020 | a. T. Wing/J. Caffin with Regional Stroke Team b. Case Reviews: Dr. Duvernet (PSF), Dr. Sharma PSFDH Repatriation: BGH/PSFDH Managers/Flow Coordinators/S. Huffman
LG KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Review models for rehabilitation assistants related to Integrated Stroke Units and consider options for change for BrGH (may include possible CDA role, and new ways to use assistants across acute and rehab) b. Plan and implement any identified change opportunities for rehab assistant models in conjunction with launch of ISU c. Monitor and sustain use of rehabilitation assistants in contributing to rehabilitation intensity minutes and ensure data quality consistency for rehab assistant time collected with any changing staff or roles. | a. Dec 2019 b. Sept 2020 c. Ongoing | a. T. Wing and S. Huffman b. T. Wing/A. Rodgers c. A. Rodgers b. Case Reviews: Dr. Duvernet (PSF), Dr. Sharma PSFDH Repatriation: BGH/PSFDH Managers/Flow Coordinators/S. Huffman
Lanark | Objectives | LANARK COUNTY - Knowledge Translation | Timeline | Lead/Contact
L KT1 | Build inter-professional stroke expertise across the continuum (physician, nursing, allied health, PSWs, champions) | a. All team members participate in local stroke education as available and relevant to roles. b. Team members to consider use of shared work day or field training to provide learning related to stroke care across the continuum. c. Utilizing our Learning Management System (LMS), work with KGH and BGH to determine the feasibility for common educational modules for education and ongoing training that can be shared in order to ensure consistent practices | a. Ongoing b. As required with new staff or changes to practice c. develop timelines at next regional meetings | J.Torode, K.Kehoe, K.Stolee
L KT2 | Identify and implement quality improvement initiatives to support best practice stroke care across the care continuum | a. Review inpatient admissions from Brockville and identify any process improvements to improve transitions and work in collaboration with BGH to jointly problem solve any issues that arise. b. Participate in adopting any changes to the Community Stroke Rehabilitation Program and provide feedback on program. c. Utilizing experience and learnings from the implementation of Patient Oriented Discharge (PODs), improve the content and utilization of patient discharge packages etc. d. Build a better understanding of patients' therapy experience in terms of intensity of treatment, frequency and other treatment factors for community PT (ie Community Stroke Rehab Program ) to better inform referrals. e. Sustain peer stroke support volunteers linked with the Perth Stroke Support Group | a. Ongoing b. As required c. Complete a consultation of patients through follow up phone calls and support service stakeholders for feedback from September -December 2019 d. Ongoing e. Ongoing | J.Torode, K.Kehoe, K.Stolee
L KT3 | Explore the role of rehabilitation assistants in stroke rehabilitation therapy delivery models. | a. Participate in gathering information on these roles across the province by providing details related to our own hospital practices. b. Participate in practice changes and local implementation pilots as required. | a. As required b. As required | J.Torode, K.Kehoe, K.Stolee

## Leadership & Coordination
Leadership & Coordination
REG | Objectives | REGIONAL and Local Implementation Activities- Leadership & Coordination | Timeline | Lead/Contact
R L&C1 | A. Plan Successions to build and mentor new leaders within the regional stroke program B. Develop Stroke Team Leadership Skills and Sustain Engagement | A. Develop and support leadership knowledge and skills as change agents (change and project management, quality improvement, evaluation). Watch for opportunities to recruit new leaders for succession planning. B. Develop Stroke Team Leadership Skills and Sustain Engagement • Sustain funded stroke centre/SPC human resource infrastructure; recruit, retain, develop staff • Support achievement of Professional Development/Goal Setting and Engagement Plans by RSC/DSC/SPC staff • Ensure each team member has opportunities to develop leadership/QI/KT/Project management skills • Continuously develop stroke team best practice knowledge through annual participation in national stroke congress; and other relevant stroke conferences - deliver at least 3 posters/presentations annually • Make use of narrative practice to communicate patient-centred care, interprofessional team expertise • Share professional development, best practice and leadership information amongst stroke teams | Ongoing Ongoing as detailed in professional development plans | C. Martin
R L&C2 | Sustain a resilient Stroke Network that is flexible and responsive to a changing provincial context. | • Sustain strong communication links with CorHealth • Remain aware of the recommendations to the MOHLTC by CorHealth Ontario in relation to the Regional reviews, potential redeployment of stroke infrastructure, • Advise on plans for changes to sustain stroke network and apply learnings to cardiac and vascular care. • Revisit the workplan to accommodate changes | expected in Year 1 with ongoing adjustments in Yr 2 | C. Martin
R L&C3 | Develop, monitor and implement Regional Stroke Workplan based on RSSC priorities and program mandate | Develop, monitor and deliver Regional Stroke Workplan Implement, monitor and sustain system change; build capacity for interprofessional expertise and knowledge translation in Best Practice Stroke Care; build transitions and connections across the continuum of care; promote use of a standard CQI approach; Support Clinical Implementation of Bundled Funding in stroke care • Report on workplan progress at each RSSC meeting (using workplan progress report and briefing notes) • Engage and support stakeholders in reporting on local aspects of workplan including bundled funding for stroke care • Sustain infrastructure required to oversee workplan • Deliver on Education/Knowledge Translation plan embedded in workplan building capacity for best practice • Continuously review evaluation data and adjust workplan accordingly with stakeholders • Set new priorities and develop next two year plan with stakeholders in 2021 | Ongoing as detailed in workplan | C. Martin
R L&C4 | Engage stakeholders in workplan priorities through an effective communication strategy | Engage stakeholders in workplan priorities through a communication strategy: • Ensure website is current and communication strategy is linked with workplan priorities • Direct stakeholders to website resources through regular updates to news page and quarterly e-news • Invest in Adobe illustrator and learn to create infographics for communication of performance and project reports • Increase photography archive for use on SE website • look for opportunities to use narrative practice and create one to two more patient stories • continue to make use of videotapes and on-line learning modules • Develop a new logo with graphic design support [HOLD until regional review changes with CorHealth] • Maintain current contact lists - check annually • Internal team communication - monthly team meetings and workplan review | Ongoing E-news quarterly Invest in Adobe Illustrator in Year 1 | C. Martin
R L&C5 | Sustain governance infrastructure for effective program oversight and stakeholder engagement | Sustain governance infrastructure for effective program oversight and stakeholder engagement • Coordinate strategic focus of Regional Stroke Steering Committee (RSSC) • Coordinate Sustain RSSC Planning Subcommittee to guide meeting planning • Maintain membership of RSSC and subcommittees/workgroups per terms of reference (TOR) • Review and revise TOR for each committee/workgroup in 2019 • Sustain stroke survivor patient advisor membership and active engagement in RSSC and related committees • Provide orientation for every new member of RSSC • Evaluate RSSC meetings using survey monkey • Perform a full evaluation of steering committee in 2019 and respond accordingly • Sustain Subcommittees and develop Workgroups as required to deliver workplan • Provide support as needed to District Stroke Advisory Council (DSAC) | Ongoing RSSC meetings 5X /year Evaluate RSSC and Revise TOR in 2019 | C. Martin
R L&C6 | Build Communication and Accountability Links with SE LHIN | Build Stroke Program Communication and Accountability Links with SE LHIN/Regional Planning Body • Sustain relationship with SE LHIN/New Regional Planning Body and connect as needed with planning & performance teams • Continue to use LHIN/Regional Planning team meetings as mechanism for effective information flow and planning for collaborative system change • Sustain LHIN/Regional Planning membership on RSSC • Ensure alignment of Stroke Network workplan with LHIN/Regional Planning Infrastructure, CorHealth Ontario and MOHLTC Priorities e.g. Bundled Funding; EVT and QBP implementation; Rehabilitation Alliance activity; LHIN IHSP; Health Links; Sub-regions • Meet annually with LHIN/Regional Planning Infrastructure senior leadership team re SE LHIN Stroke Report Card, SE Dashboard, interpretation, progress and workplan • Sustain communication with LHIN/Regional Planning Infrastructure, Designated Stroke Centres and Stroke Prevention Clinics to meet stroke HSAA accountabilities; send annual letters after SE Stroke Report Card is publicly released, highlighting HSAA indicators | Ongoing Report Card meeting May/June each year HSAA letter July each year | C. Martin
R L&C7 | Monitor and evaluate stoke care in the SE against provincial and national standards | Quality Monitoring and Evaluation (As embedded in each section of the stroke workplan) • Disseminate annual Stroke Report Card and Ontario Stroke Evaluation Report; LHIN and Sub-LHIN analysis • Ensure all stakeholders are aware of Stroke Report Card and QBP indicator reports - provincial and facility- based • Continue to develop and make use of Regional Stroke Dashboard - report quarterly and use to plan and sustain local quality improvement initiatives • Assist with data interpretation and use of data in bundled funding models • Use data to inform workplan activities and best practice implementation priorities at regional and local levels • Support data quality in CIHI project #340, #640, #740 and CIHI NRS Rehab Intensity measures • Continue to collect SPC activity and wait times on a regional basis. • [Trial NACRS lite for SPC data collection - on hold until supported by CorHealth Ontario/MOHLTC] • Sustain collaboration with RPPEO for pre-hospital data and Stroke Report • Support and Sustain annual evaluation and monitoring of Enhanced Community Stroke Rehab Program, Stroke Support Group Evaluation and Community Aphasia Conversation Groups • Consider how South East Integrated Information Portal (SHIIP) and Connecting Ontario might assist the Stroke Network and its stakeholders in informing stroke care transitions; make use of SE Data Centre • Leverage findings of CCC/LTC Evaluation Report including potential to link with research initiatives in LTC (e.g. QUILT research initiative) | Ongoing as indicated in Workplan | C. Martin
R L&C8 | Manage fiscal and human resources within given parameters | Fiscal Planning & Human Resource Management • Monitor fiscal resources and variances associated with designated stroke funding at each centre • Deliver on HAPS accountabilities for mandated stroke services • Ensure designated stroke staff deliver on Performance Agreements/Professional Development Plans and Workplan accountabilities | Ongoing | C. Martin
R L&C9 | Link with/contribute to Regional, Provincial and National Networks & Organizations regarding workplan activity; link learning back to regional activity | Provincial and National Collaboration and Linkages • Support strategic plan and workplans of CorHealth Ontario • Participate in HQO Bundled Funding Communities of Practice • Participate in Provincial Priority Workgroups (Secondary Prevention in 2019/20) • Maintain membership in Stroke Evaluation and Quality Committee and subcommittees • Participate in other provincial committees and workgroups such as Stroke Leadership Council, CorHealth EVT Steering Committee and workgroups, CorHealth Bundled Funding Workgroup, Ontario Regional Education Group-OREG, Regional Director/DSC Advisory Council, Regional Rehabilitation Coordinators,CLTC Coordinators Workgroups, Best Practice Coordinators Workgroup • Transition from Chair role on Regional Director/DSC Advisory Council and support succession plan for new Chair • Consider supporting provincial collaboration in LTC (Think Research, QUILT) • Participate in the work of the Provincial Rehabilitative Care Alliance and other provincial bodies such as RNAO • Contribute to development of new provincial resources and to updates of Educational Resource and Guidelines • Sustain partnership with Heart and Stroke Canada and contribute to National Guidelines Updates as invited • Facilitate awareness of and dissemination of resources • Maintain close communication with all stroke regions with focus on shared learning | Ongoing | C. Martin and team
R L&C10 | Contribute to innovation in stroke care | Contribute to innovation in stroke care • Attend to opportunities for funding to address quality improvement opportunities ( e.g. business case development and spread of aphasia conversation group, Indigenous Blood Pressure Screening, I-Dynaform, e-visits, EVT, Coiling) • Engage and support stakeholders in responding to these funding opportunities/calls for proposals • Support partners in stroke project implementation, evaluation and dissemination of project findings • Sustain and spread project learning to promote knowledge translation and practice change • Maintain awareness of current funded research and Clinical Trials related to stroke best practice and apply findings to workplan activities as they become relevant ( e.g.EVT, Screening Tools, TIA triage algorithms, Stroke unit utilization, Rehabilitation Intensity, Community Based Rehabilitation/Early Supported Discharge; e-health etc) • Collaborate with Queen's School of Rehab in following up on rehabilitation provider research surveys | Ongoing | C. Martin

## Education Plan 2019-20
SOUTHEASTERN ONTARIO KNOWLEDGE TRANSLATION PLAN 2019/2020 ($68,215) Updated February 16, 2019 FINAL
Program/Project |  |  | Task | Timelines | [11 empty] | Budget
| Regional |  |  | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 20 | 20 | 20
| Priorities |  |  | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar
PROJECT 1 |  | Target Audience: | [13 empty] | Project 1: Primary Care/SPC Collaborative
|  | Stroke Prevention Clinic and targeted primary care providers | Needs Survey
|  | from across Southeastern Ontario | Plan workshop | [12 empty] | Venue & Catering 58$/person x 85 | 4930
Primary Care | Primary & | Objective: | Registration | [12 empty] | CME (20$ x 85ppl) | 1700
Stroke Prevention Clinic | Secondary | Enhance implementation of secondary stroke prevention between primary care and Secondary Prevention Clinics through | Workshop Delivery | Feb: TBD | Honorariums | 2400
Collaborative Update | Prevention |  | Evaluation | [12 empty] | Teleconference | 30
|  | best practice and collaboration. | [13 empty] | Printing/supplies | 250
[16 empty] | Travel, hotel and meals | 250
[16 empty] | Advertising CME office | 350
|  | Date: TBD February | [13 empty] | Total Cost: | 9910
PROJECT 2 |  | Target Audience: Blood Pressure screeners | [13 empty] | Project 2: Deseronto Indigenous Blood Pressure Screening Program
|  | Objective: Train and support blood pressure screeners. | Workshop delivery | [12 empty] | Supplies, printing and promotion | 300
Deseronto Indigenous | Primary & |  | Screening program planning | [12 empty] | Venue/meeting space | 400
Blood Pressure | Secondary |  | Screen program advertising | Aug: Ongoing | Catering | 400
Screening Program | Prevention |  | Screening program delivery | [12 empty] | Travel | 400
Evaluation
|  | Date: Ongoing | [13 empty] | Total Cost | 1500
PROJECT 3 |  | Target Audience: Regional Stroke Prevention Clinic Staff | [13 empty] | Project 3: Regional SPC Best Practice & Process Meetings
Objective: One half day meeting designed to meet 1) best
| Primary & | practice learning needs (e.g. case study review); and 2) process | Planning Meeting | [12 empty] | Catering (25$ x 16) | 400
Regional | Secondary | needs related to the core elements self-assessment & clinic data. | Confirm speakers | [12 empty] | Holiday Inn Express Room Rental | 375
Stroke Prevention Clinic | Prevention |  | Meeting Delivery | [12 empty] | Honorarium | 1000
Best Practice & Clinic |  |  | Evaluation | [12 empty] | Teleconference | 20
Process Update Meeting | [15 empty] | Printing/supplies | 150
[16 empty] | Travel | 300
[16 empty] | QHC Covering 2 physician honorariums (800$) | 0
|  | Date: June 2019 | [13 empty] | Total Cost | 2245
PROJECT 4 |  | Target Audience: Radiology Technologists at Brockville | [13 empty] | Project 4 Diagnostic Imaging Training
General Hospital
| Primary & | Objective: Support training Radiology Technologists | [13 empty] | Michener Institute Tuition 599$ x 2 participants | 1198
Diagnostic Imaging | Secondary | at Brockville General Hospital to perform administration of | Contrast Injection Dye Course | [12 empty] | Text Books for CAMRT | 400 | bar: Apr to May; July to Sept; Nov to Feb
Training | Prevention | contrast dye for CT and CTA during vascular | 2 Online CAMRT Courses | [12 empty] | CAMRT online courses 375 x 2 courses | 750
| & | imaging required for EVT and secondary stroke prevention.
| Hyperacute | Note: Registrants are encouraged to apply to Allied Health Fund
to maximize coverage of additional expenses (e.g. Travel, hotel)
|  | Date: Spring, Fall or Winter (dates TBD) | [13 empty] | Total Cost | 2348
PROJECT 5 |  | Target Audience: BrGH, PSFDH, & QHC Physicians | [13 empty] | Project 5: Physician Update
|  | Objective: Develop medical skills in acute stroke unit care at BrGH and PSFDH. | Identify learning needs
Physician Updates | Primary & |  | Plan sessions | Aug: Ongoing | Participant bursary (~200$pp) | 1200
Acute Stroke Unit, ED | Secondary | May include site visits, Physician Champion | Deliver sessions | [12 empty] | Lunch $15/person x 40 | 600
& Critical Care | Prevention | mentoring, and skill training (e.g. tPA, telestroke, and | Evaluation | [12 empty] | Travel | 300
| & | acute complications)
Hyperacute
|  | Date: TBD | [13 empty] | Total Cost | 2100
PROJECT 6 |  | Target Audience: BrGH ED & Critical Care teams | [13 empty] | Project 6: Telestroke Planning
|  | Objective: Engagement/planning for Telestroke at BrGH | [13 empty] | Speaker honorarium | 400
|  |  | Planning meetings | Aug: Ongoing | Printing | 245
Telestroke Planning | Hyperacute | [14 empty] | Lunch $15/person x 25 | 375
[16 empty] | Travel/parking | 600
[16 empty] | Telephone | 60
|  | Date: TBD | [13 empty] | Total Cost | 1680
PROJECT 7 |  | Target Audience: Acute-rehab-comm staff developing | [13 empty] | Project 7: Integrated Transition Pathway Development
|  | integrated transition pathways in SEO. | Planning meetings | [12 empty] | Venue & Catering (39$ + tax/gratuities)x75ppl+AV) | 4824
Integrated Transition | Integrated | Objective: Support the implementation of integrated | Think Tank Event | Sept: TBD | Honoraria | 1000
Pathway Development | Pathway | transition acute-rehab-community pathways across SEO | Evaluation Monitoring | [12 empty] | Travel/Parking | 700
Support & Education | Acute - Rehab - | [14 empty] | Printing & supplies | 200
"Think Tank" | Community | [14 empty] | Teleconference | 100
|  | Date: September TBD | [13 empty] | Total Cost | 6824
PROJECT 8 | Expertise | Target Audience: 1 SLP BrGH & Front line Staff | [13 empty] | Project 8: Training in Supportive Conversation
Objective: Train Stroke Champions in Supportive
|  | Conversation skills. | [13 empty] | A2 & A3 Registration (paid by Aphasia Institute) | 0
|  | Projects Offered: | [13 empty] | Travel and accommodations x1 for A2 and A3 | 600
Training in Supportive |  | 1) Aphasia Institute Training: 1 BrGH SLP stroke champion | Confirm registrant
Conversation |  | A2, & A3 | Course participation | [12 empty] | Field Training (100$/hour) | 1000
2) Communication Training (Field Training Format)
|  | Date: June 7 Ongoing | [13 empty] | Total Cost | 1600
PROJECT 9 |  | Target Audience: PTs & PTAs (primarily focused on newer | [13 empty] | Project 9: Neuro Physio 101
grads/less experienced PTs and PTAs in acute, rehab and
|  | community. | Session planning | [12 empty] | Presenter Fee (4750$-1500$=$3250) | 3250
Neuro Physio 101 | Expertise | Objective: Highlight current thinking and evidence-informed | Confirm location | [12 empty] | Catering 65 ppl x2 days breaks | 500
|  | practice that touches on different treatment approaches, and | Advertising | [12 empty] | Printing | 200
|  | covers a variety of clinical conditions and functional impairments. | Session delivery | [12 empty] | Telephone | 60
|  | Co-hosted by SEO Stroke Network & PCH | Evaluation | [12 empty] | Travel/Parking | 370
[16 empty] | Accommodation/meals | 980
|  | Date: May 25 & 26 | [13 empty] | Total Cost | 5360
PROJECT 10 |  | Target Audience: Members of the Interprofessional | [13 empty] | Project 10: University of Alberta Stroke Rehab Certificate
Rehabilitation Team at Brockville General Hospital (OT & PT)
|  | Completing course #3 of 3. | [13 empty] | 600$ x 2 participants x 1 course | 1200
University of Alberta | Expertise | Objective: This online graduate level credit certificate is an | Register & begin courses
Certificate in Stroke |  | inter-disciplinary stroke rehabilitation program designed to
Rehabilitation |  | address the learning needs of rehabilitation clinicians across
the continuum of care. This will support quality improvement and
leadership skill development at BrGH.
|  | Date: Fall 2019 | [13 empty] | Total Cost | 1200
PROJECT 11 |  | Target Audience: Nursing, Allied Health and PSW’s working | [13 empty] | Project 11 : Brain, Body & You
in Acute, Complex Continuing Care, Community,
Retirement Homes, and LTC
Objective: Interactive modules
|  | designed to teach regulated and unregulated care providers | Select dates and location | [12 empty] | Run 2 Modules - SLC cost 80$x48 registrants | 3840
Brain, Body & You | Expertise | caring for stroke survivors and other complex patient | Confirm presenters
Modules |  | populations. Delivered through St. Lawrence College | Circulate registrations
|  | Based on the H&S manual "Taking Action for Optimal | Workshop delivery
|  | Community & Long-Term Stroke Care" (TACLS). | Evaluation
|  | Date: March 2020 | [13 empty] | Total Cost: | 3840
PROJECT 12 |  | Target Audience: Health care providers working in | [13 empty] | Project 12: LTC & Community Collaborative "Pain & Behaviour"
Community & LTC
|  | Objective: Introduction to Pain, manifestations of pain, | Plan workshop
LTC & Community | Expertise | assessment tools and non pharmacological interventions. | Advertising/Registration
Collaborative |  | Topics include pain in stroke, the 3 D's, pain and behaviour, | Workshop Delivery | bar: Apr to Mar
"Pain & Behaviour" |  | common sources of pain, assessment tools and | Evaluation | [12 empty] | Refreshment | 200
|  | non pharmacological interventions. | [13 empty] | Printing | 100
[16 empty] | Travel | 420
|  | Date: April 11 (HPE), 12 (KFL&A), 25 L&G,30 (Lanark) | [13 empty] | Total Cost: | 720
PROJECT 13 |  | Target Audience: Health care providers from across the | [13 empty] | Project 13: Southeastern Ontario Stroke Symposium
|  | continuum of care | Needs Survey
| All Priorities |  | Plan workshop | [12 empty] | Sound (1400) | 1400
Southeastern Ontario | & | Objective: Stroke Best Practice Update. Covering topics | Advertising/ Registration | [12 empty] | Venue 150 x 75$/person +AV (100) | 11500
Stroke Symposium | Expertise | identified from across the continue of care. | Workshop Delivery | [12 empty] | Honorariums | 4000
|  |  | Evaluation | [12 empty] | Teleconference | 100
[16 empty] | Printing/supplies | 1000
[16 empty] | Travel, & accommodations | 1400
[16 empty] | Parking | 220
[16 empty] | Poster boards | 150
|  | Date: Nov 27 | [13 empty] | Total Cost: | 19770
PROJECT 14 |  | Target Audience: Health care providers working in | [13 empty] | Project 14: Shared Work Day & Field Experience
stroke care in SEO. Includes Retirement Home Staff.
Shared Work Day & | Expertise | Objective: To support individual or group education needs | Advertise Program | Aug: Ongoing | Incentive to cover honoraria and costs for trainers | 4500
Field Experience |  |  | Learning Events
Evaluation Monitoring
|  | Date: Ongoing | [13 empty] | Total Cost | 4500
PROJECT 15 |  | Target Audience: All health care providers | [13 empty] | Project 15: Education Resource, Posters & Printing
across the continuum of care
|  | Objective: Make available education print materials, | Print/purchase as required | Aug: Ongoing | TACLS (T&T Manual) B&W spiral $10.66x50 | 533
Educational Resources | Expertise | and resources.
& Printing
[16 empty] | Annual CHEP membership | 100
|  | Date: Ongoing | [13 empty] | Total Cost | 633
PROJECT 16 |  | Target Audience: Health care providers working | [13 empty] | Project 16: Multi Media & Communication
across the continuum of care
|  | Objective: Website support, tools and resources needed to | Plan projects | Aug: Ongoing | Program development support:
Multi Media |  | support the development of online learning, communication | Identify supports needed | [12 empty] | Website hosting | 1250
& | Expertise | and evaluation. | [13 empty] | Infographic training & Support (25$/hr x 12 hrs) | 300
Communication | [15 empty] | Infographic program (illustrator 31 US /mos) | 480
[16 empty] | Online Meeting Software (Adobe Connect ) | 640.57
[16 empty] | Survey Monkey Team Package annual cost | 1314
|  | Date: Ongoing | [13 empty] | Total Cost | 3984.57
SUMMARY OF ACTUAL EXPENSES
[16 empty] | Project 1 | 9910
[16 empty] | Project 2 | 1500
[16 empty] | Project 3 | 2245
[16 empty] | Project 4 | 2348
[16 empty] | Project 5 | 2100
[16 empty] | Project 6 | 1680
[16 empty] | Project 7 | 6824
[16 empty] | Project 8 | 1600
[16 empty] | Project 9 | 5360
[16 empty] | Project 10 | 1200
[16 empty] | Project 11 | 3840
[16 empty] | Project 12 | 720
[16 empty] | Project 13 | 19770
[16 empty] | Project 14 | 4500
[16 empty] | Project 15 | 633
[16 empty] | Project 16 | 3984.57
|  |  |  | Sept: AVAILABLE BUDGET 68,215.00 | Total Cost | 68214.57

## Education Plan 2020-21
SOUTHEASTERN ONTARIO KNOWLEDGE TRANSLATION PLAN 2020/2021
Project # | Title | Regional Priority | Details | Timeline | [11 empty] | Budget Item | Projected Costing Breakdown | Total Projected Cost
|  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 21 | 21 | 21
|  |  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
1 | Regional Stroke Prevention Clinic Best Practice and Clinical Update Meeting | Prevention | Format: Half Day meeting Objective: 1) meet best practice learning needs (i.e case study review), 2) process needs related to core elements of SPC services Target Audience: Regional SPC Staff | [12 empty] | Project 1- Regional Stroke Prevention Clinic Best Practice and Clinical Update Meeting
[16 empty] | Venue (? Holiday Inn Express) | 500
[16 empty] | Catering- $30 (incl tax and grat) x 18 ppl | 540
[16 empty] | Honoraria | 2000
[16 empty] | Teleconference | 10
[16 empty] | Travel | 300
[16 empty] | Printing/ supplies | 150
[16 empty] | Total Cost: | 3500 | 3500
2 | Indigenous BP Screening in partnership with IIPCT | Prevention | Format: Train the trainer Objective: Train and Support BP screeners Target Audience: BP Screeners | [12 empty] | Project 2- Indigenous BP Screening
[16 empty] | Honoraria and professional fees to support training | 2000
[6 empty] | o | n | g | o | i | n | g
[16 empty] | Total Cost: | 2000 | 2000
3 | Telestroke planning BrGH- Physician Training | Hyperacute | Format: 3-hour on-site training session with Dr. Jin , run twice Objective: To educate staff at Brockville General Hospital in preparation for telestroke readiness Target Audience: Physicians working in Radiology, ED, Stroke Unit, Internal Medicine, Critical Care | [12 empty] | Project 3- Telestroke planning BrGH (Physician Training)
[16 empty] | Travel for team/ parking | 450
[16 empty] | Catering $22 X 15 ppl, twice | 660
|  |  |  | Jun: o; Jul: n; Aug: g; Sep: o; Oct: i; Nov: n; Dec: g | Teleconference | 20
[16 empty] | Printing/ supplies | 50
[16 empty] | Speaker Honoraria | 1000
[16 empty] | Total Cost: | 2180 | 2180
4 | Telestroke planning BrGH- Implementation Planning | Hyperacute | Format: Smaller engagement luncheon meetings with individual groups to plan their piece of telestroke, followed by simulation exercises pre-launch Objective: Telestroke planning and preparation for Go-Live Target Audience: ED, Critical Care, DI, Pharmacy, Labs, Switchboard, med. Records, Decision Support) | [12 empty] | Project 4- Telestroke planning BrGH (Implementation Planning)
[16 empty] | Travel for team/ parking | 1500
[16 empty] | Catering $17 x 140 ppl | 2380
|  |  |  | Jun: o; Jul: n; Aug: g; Sep: o; Oct: i; Nov: n; Dec: g | Teleconference | 25
[16 empty] | Printing/ supplies (Canadian stroke booklets, algorithm) | 200
[16 empty] | Total Cost: | 4105 | 4105
5 | Diagnostic Imaging Training- Brockville | Hyperacute | Format: Financial support for Brockville DI staff Objective: To ensure that Brockville DI staff has the skill to perform CT and CTA with contrast dye to support EVT and secondary prevention Target Audience: Radiation Technologists at Brockville General Hospital | [12 empty] | Project 5- DI Training at BrGH
[16 empty] | CAMRT CT courses x 2 ($375 x 2) | 750
|  |  |  | Aug: T; Sep: B; Oct: D | textbooks | 400
[16 empty] | Total Cost: | 1150 | 1150
6 | Physician Stroke Update for ED at PSFDH | Hyperacute | Format: 3-hour session with light meal Objective: Develop medical skills in hyperacute stroke care. Includes imaging interpretation, neuro assessment, EVT, tPA, telemedicine, prompt card. Target Audience: ED physicians at PSFDH | [12 empty] | Project 6- Stroke School PSFDH | bar: Apr; Jul to Mar
[16 empty] | Catering $15x 30 ppl | 450 | bar: Apr; Jul to Mar
[16 empty] | Travel (100km 1 way x 2 vehicles)/ parking | 100 | bar: Apr; Jul to Mar
[16 empty] | Total Cost: | 550 | 550 | bar: Apr; Jul to Mar
7 | Physician Stroke Update for QHC-ISU | Hyperacute | Format: 3-hour session with light meal Objective: Develop medical skills in stroke care, acute stroke unit care. Target Audience: Physicians who care for stroke patients at QHC | [12 empty] | Project 7- Stroke School QHC-ISU | bar: Apr to Aug; Nov to Mar
[16 empty] | Catering- $25x 30 ppl | 750 | bar: Apr to Aug; Nov to Mar
[16 empty] | Travel/ (200km round trip x 2 vehicles)/ parking | 200 | bar: Apr to Aug; Nov to Mar
[16 empty] | Total Cost: | 950 | 950 | bar: Apr to Aug; Nov to Mar
8 | ISU Workshop Brockville General Hospital | A-R-C Transitions | Format: 2 Full day workshops (repeated for target multiple staff groups) Objective: To prepare staff to work in the new Integrated Stroke Unit Target Audience: staff of the ISU | [12 empty] | Project 8- ISU Workshop BrGH
[16 empty] | Travel/ parking | 400
[16 empty] | Catering 60 ppl x $22, twice | 2640
[16 empty] | teleconference | 15
[16 empty] | Printing/ supplies | 150
[16 empty] | Total Cost: | 3205 | 3205
9 | Stroke Skills Fair QHC | A-R-C Transitions | Format: 1-day station-based stroke skills fair Objective: To provide a skills refresher/ training for new staff of ISU Target Audience: All nursing and allied staff working on ISU | [12 empty] | Project 9- Stroke Skills Fair QHC
[16 empty] | Travel/ parking/ teleconference | 100
[16 empty] | Catering -35 ppl x $22 | 770
[16 empty] | Total Cost: | 870 | 870
10 | Navigation Workshop | A-R-C Transitions | Format: half day event starting with lunch, speakers, followed by brainstorming Objective: to network and plan the role of navigation and the utilization of the navigation toolkit Target Audience: care providers working in acute, rehab, community care and community support | [12 empty] | Project 10- Navigation Workshop
[16 empty] | Venue | 2800
[16 empty] | Catering 85 ppl x $30 | 2300
[16 empty] | Teleconference/ parking | 50
[16 empty] | Printing/ supplies | 450
[16 empty] | Honoraria | 600
[16 empty] | Travel | 300
[16 empty] | Total Cost: | 6500 | 6500
11 | Training in Supportive Conversation | All/ Expertise | Format: Aphasia Institute Courses, Communication training (field work style) Objective: Train Stroke Champions in Supportive Conversation skills. Target Audience: New PCH SLP, other front-line staff and volunteers | [12 empty] | Project 11- Training in Supportive Conversation
[16 empty] | Aphasia Institute A2/A3 registration (1 free, 1 paid) | 988
[16 empty] | Travel, accommodation and meals for A2/A3, 2 people | 1500
|  |  |  | Jun: o; Jul: n; Aug: g; Sep: o; Oct: i; Nov: n; Dec: g | Aphasia Institute D3 registration | 613
[16 empty] | Travel, accommodation and meals for D3 | 600
[16 empty] | Field training for volunteers @$100/ hr | 1600
[16 empty] | Total Cost: | 5301 | 5301
12 | Brain, Body and You | All/ Expertise | Format: Interactive modules offered as a partnership with SLC Objective: to deliver the TACLS content to staff caring for stroke and other complex patients Target Audience: regulated and unregulated staff of LTC/ RH's | [12 empty] | Project 12- Brain, Body and You | bar: Apr; Jun to Oct; Dec to Mar
[16 empty] | Run 2 modules in Brockville (spring 2020) | 3840 | bar: Apr; Jun to Oct; Dec to Mar
[16 empty] | Run 4 modules in Kingston (fall 2020) | 7680 | bar: Apr; Jun to Oct; Dec to Mar
[16 empty] | Content update consultation fees | 500 | bar: Apr; Jun to Oct; Dec to Mar
[16 empty] | Total Cost: | 12020 | 12020 | bar: Apr; Jun to Oct; Dec to Mar
13 | LTC & Community Collaboratives | All/ Expertise | Format: half-day in-person sessions offered in 4-5 locations Objective: Topic TBD- provide information about the complexity of stroke patients living in LTC Target Audience: Health care providers working in community and LTC | [12 empty] | Project 13- LTC & Community Collaboratives
[16 empty] | Refreshment | 225
[16 empty] | Printing/ supplies | 100
[16 empty] | Travel/ parking/ teleconference | 450
[16 empty] | Total Cost: | 775 | 775
14 | Designing Exercise Workshop | All/ Expertise | Format: 1-day workshop with Jacquie Levy and Wendy Sarsons Objective: To enhance the skill of those who design and implement fitness programs for stroke survivors Target Audience: Community and LTC health care providers including recreation therapy, PT/PTA's, health promoters and trainers, restorative care aides | [12 empty] | Project 14- Designing Exercise Workshop
Venue (Founders Hall at PCH)
[16 empty] | Catering ($22 x 40 ppl), through PCH) | 880
[16 empty] | Teleconference/ parking/ travel for team | 500
[16 empty] | Printing/ supplies | 75
[16 empty] | Honoraria | 2500
[16 empty] | Travel/ accommodations/ meals for speakers | 600
[16 empty] | Total Cost: | 4555 | 4555
15 | Community Expo Belleville | All/ Expertise | Format: Half day event Objective: To increase local stroke care providers' awareness of resources and services in their area Target Audience: all stroke care providers in the QHC region | [12 empty] | Project 15- Community Expo Belleville
[16 empty] | Venue (Maranatha Church) | 500
[16 empty] | Catering $15 x 80 ppl | 1200
[16 empty] | Printing/ supplies | 300
[16 empty] | Honoraria | 500
[16 empty] | Teleconference/ travel/ parking for team | 100
[16 empty] | A/V ($240), custodia $60, linens ($100) | 400
[16 empty] | Total Cost: | 3000 | 3000
16 | Shared Work Day/ Field Experience | All/ Expertise | Field Work Experience Projects: | [12 empty] | Project 17- Shared Work Day/ Field Experience
|  |  | Exercise providers session with Shannon | [13 empty] | 200
|  |  | Nursing skills sessions at PCH | [13 empty] | 600
|  |  | Healthline webinar (with Rebecca Phillips) | [13 empty] | 0
|  |  | Vision Therapy collaboration with Zoe Briggs- QHC | [13 empty] | 500
|  |  | Vision Therapy collaboration with Zoe Briggs- PCH | [13 empty] | 500
|  |  | Art Therapy Field experience for OT's/ volunteers PCH | [13 empty] | 200
|  |  | Shared Work Day s, additional Field Experiences | [13 empty] | 2400
[16 empty] | Total Cost: | 4400 | 4400
17 | Multi-media and Communications | All/ Expertise | Format: Objective: purchase of tools and resources to support the development of online learning, information sharing, communication and evaluation Target Audience: all stroke care providers across continuum of care in our region | [12 empty] | Multi-media and Communications
[16 empty] | Website hosting/ mailgun | 850
[16 empty] | Adobe Illustrator $533 per person, x 2 | 1066
[16 empty] | Adobe Connect | 850
[16 empty] | Survey Monkey | 1800
[16 empty] | Total Cost: | 4566 | 4566
18 | Education Resources and Printing | All/ Expertise | Format: Objective: to make printed information and education resources available Target Audience: all stroke care providers across continuum of care in our region | [12 empty] | Education Resources and printing
[16 empty] | TACLS manuals (B/W spiral) $12.66x 50 | 633
[16 empty] | Annual CHEP Membership | 100
[16 empty] | TACLS Posters ($75 for one set of 3 panels) x 12 | 900
[16 empty] | other printing? | 300
[16 empty] | Patient Journey Map Posters | 500
[16 empty] | Total Cost: | 2433 | 2433
[16 empty] | Cost Summary: |  | 62060